## Action Items (hidden)
MVP RELEASE ACTION ITEMS
Actions: | Size | Status | Assignee:
Finalize Wording of AWP Investment & Benefits Tab | Large | Complete | Andrew
Finalize Getting Started Tab | Small | Complete | Josh
Finalize Where to Go Next Tab | Small | Complete | Josh
Reformat Where to Go Next Tab | Small | Complete | Josh
Finalize Measuring AWP Success List | Medium | Complete | Josh & Andrew
Clean up AWP Benefits Descriptions | Medium | Complete | Andrew^2
Review of Measurig AWP Success Updates | Small | Complete | Cory
Review Acknowledgements Tab (Update from survey) | Small | Not Started | Jintae
Reformat Measuring AWP Success Tab | Medium | Complete | Jintae
Final Clean-Up and Styling (Add CII Logo, and colors throughout) | Small | Complete | Mandi
Future "Post MVP Release" Actions:
Align with Business Accelerator (AWP Maturity and Capabilities Assessment Tool)
Add Quantitative Component
Templates / Checklists as a tool for companies to use? (Align with Assessment Tool)
Quantitative ROI Tool Next Steps:
Simple inputs (accessible to high level execs and people new to AWP)
Advanced inputs (scaffold, Modules, etc) for people that want to go to the next level
Contract Strategy complexities (who makes which investments, who gets which benefits, does this impact the level of AWP achieved?)
Connecting Returns to Metrics to help people monitor outcomes against expectations
RFI Costs Reduction by type
Tool Time Productivity Increase
Unit Rate Productivity Increase by discipline
Scaffold efficiencies
Rework Reduction
Connecting Investments to People, Process, Technology investments here
Additional WorkFace Planners
Additional AWP Champion
Additional Engineering upfront
Software

## Getting Started
GETTING STARTED
Description and Purpose
This tool is designed as high-level guidelines to assess the level AWP implementation maturity on a single project setting, rather than an organization as a whole.
Additionally, this tool will help identify potential investments and benefits associated with the project at its current standing or at the next level of AWP implementation
This tool is not designed to quantify the benefits or investment that you would expect to see from implementing AWP or increasing the level of AWP on a project.
Project teams that are implementing AWP for the first time should not expect to see the same benefits as project teams that are experienced with AWP
This tool will work for projects of all sizes. It is a myth that AWP is only viable on large projects. This tool can be used with small cap brownfield projects, mega projects, and everything in between
This tool is also meant to help educate on the idea that AWP is not an all or nothing endeavor. There are levels of AWP and the amount of investment required to reach those levels as well as the benefits that can be expected from each varies. This tool can be used to evaluate the process of taking a "crawl, walk, run" approach to AWP where AWP maturity is increased over a series of projects. This process of meeting project management teams where they are in AWP maturity allows the team to reduce the large change management challenge to a series of smaller, more manageable changes.
Instructions on How to Use the Tool
1. Review the descriptions for each AWP implementation category and identify which one most closely aligns your project. Each AWP Implementation Category will contain following information:
Please be aware that descriptions for each of the levels are holistic suggestions, not requirements. Projects not completing a singular item in the long description does not exclude the project from being assigned to the corresponding implementation level. Similarly, project completing a single item from a higher category should not justify assigning the project to the said level.
Information | Column | Note
Category Name | A | Name of the level of AWP in use on the project
Category Description | B-C | Short and long description about each implementation category
Typical Technology Stack | D | Lists the technologies that are usually used at this level of AWP maturity
Investment | E-F | Description and sizing of investments needed for each implementation category
Value (or Generated Benefits) | G-L | Timing, recipient, type, sizes and description of the benefits associated with each AWP implementation category
Good Project Delivery | M | Defines what is done on a good project when AWP is not used
AWP Delivery | N | Shows the distinction between doing good standard project execution and doing AWP project execution
2. Review each category descriptions and typical technology stack (Column B, C and D) to identify the category which most closely aligns with the project you are trying to assess
3. Filter out column A based on the AWP implementation category which the project is most aligned with
4. Examine investment and value associated with the category
Expected Outcomes
After using the tool you should have achieved the following:
1. Organized a committee to review the tool, perform evaluations, and record outcomes
2. Have collected available industry information and case studies
3. Have identified the category of current practice (A through D)
4. Have identified value scenarios of interest and applicable to the organization
5. An understanding of a desired future state and investment implications
6. Have created an initial ROI for leadership consideration

## AWP Investment & Benefits
|  | AWP INVESTMENT & BENEFITS |  | Disclaimer Below are general statements on indications of implementation category, rather than a strict-guideline. For instance, project not completing a singular item in the long description does not exclude the project from being assigned to the corresponding implementation level. Similarly, project completing a single item from a higher category should not justify assigning the project to the said level.
Category | Short Description | Long Description / Example | Typical Technology Stack | AWP Investment | AWP Investment ($) | Value Phase | Benefit Role | Benefit Category | Return ($, $$, $$$) | Value Summary | Value Description | Good Project Delivery | AWP Project Delivery
Category A - Traditional | No AWP Principles | Project operating in a traditional manner without AWP Principles Legacy processes are used, which do not incorporate AWP Foremen are issued drawings in the field Work is planned and tracked using scheduling tool | Scheduling Tool Progress Tracking Tool Cost Tracking Tool Materials Management Tool Procurement Tool Engineering Design Tools Document Management Tool | N/A |  | N/A |  |  |  | N/A | N/A | N/A | N/A
Category B - WFP | Workface Planning | Construction Workface planners are in place and begin development of IWPs upon receipt of issued for Construction (IFC) drawings from engineering Construction is executed using IWPs for key disciplines (Pipe & Steel) only | Scheduling Tool Progress Tracking Tool Cost Tracking Tool Materials Management Tool Procurement Tool Engineering Design Tools Document Management Tool Non-Graphical Tool capable of creating IWPs for Pipe & Steel Basic VCM capable of viewing 3D Model | People - Added FTEs: Workface Planning Lead Discipline Workface Planners Additional Cost of Meetings: CWP Review Meetings WFP Requirements for Contractors Process - Training: Awareness training for site supervisors Workface Planning training for Workface Planners Procedures: Workface Planning procedure development Guidelines Package templates Communication aids Contracts: Contract Language Development - Workface Planning Technology - Non-Graphical Tool capable of creating IWPs for Pipe & Steel capable of adding 3D Model Shots | $ | Construction | Project Controls | Predictability | $$ | Monitor Progress with Minimal Effort | Using an IWP breakdown during Construction will provide a more detailed and granular tracking system for monitoring progress. Instead of tracking progress at a discipline level, using high level quantities, it can be tracked directly based on the IWP progress, using the detailed quantities tied to the estimate. By incorporating the IWPs into the construction schedule, this physical progress can be easily aligned to schedule progress. | Progress is typically captured at the discipline level, using a high level quantity tracking (such as linear feet of pipe installed). | IWPs will contain detailed work scopes, tied to the project estimate on a quantity basis. Progress does not rely on rules of credit, but can be a simple checklist of activities completed. By tying progress to the IWPs on a weekly or biweekly basis, a more accurate picture of progress is available sooner. This approach provides more assurance on quality of tracking/quality of data, as well as timeliness, repeatability, and accuracy of data.
[6 empty] | Construction | Quality | Alignment | $ | Improve auditability | When reviewing CWPs with a view to breaking them into IWPs, the Workface Planners can provide feedback on CWP content, to help close any upstream gaps for subsequent packages. For the Workface Planning, tracking the IWPs in a Release Plan will provide up-to-date information about the status of each package, which will allow for easy summary of available hours of work (backlog), progress (by package, area and discipline) and performance. IWP information can be summarized in KPIs to provide an overview of the effectiveness of the Workface Planning effort. | Having an audit plan in place and well staffed. Audits are typically carried out at the discipline level. | Standardized and organized information facilitates auditing, as well as measuring the impact of decisions / actions. AWP provides granular information for tracking and monitoring, which easily lends itself to auditing field performance and workface planning KPIs.
[6 empty] | Construction | Construction Management | Schedule | $$ | Leverage virtual construction model for status, planning and execution | A 3D model, even if not used for graphical packaging, can have significant benefits for workface planning. It can be used to simulate the path of construction, either for the whole project, or subsets for area reviews. A color overlay can be used to represent availability of material or drawings, using Excel reports. It can be used to represent field progress, giving an excellent tool for verification and audit. And model shots, included in IWPs, will give the installation crew an accurate understanding of the scope. | Typically, the model is used primarily for Engineering. When used in Construction, it is typically just as a view of the scope. | Support Path of Construction planning at the project or CWP level. Can be used for tracking and monitoring per work package. The use of a graphical tool, even if not for packaging, can increase the value of the IWPs, by making the scope more clear to the crews. And by using the model to show availability of engineering and materials, the planners can focus their efforts in the right areas, or highlight problems which can be addressed earlier.
[6 empty] | Construction | Construction Management | Cost | $$$ | Execute Constraint Free IWPs in the Field (including planning, management, tracking/punch improvements) | AWP is about getting constraint free work in the hands of the foreman…they are the customer. AWP project value includes: all material in hand, plans in place, tools ready and available and planned for safe execution. | Basic grouping of work scopes by discipline and crew capability, often limited to separation by large area and working from a stack of drawings. | AWP forces constraint free packages and the related project value improvements in planning, productivity improvement and alignment. Constraints are visible, known, tracked and closed. Giving the field installation crews constraint-free packages will allow them to be more efficient in their work, reduce downtime, increase tool time, and improve crew morale.
[6 empty] | Construction | Supply Chain | Alignment | $$ | Reduce Materials Chaos at Site / Yard (including information/tracking/locating) | The workface planning implementation can be augmented with tools to help with material management. Tagged materials are received against the EWP or CWP, and assigned to the IWP. Bulk materials can be managed on a min/max system and assigned to the IWPs by priority. Other tools can assist with traceability and location accuracy for materials by leveraging RFID or other active / passive tagging methods. | Material managed at the project / site level, with only a basic discipline split. Tagged items not assigned to a specific package. | Setting Path of Construction early in the project so purchasing can schedule material to arrive per the construction Required At Site (RAS) date. Material availability can give workface planners insight into material constraints. Material can be assigned to specific IWPs and tracked in the field prior to starting any work. Materials can be "bagged and tagged" and made available for a specific IWP scope at a pre-agreed time and date.
[6 empty] | Construction | Construction Management | Alignment | $$ | Improved visibility - Work package level tracking and constraint management (supporting better decisions) | Workface planning provides a more detailed and consistent understanding of project status in the field. The visibility provided can include: Backlog - how much work is available (constraint free) per discipline. Progress - detailed progress at the discipline / area / foreman level. Performance - actual hours by IWP will allow for performance information at the discipline / area / foreman level. | Progress and performance are typically limited to a discipline level. Backlog data is more difficult to understand, if available at all. Issues can often only be found immediately before they are an impact. | Workface planning improves communication, facilitates earlier decision making and more effective crew planning for safer, efficient installation.
Category C - AWP | Advancing Construction into FEL 2 and FEL 3 (early engineering phases) | Front End Loading Earlier engagement of stakeholders for development of a Path of Construction as input into the project schedule CWP and EWP Boundary Creation (CWAs) High Level Alignment of execution between Path of Engineering and Path of Construction Constructability process leveraging Path of Construction is utilized for early construction input Detailed Design Constructability process is used to update design plans in real-time based on constraints EWPs are used to organize and track Engineering Deliverables Procurement Material RAS dates feed from Construction Planning Material availability feeds status visualization and WFP Construction CWPs are developed, sequenced and released as part of construction management process Graphical & Non-Graphical WFP is used to create IWPs for all disciplines | Scheduling Tool Progress Tracking Tool Cost Tracking Tool Materials Management Tool Site Materials Management Tool Procurement Tool Engineering Design Tools 3D Modeling Engineering Tool Document Management Tool 4D Sequencing Tool for Path of Construction Development and Review Sophisticated VCM capable of creating both graphical and non-graphical IWPS VCM is integrated with materials management tools for status visualization in the model, and one-way integration with scheduling tool Field mobility tool for accessing IWPs and progressing in the field | People - Added FTEs: Workface Planning Lead Discipline Workface Planners AWP Manager Model / Data Manager Earlier Engagement of: Construction Manager Supply Chain Manager Commissioning and Startup Lead Additional Cost of Meetings: Interactive Planning Meetings Path of Construction Team Alignment AWP Requirements for Contractors Process - Training: Awareness training for key project stakeholders Champion training for project leadership Engagement training for key executors Oversight / compliance activities Procedures: Policies and procedures update RACI chart development Guidelines Package templates Communication aids Contracts: Contract Language Development Technology - 4D sequencing tool for planning and review Virtual Construction Model for creation and management of IWPs Field mobility tool for IWP and progress review in the field AWP Master Index | $$ | All Phases | Project Controls | Predictability | $$$ | Increase Project Visibility | The AWP breakdown will increase the project's granularity, by making the project a series of mini projects. This will provide a tighter set of deliverables (as they are focused on a single area), and will improve the accountability for the deliverables. Using this breakdown, and tying it to the project schedule, will give an earlier indication of when project deliverables are slipping, which will allow for earlier corrective actions. | Track Project Progress using earned value and quantity S-curves. | Track project progress by package close out to get an accurate understanding of the true progress as well as the ability to accurately forecast future issues. Increased visibility of project status at a more understandable, granular level.
[6 empty] | All Phases | Project Management | Predictability | $$$ | Increase proactive management, including better evaluation of alternatives/solutions to problems | AWP provides better visibility, which in turn supports better and earlier decisions - the project sees a shift from reactive to proactive. It also provides an increase in the accuracy of information, which allows for better prediction/forecasting - the project team can explore alternatives, and see what the issues are sooner. This enables more proactive management, which in turn enables better planning and less field re-work. This has a positive link to improved safety and quality outcomes. | Improved trending and forecasting based on status. Forecasting that links across phases (e.g. monitoring PO timing to predict site delivery dates) | The timeliness and availability of up to date and detailed information will allow the project team to react faster to many situations and correct a number of execution issues before they create a critical impact on project outcomes.
[6 empty] | All Phases | Project Management | Alignment | $$$ | Improved interface management/assignment of responsibilities | AWP better defines interfaces between project stakeholders, by identifying the deliverables for each package, and the link between the Engineering, Procurement and Construction components. By understanding the deliverables and interfaces, and highlighting those interfaces in the schedule, improvements in accountability can be achieved. A truly integrated schedule with well defined deliverables between stakeholders will lead to improved project predictability. | Good definition of RACI charts and interface management plan. | Adding work package level constraints and needs to the RACI assignments, increasing the visibility and clarity around timing of information needs and interface points. More accountability for visibility, completeness, accuracy, and timeliness of information transfer.
[6 empty] | All Phases | Quality | Alignment | $ | Improved feedback/lessons learned at all cycles; supports continuous improvement | Using the AWP approach will bring the project stakeholders together earlier in the project lifecycle, allowing more timely discussions and interactive review of project plans. This will also help in understanding learnings through each phase of the project, as more detail becomes available and project plans are refined. In doing so, the project team can collaboratively review feedback and lessons learned from each phase. Lessons learned at a package level can be applied to other packages, rather than waiting for the next project. | Closeout of lessons learned per project phase and per success or challenge. Often only carried out at the end of a project. | AWP allows for a specific, granular capture of the lessons learned at the work package level, creating opportunities for receiving earlier and more detailed feedback.
[6 empty] | All Phases | Project Management | Alignment | $ | Develop high performance teams | AWP fosters greater collaboration between project stakeholders, who are required to share information earlier and more consistently, to drive the project towards its goals. This enhanced collaboration provides a greater emphasis on team development, and creates early alignment between the team members. | Alignment and team development are often based on procedures and supported by informal practices. | AWP supports early involvement of multiple stakeholders for effective planning and can increase communication through the use of work packages as information vehicles.
[6 empty] | All Phases | Project Management | Alignment | $$ | Increased owner communication | AWP supports increased ability to track and manage deliverables at the work package level - this means better reporting and better accountability with owners. This works both ways - AWP can make clear owner requirements for decision making and input/direction to the project team. AWP ensures stakeholders have clear definition and agreement about project scope, priorities, etc. This supports all benefits, but most clearly is associated with Alignment and Predictable outcomes. | Undertake alignment activities between the owner and other stakeholders. Identify key deliverables and decision points for the owner based on project-specific needs. | AWP can provide insight and detail regarding interfaces and information flow between Owners and Contractors. The work package breakdown can be used to make clear owner or contractor requirements for decision making and input/direction to the project team.
[6 empty] | Pre-FEED/FEED (FEL) | Supply Chain | Alignment | $$ | Increase support for prequalification | For AWP to be successful, it is important to have contractors with experience and willingness to use AWP. As part of the AWP breakdown, it is useful to break work into relevant contract packages, to align to the capabilities of each contractor. Not being an AWP expert contractor / service provider does not disqualify, but that contractor must show willingness to learn. Pre-qualification should detail clear expectations for AWP, including KPIs such as IWP backlog. | Assessment of historical performance, relating to safety, quality, cost and schedule. These are used as indicators of acceptable performance and possible indicators of future performance. | Tailor the contract package with more granular detail to understand the contractor's ability to perform that specific scope, rather than just in general. Can the contractor meet the need? For areas of contractor weakness, you can identify where they will need support.
[6 empty] | Pre-FEED/FEED (FEL) | Project Management | Predictability | $$ | Increase likelihood of moving to next steps/gates through better planning | Higher quality and certainty in the schedule and estimate, particularly considering the alignment of those two elements. Adopt an AWP strategy to increase the likelihood, particularly in contracting terms, to get all parties aligned on key expectations and deliverables early in the process. Detailed Path of Construction can help to support assurance reviews and show alignment with engineering and procurement. It can also facilitate better risk management and assessments. | Rigorous use of assurance reviews and peer/third party assessments to determine project suitability to advance to next stage. Lots of reliance on standard estimating and scheduling processes. People working in a vacuum or silo. | Improved interactive planning, collaboration and early involvement of all parties, to provide added assurance and certainty around the key deliverables, such as the schedule and the estimate. Additional certainty when going through project assurance reviews / gates that construction inputs have been considered, and that the integrated schedule is achievable.
[6 empty] | Pre-FEED/FEED (FEL) | Supply Chain | Cost | $$$ | Optimize use of modularization/pre-fabrication | A detailed path of construction, conducted as part of an early engagement of construction personnel, will help to verify (or refute) the possibility of modularization from a schedule perspective. (Can engineering and supply chain support modularization within the project schedule?). This will help to align supply chain to the path of construction, particularly for equipment modules. Prioritize modules in the sequence to support the field path of construction. Separate module work packages can be incorporated into the schedule to verify the plan, to ensure that earlier IFC drawings and materials can be provided. | Generally assessed and refined later in the project. Mostly an engineering effort, without full focus on impacts to procurement and construction. Used to help mitigate project risks. | Early alignment of procurement and engineering with the fabrication and construction installation sequence to ensure that the planned modularization effort and level of modularization can support the optimal path of construction. Additional review of module sizes, to consider logistics and crane requirements. Reduces the impact of late changes with construction working to optimize the engineering plan for modules. Better specificity of EWPs and CWPs for module scope.
[6 empty] | Pre-FEED/FEED (FEL) | Information Management | Alignment | $ | Optimized solutions/improved work packaging technology stack | Understanding the complexity and scalability of the project early on will help to guide the selection of the work packaging technology, and will allow the AWP program to be fit-for-purpose. Early understanding of AWP requirements will allow for definition of data requirements, which will assist with data transfer / exchanges later in the project. | All contractors will use their proven technology to perform their scope to the best of their abilities, with limited data transfer. | Technology and data alignment allows for leveraging of all project information, moving away from transactional information transfer, allowing the project team to use all available information to make the best decisions. Earlier adoption of technology allows for a better planned approach to mobilization and avoids possibility of last minute rush to implement.
[6 empty] | Pre-FEED/FEED (FEL) | Project Controls | Schedule | $$$ | More accurate and achievable schedules | Path of construction development and refinement helps support the schedule basis. Interactive planning and early involvement of key stakeholders provides early definition of timing and constraints, allowing for a more detailed schedule with collective buy-in. The schedule at the end of FEED(FEL3) should be level three - to CWP level. Increased granularity will allow for better definition of interfaces between stakeholders and more finish-to-start relationships, rather than relying on assumed percentages for activity transfer. Helps to support or refute timing of mobilization, to ensure that work is ready to be performed. | Built on previous performance and benchmarking information. Relies heavily on project controls team pulling together disparate elements. Integrated schedule with E,P,C interface points clearly identified. | Promoting interactive planning, with all stakeholders included, allows for earlier and more systematic understanding of all possible constraints to the schedule. This helps to remove the 'optimism bias' and ensure that all parties that have deliverables can provide input, which fosters buy-in and acceptance of the plan. Ensures that engineering and procurement are feeding the path of construction, and highlights the interface points between the stakeholders. Helps to avoid the delay and then deluge of information.
[6 empty] | Pre-FEED/FEED (FEL) | Project Controls | Schedule | $$ | Increase confidence in resource requirements for execution | AWP provides earlier and more assured manpower loading requirements, based on the detail in the schedule being supported by the granularity of the estimate. Schedule activities are defined by detailed quantities and discrete packages, which allows for early identification of conflicts and manpower density. Allows for early comparison with market manpower availability. Resource loading by CWP helps to clearly communicate the project scope to the contractor(s). | Use the schedule and estimate to create a project-level resource loading. | Each work package will have a discrete number of manhours and a schedule duration, which gives better definition and clarity on the resource requirements. Allows better understanding of crew flow between packages and possibility of overlap, as well as easier definition of schedule lags between disciplines. Helps to support engineering loading by providing a realistic construction resource plan, for engineering to 'feed'.
[6 empty] | Pre-FEED/FEED (FEL) | Supply Chain | Schedule | $$ | Improve quality of long lead decisions (timing/choice) | Path of construction will identify the need for long lead items, and allows for prioritization of the items, using backwards pass scheduling. Early identification will also allow for earlier discussions with suppliers to understand if deliveries can be improved, or reserve space in the manufacturing queue. More assurance on hitting the manufacturing window cuts down on supplier uncertainty, which can improve bids for accuracy and cost. | Based on assumed definition of long leads. Construction input will be limited to assessment of that against the agreed schedule. Proactive management of long lead items, and procurement efforts to adhere to or improve the schedule. | A detailed Path of Construction, carried out early in the project, will provide a much earlier understanding of the impacts of long lead equipment timing. The path of construction can be used to accommodate / optimize long lead order timing. This will provide a more realistic Required At Site date, ensuring that long lead items are not purchased before they are needed, leading to additional storage and preservation costs.
[6 empty] | Pre-FEED/FEED (FEL) | Construction Management | Alignment | $$ | Improve quality of execution plan | Getting construction management personnel onto the project earlier will improve the path of construction. Higher levels of collaboration between stakeholders, to allow everyone to provide relevant details, will gain early alignment on the plan. All stakeholders are heard and involved. Early identification of execution risks and constructability allows for improved mitigation plans and less design rework. Improves visibility of deliverable dates and improves accountability to the agreed dates, allowing for better definition of roles and responsibilities. | Detailed execution plan completed before funding request, to support the assurance review. | Path of Construction becomes the basis of the execution plan, providing an earlier opportunity for Construction to outline the optimal strategy, before the project team have gone too far along the process. Increased project confidence and ability to communicate clear and consistent plan to all stakeholders / suppliers / contractors.
[6 empty] | Detailed Design | Engineering | Cost | $$$ | Reduce Engineering inefficiencies during Detailed Design (reduction in RFI's, reduce engineering rework) | Using AWP will require that Engineering deliverables are prioritized and sequenced to support construction, which could introduce some minor inefficiency over a purely engineering-driven engineering process. This inefficiency is greatly limited with earlier identification of the Path of Construction and good collaboration with the Engineering contractor. Better information exchange with construction as well as earlier identification of issues reduces the inefficiencies around RFIs and engineering rework which is particularly costly due to context switching. | Good design review and engineering approval processes are in place. Engineering teams establish internal quality checking procedures. Engineering works toward optimum sequence for engineering efficiency. | Early alignment of Engineering including construction. This early team engagement of construction results in reduced RFI's and engineering rework and improves team engagement. Construction participates in model reviews for input and understanding of scope.
[6 empty] | Detailed Design | Engineering | Schedule | $$ | Engineering schedule (Path of Engineering) supports Path of Construction | As part of the AWP process, Engineering will prioritize their deliverables in order to support Construction. This involves a Path of Engineering that aligns with the Path of Construction. Increased alignment between engineering and construction leads to construction efficiencies by removing or limiting engineering-related constraints. | Engineering utilizes best practices for optimizing design for engineering efficiency. | The Path of Construction leads to development of an engineering schedule aligned with planned construction activities through building of Engineering Work Packages aligned with Construction Work Packages. Construction and Engineering work closely in an interactive development of the schedule. Also allows for better understanding of interfaces between Engineering and Construction.
[6 empty] | Detailed Design | Engineering | Cost | $ | Minimize engineering waiting (prevent staffing inefficiency due to out of sequence engineering activities) | Better visibility into engineering requirements allow for more efficient discipline-specific staffing to keep staffing levels in line with requirements. Engineering teams are working on the right deliverables to support construction, rather than just ramping up to achieve a percent complete target. | Engineering staffs in order to maximize engineering output. Engineering works on the available work front. | Engineering staffing requirements are better known and aligned with construction. Engineering staffing model supports demand of overall project schedule. Overall engineering output may decrease in efficiency but this is more than compensated by delivery of what is needed.
[6 empty] | Detailed Design | Supply Chain | Schedule | $$$ | Clarity for procurement (streamline work with knowledge of what/when) - Path of Procurement supports Path of Construction | As part of the AWP process, Procurement will prioritize their deliverables in order to support Construction. This involves a Path of Procurement that aligns with the Path of Construction. Increased alignment between procurement and construction leads to construction efficiencies by removing or limiting procurement-related constraints. | Procurement aligns with the project schedule and milestone dates to ensure deliveries in support of the project. | Procurement is included in the creation of the Path of Construction to share key equipment dates and ensure that they meet the requirements of the Construction Work Packages. The Virtual Construction Model becomes a tool for communicating material status to workface planning. Real-time material status available to support planning and construction readiness. Early identification of material delivery issues.
[6 empty] | Detailed Design | Supply Chain | Cost | $ | Lower project materials costs (potential to optimize purchase of bulk material items, reduced waste) | Improved and earlier visibility into true material requirements enables procurement to reduce over-purchasing. Reduced project cost through optimized material sourcing/quantification. | Less scope clarity early in the project results in over-purchasing or contractor material purchasing that increases inefficiency. | Scope is further defined prior to purchasing which reduces the need to over purchase or push purchasing to contractor. Note, if purchasing is completed in more steps (per package), bulk material savings could be less.
[6 empty] | Detailed Design | Supply Chain | Cost | $ | Reduce/optimize inventories | Reduction of material storage and preventative maintenance costs resulting from more accurate material requirements in terms of quantities and construction need dates. Higher visibility into material status and reduced material contingency. Reduced storage and preventive maintenance cost. | Materials, especially long-lead items, are ordered with plenty of delivery float to ensure that construction productivity is not impacted. | Alignment between E&P and construction allows delivery float to be minimized which reduces storage, handling, and preventative maintenance costs.
[6 empty] | Detailed Design | Project Management | Predictability | $$ | Better visibility into engineering and procurement status | Improved visibility and measurement of engineering and procurement progress enables earlier intervention for corrective action as well as ability to optimize processes through meaningful metrics. | Engineering and procurement progress is tracked using s-curves. Engineering readiness often "sits" on 99% complete for extended periods of time. | Progress is tracked by package closeout providing a more accurate view of progress. Engineering status is available in a more meaningful view for other project roles such as construction. More visual status is available. For example, availability of materials and engineering information overlaid on the Virtual Construction Model
[6 empty] | Pre-FEED/FEED (FEL) | Construction Management | Schedule | $$$ | Early project phases benefit from requirement for construction role and interaction through POC | Involvement of construction, Startup and Operations in the early phases of the project leads to earlier identification of issues that would otherwise manifest as expensive rework. Also enables facility to start up earlier leading to increased operational and earlier revenue capture benefits. This ties in with Constructability, which is detailed further in the CII Best Practice for Constructability (RT-034, RT-003) | Construction, Commissioning and Operations are typically engaged later in the project and even as late as the punchlist process which leads to expensive re-work. | Construction, Commissioning and Operations are involved throughout the interactive planning, path of construction and constructability reviews, enabling the capturing of input before detailed Engineering or Procurement activities have started, and before construction has been performed.
[6 empty] | Pre-FEED/FEED (FEL) | Construction Management | Schedule | $$$ | Constructability starts early and is more continuous | AWP will help to provide a focused constructability process leveraging better division of work and enhanced 3D/4D visibility. This leads to earlier identification of issues that would otherwise manifest as expensive rework. | Constructability is utilized but may be an event at the beginning or end of detailed engineering and prior to construction. Not continuous through FEL. | Constructability begins with early alignment during FEL and becomes the basis for Path of Construction. Constructability input leads to improved project scoping and improved estimate accuracy, improved schedule, and minimizes late changes.
[6 empty] | Detailed Design | Project Management / Supply Chain | Cost | $$ | Reduction in change orders, due to clarity of scope | Procurement process for change orders is greatly streamlined through better visibility for both owners and contractors into the exact scope and impact of changes. | Change orders are common and expensive. | More defined scoping leads to improved transparency which improves bidding accuracy and cost accuracy. Bidding can become more competitive. The number of changes orders are decreased, and potential changes are identified and mitigated earlier.
[6 empty] | Detailed Design | Engineering | Cost | $ | Potential to reduce some engineering deliverables | The process of creating and sharing deliverables that are no longer necessary such as some arrangement drawings reduces the burden on engineering. Reduced engineering hours to create the deliverables. | Engineering provides all the deliverables necessary / requested to perform construction. | Properly attributed models include the data needed by Construction. Removes need for certain documents (moving from document centric to data centric approach).
[6 empty] | Construction | Project Controls | Cost | $ | Increase Accuracy in Estimating of Cost-to-Complete (Forecasting) | Using AWP and workface planning will help to focus on the completion and timing of IWPs, which will provide better "real-time" data relating to work remaining. IWP granularity helps to provide a basis for to-date productivity factors, which can be used as the basis for estimating cost to complete. | Forecasting is typically done at the discipline level, using aggregated quantities and overall performance. | Progress and performance can be measured at the IWP level, allowing for more accurate understanding of progress and performance to date. This data can then be used to assess work remaining and the cost to complete.
[6 empty] | Construction | Project Management | Cost | $$$ | Reduction in overhead costs resulting from decreased site schedule. | Implementation of AWP will help to ensure a better understanding of Construction readiness, which means that work at site starts when there is sufficient backlog. This can reduce the overall schedule, which can often be impacted by starting Construction too early. This reduction of the site schedule will lower overhead costs. | Construction starts when the initial disciplines receive the first IFC drawings, which can lead to subsequent delays if Engineering progress cannot be maintained. | AWP will allow for a clearer understanding of all disciplines, to ensure that the engineering and material will be available to support not only the first disciplines in the field, but all those that follow.
[6 empty] | Construction | Construction Management | Cost | $$ | Improve Construction Readiness Assessment | AWP enhances Construction Readiness by packaging and alignment of Construction priorities with engineering and material delivery. Readiness assessments require all participants to more fully understand readiness conditions including Engineering, Procurement, Site materials, Site Execution, Project Controls, and others. AWP helps with alignment prior to starting work that significantly increases the probability of execution success through transparent readiness assurances prior to getting in the field. | A big factor in project cost overruns is getting in the field to early and running out of material and late engineering. Good projects try and get a major portion of Eng. complete and a head start on material delivery…...but not necessarily in the sequence to most effectively construct the project. | AWP's constraint-based approach and the granular nature of the work packaging system provide an excellent basis for Construction Readiness Assessments, which can be done at a greater level of detail. The CRA will also be used to check the ability of the project to execute per the Path of Construction, making sure that the agreed plan is being adhered to.
[6 empty] | Detailed Design | Engineering | Schedule | $$ | Minimize Engineering errors and Field Revisions | Using a 3D model for design not only supports AWP requirements for field construction - it also provides an opportunity to visualize the work and any interference, allowing a number of issues to be addressed prior to getting to the field. CWP-level model reviews can provide more results, as they are targeted at a limited scope. At site, the Planners can use the model to perform a secondary check, to assess and review the work in detail by IWP to help identify potential errors and issue any necessary RFIs before the IWP is released to the field. | Model reviews during Engineering phases of the project. Engineering contractor running clash detection. | Earlier, more thorough and more granular review of the model, at the site, CWP and IWP level, will allow errors to be found and resolved sooner.
[6 empty] | Construction | Quality | Cost | $ | Reduce defects and rework | The structured AWP approach uses detailed planning and scope preparation to ensure that the crew has all the information needed to perform their work. This will also help to verify the accuracy of the engineering information, and check that the latest revision of all technical documents is being used, prior to the scope being issued. This validation, particularly when coupled with advanced notification of potential change, will reduce the amount of rework performed on site. Thorough planning will also minimize out-of-sequence work, and the need for temporary fixes in the field. RFIs can be tied directly to IWPs, so that responses can be addressed immediately. | Focused on the quality of the execution with the known scope. Rarely includes validation of engineering revisions or pending changes. RFIs are reactionary. | The up-front work of the Planners will help to keep the foremen in the field so they can manage their crew quality. Detailed scope review and document revision control ensures work is being performed on the latest engineering information. Reduction in unplanned work will also improve safety on site.
[6 empty] | Construction | Quality | Schedule | $ | Reduce the number of RFIs and improve timing of RFIs in the Field | An important element of AWP is to pull issues away from the field, where delays can have severe impacts. More thorough scope and technical reviews during the Engineering stages, including detailed constructability, will identify issues earlier, allowing them to be solved before they reach the work site. Construction input during Engineering means that these issues can be solved during design, which will lead to fewer field RFIs. In the field, the detailed IWP-level scope reviews by the Planners mean that remaining issues can be addressed as RFIs during planning stages, before they impact the field crew productivity. | Early planning will reveal a number of issues, which can be addressed as RFIs. But lack of construction input during Engineering stages will still lead to a greater number of issues in the field. | Construction input during Engineering phases will remove many of the issues, particularly when performing detailed scope and constructability reviews. Field level planning means that remaining issues can be addressed before the IWP is issued.
[6 empty] | Construction | Construction Management | Cost | $$$ | Better utilization of construction equipment/scaffolding | Construction equipment and scaffolding costs on projects can be significant. More detailed planning, especially in the early project stages, can help to minimize these costs. Requirements for large equipment durations on site can be shortened by executing major lifts in a well-planned sequence. Large-scale scaffolds can be planned during Engineering to minimize size and changes. IWP planning can include equipment and scaffold requirements, so that these elements can support all the trades on site, rather than reacting to single-trade requests. | Scaffold and equipment planning is typically planned as a best reaction to the active work fronts, with minimal advanced notice of upcoming work. | Early planning during Engineering can identify and minimize large equipment and scaffold requirements. IWPs are routed to the Equipment Manager and Scaffold Supervisor as soon as they are generated, along with details of the planned execution date, so that resources can be assigned and efficiently planned to support all work scopes.
[6 empty] | Construction | Construction Management | Alignment | $$ | Improve worker morale | Constant changes to work scopes and movement of crews due to constraints can have a negative impact on worker morale and happiness. By planning out the work, so that crews can execute their scopes from start to finish without interruption or movement, the increase in productivity will have a beneficial impact on morale. It will also reduce unplanned work, lowering the likelihood of safety incidents due to changes. | Workers are assigned to available work fronts, and continue working until another scope becomes more critical, or the current scope hits a constraint that can't be worked around. | The planning and preparation involved in an AWP process will give the crews the chance to be as efficient and safe as possible, which will support morale on site.
[6 empty] | Construction | Construction Management | Schedule | $ | Supports an efficient permitting process | Early creation of IWPs, with details of scope and location, will provide the Operations team with advanced notification of the construction plan. This will allow them to make the necessary preparations to support the work, and issue permits on time. Performing daily planning sessions on site, where the work for the coming week is reviewed, will also support this process. | Typically involves providing some advanced notification to Operations, but can often be derailed with changes to the plan based on delays associated with Engineering, materials or other constraints. | The use of constraint-free IWPs helps Operations to fully understand what work will be done for the permit requested, and allows them to plan for the work on the understanding that it will not change, either in scope or timing. This reduces waiting time for the field crews, allowing work to be more efficient.
Category D - Full AWP | Advancing Construction into FEL 2 and FEL 3 and downstream into testing, startup and commissioning combined with the use of advanced technologies | Front End Loading Earlier engagement of stakeholders for development of a Path of Construction as input into the project schedule Labor Work Packages (LWP) are used to organize the bidding and contracting process AWP Master Index is managed in AWP Software that maintains digital connections between all package types CWP and EWP Boundary Creation (CWAs) Detailed alignment of execution between Path of Engineering and Path of Construction Constructability process leveraging Path of Construction is utilized for on-going construction input Contracts clearly reflect AWP Practices and Data Requirements Detailed Design Constructability process is used to update design plans in real-time based on constraints EWPs are used to organize and track Engineering Deliverables Vendor Work Packages (VWP) are used to organize and manage vendor data requirements DWPs are used to organize and manage Engineering work at the Level 4 Procurement PWPs are used to organize and track Procurement Deliverables Material RAS dates feed from Construction Planning Material availability feeds status visualization and WFP Construction CWPs are developed, sequenced and released as part of construction management process Graphical & Non-Graphical WFP is used to create IWPs for all disciplines Scaffold Work Packages are used to optimize multi-discipline scaffolding across IWPs Module Work Packages (MWP) are used to package Module work Startup & Commissioning Early definition and prioritization of turnover systems and sub-systems Test Work Package (TWP) are used to track and manage testing process Turnover Work Packages (TOP) are used to track and manage the system turnover process | Scheduling Tool Progress Tracking Tool Cost Tracking Tool Materials Management Tool Site Materials Management Tool Procurement Tool Engineering Design Tools 3D Modeling Engineering Tool Document Management Tool 4D Sequencing Tool for Path of Construction Development and Review Sophisticated VCM capable of creating both graphical and non-graphical IWPS integrated with materials management tools for status visualization in the model Purpose-Built AWP Tool with a complete AWP Master Index, AWP Reporting & Analytics, and multi-organization collaboration environment. Integration with Engineering Design tools Bi-directional integration with scheduling tool to move from "scheduling" to "planning" for level 4 activities Cross Organizational Integrated Data Warehouse for consolidating data across all stakeholders Field mobility tool for accessing IWPs and progressing in the field | People - Added FTEs: Workface Planning Lead Discipline Workface Planners AWP Manager Model / Data Manager AWP in Engineering Lead AWP in Procurement Lead AWP in Startup Lead Earlier Engagement of: Construction Manager Supply Chain Manager Commissioning and Startup Lead Operations Contractors Additional Cost of Meetings: Interactive Planning Meetings Path of Construction Team Alignment AWP Requirements for Contractors Process - Training: Awareness training for key project stakeholders Champion training for project leadership Engagement training for key executors Oversight / compliance activities Procedures: Policies and procedures update RACI chart development Guidelines Package templates Communication aids Contracts: Contract Language Development Technology - 4D sequencing tool for planning and review Virtual Construction Model for creation and management of IWPs Field mobility tool for IWP and progress review in the field AWP Master Index AWP Capable Engineering Work Management Tool AWP Capable Procurement Work Management Tool AWP Capable Startup & Commissioning Work Management Tool AWP Data Management Tool Field Mobility Tool for Completions | $$$ | All Phases | Construction Management | Schedule | $$$ | Reduce time spent waiting for information by planning earlier for what information is required by whom, when, and in what priority | Making information available at the right time to the right people by better prioritizing what information is needed when and by whom. This benefit is a result of a better planning process and a better assignment of responsibilities that results from the clear definition of the work package plan at all levels. Better availability of information stems from clear asks due to planning and capability of IT systems to access information which supports making constraint free work packages. This also supports earlier efforts such as engineering access to supplier (vendor) data. The key idea is that earlier planning allows knowing what information to ask for and in what priority. If this is achieved in early planning, then subsequent phases benefit from the improved access to the data. Access to the right information benefits Quality by decreasing mistakes; increases alignment through improved clarity and protects the schedule by reducing delays. | It is a function of clear assignment of responsibilities as well as expectations for turnaround time. Also supported by clarity of asks for information in contracts. | AWP results in better planning, leading to a better understanding of what is needed and when. Benefits are reduced likelihood of data availability problems, clarity of priority dates, minimizing constraints on engineering by providing data when required.
[6 empty] | Pre-FEED/FEED (FEL) | Project Controls | Alignment | $$$ | Improve identification and mitigation of execution risks through a well-defined path of construction development process that drives early alignment of all project stakeholders | Early collaborative development of a well-defined path of construction is key to aligning construction with engineering, procurement, and startup. This alignment ensures that engineering and supply chain deliverables will support the needs of construction and that construction will support the needs of startup. Use of a 4D virtual construction model (in FEED) to graphically validate and optimize the path of construction enables a level of development not possible without the use of technology. The process of interactive planning with representation from all project stakeholders increases the early identification of constraints and helps to support constructability and optimization of scope. | Early and consistent project risk review meetings involve all key stakeholders and target risks with the greatest impact to project performance. | Greater shared understanding of the risks, due to the increased definition of scope and timing. Better alignment on the end goal for the project, rather than just for the current phase, forces a more holistic view of the project risks (particularly if a different contractor is used for various phases).
[6 empty] | Pre-FEED/FEED (FEL) | Project Management | Cost | $ | Improved Bid Process through more accurate project definition earlier in the process | The early planning process leads to more complete information that enables the team to produce more complete documents in their bid packages. Improved accuracy of MTOs and models ensure that the contractors are bidding on the most up-to-date scope with the fewest holds and planned changes. Access to more complete path of construction and schedule information developed during early planning contribute to a better understanding of the scope and requirements of the project. This more defined approach allows for more specific targeting of bidders, and more accurate bids that require less contingency to account for the unknowns. | Provide the best available information that is current at the time of issuing the RFP to the contractors, whether complete or not, typically in a single offering. | The increased granularity allows for better understanding of the status and readiness of the information at the time of RFP, as well as providing the contractor with a more detailed and accurate understanding of the scope of work to be performed. The more detailed understanding of which packages are not ready will provide greater visibility on project readiness and risks.
[6 empty] | Pre-FEED/FEED (FEL) | Operation Representative | Alignment | $ | Improved integration with existing site infrastructure | Early involvement of operations personnel during early planning and path of construction development improves the integration with the existing facility. This reduces delays and quality issues that result from poor interface management by identifying the interface points and promoting higher levels of collaboration early in the project. | Use existing models and as-built information to provide an engineering basis for the new design. | Early stakeholder engagement and alignment which will help to reduce changes later in the project, and builds on the data available. Construction and operations involvement allows for earlier collaboration and buy-in.
[6 empty] | Pre-FEED/FEED (FEL) | Engineering | Alignment | $ | Maximize value of IT investments | AWP data requirements are defined early in the project, allowing for better standardization and cross-organizational configuration of data exchanges and capabilities. Consistent application of data attribution will lessen rework and allow early assessment of capability of tools to support the AWP process. | Point to point integrations and flat file exchanges are used to move data between systems | Clear definition of data requirements to support AWP drives more efficient data exchanges and integrations. Leveraging CII standards further facilitates this process.
[6 empty] | Pre-FEED/FEED (FEL) | Construction Management | Predictability | $ | Reduce time spent on regulatory permitting / reduce likelihood of impact from regulatory permitting | Integrated Project Planning Meeting (IPPM) and path of construction can be used to identify permit constraints. Backwards pass allows for an earlier identification of timeline required to get the permits and gives the permit team within the project a better understanding of the timelines required. This will help support team effort to provide the necessary information to support the permit application, which will reduce the likelihood of rejected applications. Permitting will be a key part of the project plan, and dates will be integrated into the schedule. The impact of permit delays can be clearly seen. Permitting process can be work-packaged to drive accountability and completion. | List of all permits, with an understanding of the timing required to receive. | Path of Construction provides a more accurate understanding of timing for when the permits are needed, avoiding the traditional trap of starting work when it can be started, rather than when it should be started. The permit cycle can be tied directly to specific construction activities in the detailed EPC schedule, allowing each party a clear understanding of the timing for their deliverables. Better definition may also improve the quality of the permit application, reducing the likelihood of rejection.
[6 empty] | Detailed Design | Project Management | Cost | $$$ | Leverage new contracting strategies that incent overall project optimization | Traditional approaches to contracting rely on earned value and quantity tracking that reward work but do not distinguish between work that will contribute to the overall optimization of the project and work that is easy or convenient to execute. Enhanced contracting capabilities resulting from better visibility into "true" project progress as opposed to antiquated earned value based on quantity curves enables better payment and incentive approaches that drive the behavior that supports the overall project optimization. | Engineering progress is measured and contract payments align with percent complete, drawing completions, and/or major engineering milestone. | Engineering Work Packages built from the Path of Construction and master project schedule can become the basis for reporting and payment terms. Payments are aligned with package close-outs.
[6 empty] | Detailed Design | Project Controls | Cost | $$ | AWP allows improved scope and leads to improved bid accuracy / less contingency | More granular and accurate definition of scope by Owners allows contractors to make more accurate bids that contain less contingency. (Southern company publicly announced a savings of 2% of project TIC as a result of better scope definition and a per-CWP contracting strategy). | Projects provide sufficient data for contractors to bid with a standard contingency | Scope is further defined prior to bidding enabling removal of a portion of contingency. Contractors apply contingency in a manner inversely proportional with the level of detail and certainty that they have in the package. AWP also helps to improve understanding of start-up timing, giving more accurate pricing.
[6 empty] | Detailed Design | Supply Chain | Schedule | $ | Efficiency gain in managing long-lead equipment (including vendor documentation) | Better visibility into construction need dates leads to increases in efficiencies for managing long lead items especially around management of vendor documentation. Many organizations use a "first in first out" process for reviewing vendor documentation. By shifting to a prioritized review driven by construction need, significant efficiencies are gained. | Vendor documentation is managed on a first in first out basis separately from other departments. | Construction need dates are used to prioritize vendor documents. Vendor Work Packages (VWPs) are used to organize the data and process. This enables backwards passes to verify dates and timing.
[6 empty] | Detailed Design | Engineering | Cost | $$ | Potential for repeatable packages / repeatable designs for reuse and efficiency | Better breakdown of engineering and procurement scopes into defined packages improves the possibility of reusing portions of a design. While an entire project may not be reusable, AWP allows you to identify portions that are, so that those pieces can be leveraged even if the entire plan cannot be reused. | Little to no data and deliverables are reused on projects | Breakdown of projects into smaller work packages facilitates potential reuse of a portion of a project.
[6 empty] | Detailed Design | Construction Management | Alignment | $$ | AWP forces engineering development of the 3D model to be provided as a deliverable to construction (not engineering only) | Construction requires more data to be added to the 3D model which has benefits for engineering, procurement, construction, startup and operations. By driving this increased attribution and details into the model other phases of the project benefit all the way through to operations and the digital twin. | 3D models are used for engineering only | 3D models are conditioned and combined with additional data to make a virtual construction model. The virtual construction model can be used for constraint analysis, package scoping, material status, progress tracking.
[6 empty] | Startup & Commissioning | Operation Representative | Alignment | $$ | Smoother handover/ turnover of facilities to Operations at start-up | The early involvement of operations personnel will help to identify systems and sub-systems, which can be prioritized and scheduled. This will allow the project team to check the Path of Construction to make sure that it supports the commissioning and start-up sequence. With advanced planning and well thought out isolation strategies, work can be handed over to commissioning sooner, without impacting the construction activities within an area. | This is just good project delivery, but often causes more time in turnover meetings to ensure alignment and actual system turnover. | Operations personnel are involved during the early design phases to provide input on systemization and turnover sequence. This will ensure that the Path of Construction, which is primarily designed to support construction activities, also accounts for the turnover sequence.
[6 empty] | Startup & Commissioning | Operation Representative | Alignment | $$ | Improved integration with operations (brownfield and greenfield) | Using an AWP approach, the 3D model will include data attribution for turnover systems and sub-systems. This, coupled with the agreed turnover sequence and dates, will allow construction to plan for an efficient and timely handover to operations. This integration between the project team, contractor and operations team will be improved with the visibility of being able to report progress and turnover readiness by system / sub-system. | Heavily-reliant on manual records for tracing installation progress to turnover systems. | Removes the human element of knowing what work is needed to close out systems and optimize the transition to startup and commissioning. The process and technology automate this connection.
[6 empty] | Construction | Construction Management | Cost | $ | Streamline Time to Assemble Data & Docs for Turnover | When IWP scopes are completed, if they are completed fully ("done done"), they can be inspected and verified at that time. This avoids leaving the majority of the inspection and turnover documentation to the latter stages of project, where it becomes a significant effort to complete, and can delay the turnover to commissioning. | This is just good project delivery. | The granularity of AWP will help to align the contents of the IWPs with the systems and sub-systems, meaning that sub-systems can be turned over when complete, rather than waiting for the balance of the system to be completed.

## Measuring AWP Success
MEASURING AWP SUCCESS
Measuring AWP Benefits
Metrics measuring the Benefits of AWP (the project outcome of effective AWP implementation)
A portion of the metrics included here are standard project metrics that apply to all categories. The values achieved will vary by category showing the benefit of AWP.
Metric Category | Metric | Description | AWP Maturity Category
|  |  | A - No AWP | B - WFP | C - AWP | D - Full AWP
Performance | Construction PF @ Prime (Commodity) Level | Hours per unit of prime commodity (e.g. LF of pipe, kg of steel etc) | X | X | X | X
| Construction PF @ CWP Level | Estimated (or earned) hours for a CWP over expended hours. (Some organizations state PF as expended / earned). |  |  | X | X
| Construction PF @ IWP Level | Estimated (or earned) hours for an IWP over expended hours. (Some organizations state PF as expended / earned). |  | X | X | X
| Time of Tools | Craft time spent on actual direct work, vs support (such as obtaining material) & delay (such as waiting for equipment...), | X | X | X | X
| Cost Predictability & Forecasting | Percentage deviation (from final TIC) of forecast TIC reported at 25%, 50%, 75% construction complete. | X | X | X | X
| Reliability & Repeatability | Percentage of commitments made in three week lookahead that are met |  | X | X | X
Safety | Leading Indicator: Observations | Number of safety observations per 200,000 manhours of work | X | X | X | X
| Leading Indicator: Near Misses | Number of near misses per 200,000 manhours of work | X | X | X | X
| Lagging Indicator: 1st Aids | Number of first aids per 200,000 manhours of work | X | X | X | X
| Lagging Indicator: Recordable | Number of recordable incidents per 200,000 manhours of work | X | X | X | X
| Lagging Indicator: Restricted work | Number of restricted work cases per 200,000 manhours of work | X | X | X | X
| Lagging Indicator: Lost time | Number of lost time cases per 200,000 manhours of work | X | X | X | X
Schedule | Plan vs Actual MC dates | Number of days difference between planned and actual mechanical completion date | X | X | X | X
| Time between Construction Installation complete and Construction Close out | Average number of days from IWP status of "Construction Complete" to IWP status of "Closed" | X | X | X | X
| Plan vs Actual ready for commissioning or RFSU | Number of days difference between planned and actual ready for startup date | X | X | X | X
| Out of Cycle work | Number of hours spent performing out of sequence work over total hours spent to date |  |  | X | X
| Schedule Predictability & Forecasting | Percentage deviation (from final MC date) of forecast MC date reported at 25%, 50%, 75% construction complete. | X | X | X | X
Quality | NCRs | Number of Non-Conformance Reports per 200,000 manhours of work | X | X | X | X
| Rework | Number of hours spent on rework activities over total hours spent to date |  | X | X | X
| MC Punch | Quantity of punchlist items per turnover package (Mechanical walkdown) | X | X | X | X
| Commissioning Punch | Quantity of punchlist items per turnover package (Commissioning walkdown) | X | X | X | X
Measuring AWP Adoption
Metrics that are intended to measuring whether AWP is being adopted correctly and widely on the project
Metric Category | Metric | Description | AWP Maturity Category
|  |  | A - No AWP | B - WFP | C - AWP | D - Full AWP
Personnel | Dedicated WorkFace Planners | Named Dedicated WorkFace Planners Assigned to the Project |  | X | X | X
| AWP Specialist | Named AWP Specialist Assigned to the Project |  |  | X | X
| Ratios of Planners to Craft | Total number of WorkFace Planners over the total number of craft |  | X | X | X
| Ratios of Planners to Superintendents | Total number of WorkFace Planners over the total number of superintendents |  | X | X | X
Schedule | EWPs released per plan | EWP with on time release over total released EWP count |  |  | X | X
| CWPs released per plan | CWP with on time release over total released CWP count |  |  | X | X
| Average CWP delay | Total CWP Delay Days over Total CWP Release Count |  |  | X | X
| Average EWP delay | Total EWP Delay Days over Total EWP Release Count |  |  | X | X
| IWPs released per plan | IWP with on time release over total released IWP count |  | X | X | X
| IWPs completed per plan | IWP with on time construction complete over total closed IWP count
| Unplanned IWP Execution | Total Unplanned (Not Contained in IWP Release Plan) Execution Hours over the Total Execution Hours |  | X | X | X
Engineering | Documents in MDR not assigned to a CWP | Engineering deliverables to construction that are not assigned to CWP over total engineering deliverables to construction count |  |  | X | X
| Engineering Model Attribution | Minimum Data Requirements per discipline appropriate to the AWP Maturity Category are documented and included in the contract |  |  | X | X
| EWPs Released with Holds | Number of EWPs released with holds over total number of EWPs released |  |  | X | X
| EWP Revision Cost | Total Cost of Rework Resulting from EWP Revisions
| EWP Revisions | Total Number of EWP Revisions post IFC over the total number of EWPs released |  |  | X | X
Materials | RAS dates achieved | Number of tagged items received on time divided by Total Tagged Item Count | X | X | X | X
| CWP/IWP delays due to materials | Number of CWPs/IWPs that are delayed as a result of failing to meet Material Availability Target
| Number of Tagged Items Not Associated with CWP | Count of Tagged Items that are not associated to a CWP
Planning | RFIs issued : "X" weeks before IWP start | Average number of days prior to IWP Planned Start Date that an IWP RFI is released |  | X | X | X
| Average Hours per IWP (Planned & Actual) | Total IWP Hours over Total IWP count (Planned & Actual) |  | X | X | X
| Average Duration of IWP Execution (Planned & Actual) | Average Number of Days from IWP start to Finish (Planned & Actual) |  | X | X | X
| IWP Backlog (Workfront Buffer) | Total number of Constraint Free IWP hours over Total Craft Day Hours onsite |  | X | X | X
| Constraint-Free IWP Ready Duration | Average number of days between constraint-free IWP ready for construction date and Planned Start Date |  | X | X | X
Quality | Punchlist item count per IWP/hours | Total number of Punchlist items per IWP count or man-hours | X | X | X | X
| Quality Closeout Duration | Average number of days that IWPs remain in construction complete status prior to being closed out by QC |  | X | X | X

## Where to Go Next
WHERE TO GO NEXT
Immediate Next Steps
Document outcomes from use of tool
Determine desired future state of AWP Maturity Category
Publish determinations, gaps, and priorities
Expand the committee to include identified organization stakeholders and decision makers
Setting Up for Success
Set up workshops to share and gather information to validate projections
Set up workshops to identify requirements for implementing solution sets
Gain agreement on and document an implementation strategy
Produce a roadmap and implementation plan
Assign roles and responsibilities
Put a short term action plan in place
Identify investment funding and resources
Continuous Improvement
Monitor and revisit progress (with metrics and analytics)
Workshops to reassess plan
Update roadmap and implementation plan

## Acronym List
ACRONYM LIST
Acronym | Description
AWP | Advanced Work Packaging
CII | Construction Industry Institute
CRA | Construction Readiness Assessment
CWA | Construction Work Area
CWP | Construction Work Package
DWP | Design Work Package
EPC | Engineering Procurement Construction
EPCM | Engineering Procurement Construction Management
ETA | Estimated Time of Arrival
EWP | Engineering Work Package
FEED | Front End Engineering and Design
FEL | Front End Loading (Early engineering phases)
FTE | Full Time Equivalent
IFC | Issued For Construction
IPPM | Interactive Project Planning Meeting
IT | Information Technology
IWP | Installation Work Package
KPI | Key Performance Indicator
LWP | Labor Work Package
MC | Mechanical Completion
MDR | Master Deliverable Register
MTO | Material Take-Off
MWP | Module Work Package
NCR | Non-Conformance Report
PF | Performance Factor
PO | Purchase Order
POC | Path Of Construction
PWP | Procurement Work Package
QVD | Quality Verification Document
RACI | A chart showing Responsible, Accountable, Consulted, Informed
RAS | Required At Site (date)
RFI | Request For Information
RFID | Radio Frequency Identification
RFP | Request For Proposal
RFSU | Ready For Start Up
TIC | Total Installed Cost
TOP | Turnover Package
TWP | Test Work Package
VCM | Virtual Construction Model
VWP | Vendor Work Package
WFP | WorkFace Planning

## Acknowledgements
ACKNOWLEDGEMENTS
Development
This tool was developed by the CII AWP CBA for Performance & Benchmarking whose members are listed below.
Co-Chairs | Company
Josh Girvin | O3 Solutions
Andrew Foy | Motiva
Members | Company
Mark Fields | Shell
Martin Swaine | Shell
Karan Cleland | Dow
Mark Lambert | Eastman
Jacob Bubalo | Eastman
Fernando Espana | Construct-X
Jeremy Hall | Wood Group
Bill O'Brien | University of Texas Austin
Bruce Long | Southern Company
Jintae Park | O3 Solutions
Colin Budka | O3 Solutions
Doug Theret | Digital Construction Works
Juan Velasco | McDermott
Cory Fisher | Fluor
Ryan Posnikoff | Bentley Systems
Jay Prakash | Exxon
Chuck Mies | Autodesk
Matsufuji Shinya | JGC Corporation
Yin Zhe | University of Texas Austin
Special Thanks
Andrew Foy for extensive contribution to the AWP Investments & Benefits
Mark Lambert for contributing Eastman Chemicals AWP maturity categories
Cory Fisher for contributing Fluor's Metrics for measuring AWP Benefits & Adoption
Bill O'Brien for providing academic support and extensive CII AWP knowledge
Review
This tool was reviewed and approved by CII AWP CBA Leadership whose members are listed below
Co-Chairs | Company
Eric Crivella | Digital Construction Works
Jamie Gerbrecht | Exxon
Members | Company
Josh Girvin | O3 Solutions
Andrew Foy | Motiva
Fernando Espana | Construct-X
Robin Mikaelsson | Construct-X
Tedd Weitzman | Construct-X
Mandi Coker | O3 Solutions
Bill O'Brien | University of Texas Austin
Gabby Salazar | Spaw Glass
Silvana Lara | Fluor
Mike Pappas | Construction Industry Institute
Bob Wible | Construction Industry Institute
Hala Nassereddine | University of Kentucky
Stewart White | Kiewit