## Cover
Best Practice (BP) Tool
INTRODUCTION |  |  | FAQs
| The Construction Industry Institute (CII) Best Practices (BP) Tool* is a user-friendly software application designed to summarize and streamline access to the best practices (BP) knowledge from CII. This tool provides executive summaries for each BP; report summaries; valuable insights, termed "Golden Nuggets" (GNs), from comprehensive BP research reports, and detailed action items under each GN, ensuring that users can easily apply critical BP knowledge to their specific projects. This tool is an expanded “digital” version of CII’s Best Practice Guide (IR-166-3) and provides BP guidance from a Project Perspective for CII members who want to learn more about project management fundamentals essential for improved project performance. The tool organizes information across four intuitive levels: 1. BP Compass: This initial level provides a clear overview, listing GNs for each project phase from a horizontal project phase perspective, and 17 BPs along with each report associated with each BP from a vertical perspective. 2. Summaries: Executive summaries are provided for each BP as well as report summaries for research projects deemed to be key for each BP. 3. Golden Nuggets (GNs): At this level, each research report's specific GNs is mapped to appropriate project phases, enhancing relevance and applicability. 4. Detailed Action Items: The final level breaks down actionable steps for each GN, empowering project managers and other team members to implement these insights effectively. It also includes a FAQ section to help users quickly learn about answers to common questions pertaining to each BP. *Created by RT-398 using artificial intelligence and validation by subject matter experts. |  |  | 1. ADVANCED WORK PACKAGING
2. ALIGNMENT
3. BENCHMARKING & METRICS
4. CHANGE MANAGEMENT
5. CONSTRUCTABILITY
6. DISPUTES PREVENTION & RESOLUTION
7. FRONT END PLANNING
8. IMPLEMENTATION OF CII RESEARCH
9. LESSONS LEARNED
10. MATERIALS MANAGEMENT
11. PARTNERING
12. PLANNING FOR MODULARIZATION
13. PLANNING FOR STARTUP
14. PROJECT RISK ASSESSMENT
15. QUALITY MANAGEMENT
16. TEAM BUILDING
17. ZERO ACCIDENT TECHNIQUES

## CII Glossary
Term | Definition
Actual Project Cost | This is the total actual cost of a project. For contractors, the cost includes all work performed by the company, including costs attributable to work added or deducted by change orders. For owners, it excludes the cost of land, and any site preparation cost.
Addition | A new addition that ties into an existing facility, often intended to expand capacity. Synonym: Expansion, Add-on.
Advanced Work Packaging (CII Best Practice) | Advanced work packaging (AWP) is the overall process flow of all the detailed work packages (construction, engineering, and installation work packages). AWP is a planned, executable process that encompasses the work on an EPC project, beginning with initial planning and continuing through detailed design and construction execution. AWP provides the framework for productive and progressive construction and presumes the existence of a construction execution plan.
Alignment (Best Practice) | Alignment is the condition where appropriate project participants are working within acceptable tolerances to develop and meet a uniformly defined and understood set of project objectives
Baseline Schedule | The original planned schedule approved at time of project sanction for owners and contract award for contractors. It should be updated to include any changes since change data are collected in a later section. For benchmarking purposes, the baseline schedule does NOT change during project execution.
Benchmarking and Metrics (Best Practice) | Benchmarking is the systematic process of measuring an organization’s performance against recognized leaders for the purpose of determining best practices that, when
adapted and utilized, lead to superior performance.
Best Practice | A best practice is a process or method that, when executed effectively, leads to enhanced project performance. CII Best Practices have been proven through extensive industry use and/or validation.
Brownfield | The expansion, redevelopment, or reuse of property or facility which may be complicated by the presence or potential presence of a hazardous substance, pollutant, or contaminant. Common examples are abandoned gas stations and dry cleaners, railroad properties, factories and closed military bases. Synonym: co-locate.
Building | Includes non-industrial facilities, such as a communications center, courthouse, dormitory, hotel, large apartment complex, embassy, office building, hospital, laboratory, maintenance facilities, movie theatre, parking garage, physical fitness center, prison, restaurant, nightclub, retail building, school, or warehouse.
Business Driver | Refers to the rationale behind the capital investment, e.g. increase production capacity, or mandated by regulation.
Change | A change is any event that results in a modification of the project work, schedule or cost. Owners and designers frequently initiate changes during design development to reflect changes in project scope or preferences for equipment and materials other than those originally specified. Contractors often initiate changes when interferences are encountered, when designs are found to be not constructable, or other design errors are found.
Change Management (CII Best Practice) | Change management is the process of incorporating a balanced change culture of recognition, planning, and evaluation of project changes in an organization to effectively manage project changes. These changes include scope, error, design development, estimate adjustments, schedule adjustment, and changed condition, either elective or required.
CM at Risk | A delivery method which entails the construction manager to act as consultant to the owner in the development and design phases, but as the equivalent of a general contractor during the construction phase.
Constructability (CII Best Practice) | Constructability is the optimal use of construction knowledge and experience in planning, design, procurement, and field operations to achieve overall project objectives.
Contingency | All costs in contingency accounts including but not limited to normal contingency, allowances, reserves, indirect costs for schedule contingency, escalation, etc.
Cost Escalation | The provision in a cost estimate for increases in the cost of equipment, material, labor, etc., due to continuing price changes over time.
Cost of Land | The cost of land includes the purchase price of the land obtained for project use. It does not include the cost of preparing the land for use, such as soil remediation, demolition of existing structures, site preparation, etc.
Cost Reimbursable | The owner and contractor agree as to the price that will be charged per unit for the project. It is also called unit price. Its derivatives include cost plus fee, time and materials, and guaranteed maximum price.
Days Away (DA) Case | An incident which results in days away from work.
Days Away (DA) Incidence Rate | The days away from work incidence rate (DA) is the number of DA cases occurring annually among 100 full-time workers (2,000 hours per worker per year).
Days Away Restricted or Transferred (DART) Case | An incident which results in days away from work, restricted work activity, or job transfer.
Days Away Restricted or Transferred (DART) Incidence Rate | The days away, restricted, or job transfer case incidence rate (DART) is the number of DART cases occurring annually among 100 full-time workers (2,000 hours per worker per year).
Design-Build | An integrated delivery process which combines architectural and engineering design services with construction performance under one contract agreement.
Direct Cost of Field Rework | The sum of those costs associated with actual performance of tasks involved in rework. Examples include labor, materials, equipment, supervisory personnel, and associated overhead cost.
Direct Costs | Direct costs are those which are readily or directly attributable to, or become an identifiable part of, the final project (e.g., piping labor and material).
Direct Work Hours | Direct work hours include work hours of engineers/technicians who produce engineering deliverables, including site investigations, meetings, planning, constructability, RFI, and rework. Also includes work hours of craft workers who install material or assist in installation.
Dispute Prevention and Resolution (CII Best Practice) | Dispute prevention and resolution techniques include the use of a Disputes Review Board as an alternate dispute resolution process for addressing disputes in their early stages before affecting the progress of the work, creating adversarial positions, and leading to litigation.
Expansion | A new addition that ties into an existing facility, often intended to expand capacity. Synonym: Addition.
Fatality Rate | The fatality rate is the number of fatalities occurring annually among 100,000 full-time workers (2,000 hours per worker per year).
Front End Planning (CII Best Practice) | Front end planning (FEP) is the essential process of developing sufficient strategic information with which owners can address risk and make decisions to commit resources in order to maximize the potential for a successful project. FEP is often perceived as synonymous with front end engineering design, front end loading, pre-project planning, feasibility analysis, programming, and conceptual planning.
Frontline Supervisor | Definition will come from RT-414
Full-Time Equivalent (FTE) | Represents the number of participants and the percent of time each is allocated to the project. For example, if one team member responsible for procurement works half time on the project, then the procurement contribution to the FTE measure is 0.5. Likewise, if two project controls specialists work on the team full time, they contribute 2.0 FTE.
Grass Roots | A new facility from the foundations and up. A project requiring demolition of an existing facility before new construction begins is also classified as grass roots. Synonym: Greenfield.
Heavy Industry | Includes chemical manufacturing, cogeneration, environmental remediation, gas distribution, metals refining/processing, mining, natural gas processing, oil exploration/production, oil refining, oil sands, power generation, and pulp and paper.
Implementation of CII Research (CII Best Practice) | As relates to CII Best Practices, implementation of CII research is the comprehensive and effective use of proven CII products by member organizations, as outlined in the CII Implementation Model.
Indirect Costs | Indirect costs are all costs that cannot be attributed readily to a part of the final product (e.g., cost of managing the project).
Infrastructure | Includes airport, electrical distribution, flood control, highway, marine facilities, navigation, pipeline, rail, tunneling, water/wastewater, telecom, and wide area network.
ISBL | Inside Battery Limits (ISBL) is defined as all equipment and associated components (piping, etc.) that act upon the primary feed stream of a process. ISBL is functional-based and refers to equipment and other components that are solely dedicated to a single process whether or not the equipment is physically located within the geographical boundaries of the unit.
Issue for Construction (IFC) Quantity | The quantity of work required in the project plans and specifications, which are issued for construction, and does not include rework.
Lessons Learned (CII Best Practice) | A lesson learned (LL) is a critical element in the management of institutional knowledge. An effective lesson learned program (LLP) will facilitate the continuous improvement of processes and procedures, and provides a direct advantage in an increasingly competitive industry
Light Industry | Includes automotive manufacturing, consumer products manufacturing, food and beverage, microelectronics manufacturing, office products manufacturing, pharmaceutical manufacturing, pharmaceutical labs, and clean room.
Lost Workday Case Incidence Rate (LWCIR) | The lost workday case incidence rate (LWCIR) was replaced by the DART rate effective January 1, 2001. By definition, it was the equivalent to the DART rate.
Lump Sum | The contractor agrees to provide a specified amount of work for a specific sum. It is also called single fixed price.
Major Equipment | Commonly used interchangeably with engineered equipment. It is generally defined as tagged/numbered process or mechanical equipment including drivers.
Materials Management (CII Best Practice) | Materials management is an integrated process for planning and controlling all necessary efforts to make certain that the quality and quantity of materials and equipment are appropriately specified in a timely manner, are obtained at a reasonable cost, and are available when needed.
Mechanical Completion | The point in time when a plant is capable of being operated although some trim, insulation, and painting may still be needed. This occurs after completion of precommissioning. In some industries, mechanical completion may have the same general meaning as beneficial occupancy.
Mega-Project | Although not precisely defined, this term generally describes projects with capital budgets exceeding one billion dollars.
Modernization | A facility for which a substantial amount of the equipment, structure, or other components is replaced or modified, and which may expand capacity and/or improve the process or facility. Synonyms: Renovation, Upgrade.
Modularization | Modularization refers to the use of offsite construction (including a segregated area onsite). Modularization includes all work that represents substantial offsite construction and assembly of components and areas of the finished project. Examples that would fall within this categorization include:S kid assemblies of equipment and instrumentation that naturally ship to the site in one piece and require minimal on-site reassembly. Super-skids of assemblies of components that typically represent substantial portions of the plant, intended to be installed in a building. Prefabricated modules comprising both industrial plant components and architecturally finished enclosures. Modularization does not include offsite fabrication of components. Examples of work that would be excluded from the definition of modularization include: Fabrication of the component pieces of a structural framework
Fabrication of piping spool-pieces
NDE/NDT | Non-Destructive Examination/Evaluation (NDE) and Non-Destructive Testing (NDT) are techniques of testing that do not destroy the test object.
Offshore Engineering | The practice of hiring an external organization or use of a foreign subsidiary to perform engineering functions in a developing country to gain a cost and/or schedule advantage.
OSBL | Outside Battery Limits (OSBL) is defined as utilities, common facilities, and other equipment and associated components) that support several units. Typical OSBL equipment includes cooling towers, water treatment facilities, tanks farms, etc.
Overtime | Any hours above 40 work hours per week. For example, if working 55 hours in a week, the overtime is 15 hours and the percentage of overtime hours is calculated as 15 hours overtime/55 hours worked = 27.3% overtime.
P&IDs (Piping and Instrumentation Diagrams) | Schematic diagrams that show the layout and relationship of piping and instrumentation.
Partnering (CII Best Practice) | Partnering is a long-term commitment between two or more organizations as in an alliance or it may be applied to a shorter period of time such as the duration of a project. The purpose of partnering is to achieve specific business objectives by maximizing the effectiveness of each participant’s resources.
Planning for Modularization (CII Best Practice) | Planning for modularization is the evaluation and determination of offsite construction in the front end planning phase to achieve specific strategic objectives and improved project outcomes. The process includes developing a business case and execution strategy for large-scale transfer of stick-built construction effort from the jobsite to fabrication shops or yards.
Planning for Startup (CII Best Practice) | Startup is the transitional phase between plant construction completion and commercial operations. It encompasses all activities that bridge these two phases, including systems turnover, check-out of systems, commissioning of systems, introduction of feedstocks, and performance testing.
Process Industry Practices (PIP) | A consortium of process industry owners and engineering construction contractors that publishes practices reflecting common standards for many engineering disciplines across the companies.
Product | Refers to a grouping of goods or services produced by a facility.
Project Budget | This is the estimated cost of the project at authorization to proceed (i.e., sanction, or final investment decision). For contracts, it only includes their scope of work. If a project had cost changes before authorization to proceed, then these changes should be included in the project budget. Does not include estimated costs for change orders received during project execution.
Project Definition Rating Index (PDRI) | A Front End Planning tool used to measure the level of scope definition. It helps project teams to communicate and identify risks related to project scope definition.
Project Delivery and Contract Strategy (PDCS) | A structured process of evaluating and prioritizing owner’s objectives, reviewing and evaluating delivery methods and contract types, and then determining the appropriate delivery method and contract type for a project.
Project Delivery Method | A structured approach used to organize a project team so as to manage the delivery of a project.
Project Development Changes | Changes required to execute the original scope of work or obtain original process basis.
Examples include:
Unforeseen site conditions that require a change in design/construction methods.
Changes required due to design errors and omissions.
Schedule acceleration/Deceleration.
Change in owner preferences.
Additional equipment or processes required to obtain original planned throughput.
Operability or maintainability changes.
Project Priority | Priority given to cost or schedule when making decisions during the execution of a project. Assumes safety is a given for all projects.
Project Risk Assessment (CII Best Practice) | Project risk assessment (PRA) is the process to identify, assess, and manage risk. The project team evaluates risk exposure for potential project impact to provide focus for mitigation strategies.
QA/QC | Quality Assurance (QA) and Quality Control (QC); Planned and systematic actions necessary to provide appropriate confidence that a product or service will satisfy the quality requirements.
Quality Management (CII Best Practice) | Quality management incorporates all activities conducted to improve the efficiency, contract compliance, and cost effectiveness of design, engineering, procurement, QA/QC, construction, and startup elements of construction projects.
Recordable Incident | A recordable incident is a work-related illness and any injury which results in loss of consciousness, restriction of work or motion, transfer to another job, or requires medical treatment beyond first aid.
Renovation | A facility for which a substantial amount of the equipment, structure, or other components is replaced or modified, and which may expand capacity and/or improve the process or facility. Synonyms: Modernization, Upgrade.
Request for Information (RFI) | A process used to confirm the interpretation of a detail, specification or note on construction drawings or to secure a documented directive or clarification from the architect, engineer or owner that is needed to continue work.
Safety Excellence Techniques (SET) | RT-412
Scope Changes | Changes in the base scope of work or process basis. Examples include changes in feedstock, site location, throughput, or the addition of unrelated scope.
Team Building (CII Best Practice) | Team building is a project-focused process that builds and develops shared goals, interdependence, trust and commitment, and accountability among team members and that seeks to improve team members’ problem-solving skills.
Technology Use and Integration | The Technology Use and Integration practice addresses the level of automation and integration internally and externally for predefined tasks/work functions common to most projects.
Total Recordable Incidence Rate (TRIR) | The total recordable incidence rate (TRIR) is the number of recordable injuries occurring annually among 100 full-time workers (2,000 hours per worker per year).
Turnaround | The period during which a process unit, boiler, generating unit, transmission line, or other facility is shut down and unable to perform its normal operations. The shutdown of a facility including for maintenance, inspection, testing, regulatory changes, or, in some cases, for refueling is known as a planned shutdown. Turnaround is interchangeable with shutdown or outage depending on industry groups.
Value Improving Practices | Focused activities aimed at removing non-value-added investment from the project scope. Collectively, VIPs are an organized approach to minimizing life-cycle costs while optimizing the life of a facility.
Zero Accident Techniques (CII Best Practice) | Zero accident techniques include the site-specific safety programs and the implementation, auditing, and incentive efforts undertaken to create a project environment and a level of training that embraces the mindset that all accidents are preventable and that zero accidents is an obtainable goal.

## BP_Primer
CII Best Practice | Establish Business Case (or Need) | Front End Planning |  |  | Execution |  |  |  | Operation
| Prefeasibility | Feasibility | Concept | Detailed Scope | Detailed Design and Procurement | Construction | Commissioning and Start-Up | Turnover | Operate Facility
Contractor Involvement based on Project Delivery Method |  | Collaboratory EPC
Design-Build
Design-Bid-Build
1. ADVANCED WORK PACKAGING (3)
(1). Work Packaging for Project Control (RS6-6)
• Plan the engineering effort to meet the procurement and construction needs
* Define the project scope and requirements by analyzing the owner's need date and working backwards.
* Develop a rough schedule for the start-up, construction, procurement, detailed engineering, and conceptual engineering phases.
* Identify required engineering packages, key procurements, and start-up sequences through planning and coordination with stakeholders.
* Break down the total project into smaller work packages that comprise a total project and serve as essential planning tools for all players.
* Validate the completeness and accuracy of the historical database to ensure the proper application of data during the planning phase.
• Direct the procurement operations to deliver critical materials and equipment on time
* Determine critical material and equipment needs by analyzing the project scope and requirements.
* Establish need dates for materials and equipment based on the planned start dates of construction work packages.
* Issue purchase orders with contractual requirements that include a reasonable contingency time and earliest need date.
* Track each procurement activity in coordination with project controls to ensure timely delivery.
* Verify that procurement milestones are included as a single activity on the Control Schedule.
• Guide the construction process using the owner's need date/startup milestones
* Establish a schedule of start-up milestones to guide the construction planning and execution phases.
* Define system completion schedules that meet the ultimate guides for planning, i.e., the start-up milestones or the owner's need date.
* Track the construction effort on the Control Schedule, following the area concept until an overlap with the start-up activities begins.
* Govern the construction activity using the Start-up Plan once overlap occurs, ensuring alignment with the completion schedules.
* Monitor and report progress against the start-up milestones to ensure timely and successful project delivery.
• Track start-up on the Control Schedule to meet owner's need date
* Monitor and track the project completion schedules against the ultimate guides for planning, i.e., the start-up milestones or the owner's need date.
* Ensure that the construction work packages follow the area concept until an overlap with the start-up activities begins, and then switch to governing according to the Start-up Plan.
* Schedule project completion to meet the target dates (start-up milestones or owner's need date) on the Control Schedule.
* Verify and update the Control Schedule regularly to reflect changes in project progress and to ensure alignment with the ultimate guides for planning.
* Report any deviations from the planned start-up schedules to stakeholders, including the owner, and implement corrective actions as necessary.
• Combine personnel, materials, equipment, and time in work packaging
* Assign responsibility to each level of management (engineering, procurement, construction, start-up) for managing specific parts of the project.
* Develop a Control Schedule that presents the plan for completing the total project in a logical format, with enough detail to establish key relationships.
* Identify and quantify personnel, materials, equipment, and time requirements for each work package using resource allocation templates or similar tools.
* Ensure that each work package has its own unique combination of resources (personnel, materials, equipment), and schedule the milestones to meet the owner's need date or start-up milestone dates.
* Verify and update the Control Schedule regularly to reflect changes in project progress and to ensure alignment with the ultimate guides for planning.
• Present the Control Schedule logically to complete the project
* Review and approve the Control Schedule that presents the plan for completing the total project in a logical format and with enough detail to establish key relationships.
* Verify that each work package has its own unique combination of resources (personnel, materials, equipment), and schedule the milestones to meet the owner's need date or start-up milestone dates.
* Ensure that the construction effort is tracked on the Control Schedule by system, aligning with either the owner's need date or start-up milestones as the ultimate guides for planning.
* Monitor project progress regularly against the approved Control Schedule to identify any deviations or changes that are needed to stay on track and meet the desired completion date.
* Update the Control Schedule as necessary to reflect changes in project scope, schedule, or resources, and ensure that all stakeholders are informed of any adjustments.
• Tool: Project Control for Engineering (RS6-1)
* Provides a visual representation of the cost breakdown structure for an example project.
* Relates only to engineering work products that have been chosen as the basis for progress reporting.
* Can be used for specification writing, model building, and studies.
* Involves estimating and budgeting on a bulk allocation basis rather than as a production measure.
* Determines the ‘percentage complete’ by dividing the hours/dollars spent to date by the current estimate of hours/dollars at completion.
• Tool: Scope Definition and Control (RS6-2)
* Identifies major process equipment to establish cost relationships.
* Prepares order-of-magnitude estimates using conceptual assumptions with ± 30% accuracy.
* Develops control estimates once piping and instrumentation diagrams and civil drawings are available, aiming for ± 15% accuracy.
* Establishes detailed or definitive estimates only when detailed drawings are complete, targeting ± 10% accuracy.
* Focuses on developing the design to the point of scope definition, rather than relying on factored estimates.
• Tool: Contractor Planning for Fixed-Price Construction (RS6-4)
* Ensures that planning formats are compatible with control formats for future planning.
* Develops unique management guidance for each project to cover specific situations that are not covered by standard policies and procedures.
* Incorporates oral or written guidance into an official letter that designates the project team.
* Uses a matrix to identify functions, individuals, and organizational elements that are involved in a project's management effort.
* Provides bid cost data on contract forms, including lump-sum prices for total contracts or individual portions.
RS6-6 takeaway summary
_
(2). Advanced Work Packaging: Design through Workface Execution, Version 2.1 (RS272-1)
• Adopt advanced work packaging (AWP) recommendations. Note that success is evident with only partial adoption, particularly with regard to installation work packaging (IWP)
* Develop and implement an integrated process model that includes clear definitions of construction work packaging (CWP), engineering work packaging (EWP), and IWP.
* Review and update existing project processes to ensure alignment with AWP recommended practices and IWP definitions.
* Provide training and guidance to contractors regarding the implementation of IWP best practices, including functional role descriptions and process elaboration.
* Conduct regular assessments and monitor to evaluate contractor compliance with IWP recommendations and to identify areas for improvement.
* Consider mandating work packaging practices across capital project programs.
• Commit, plan, and execute well with champions
* Develop a clear understanding of AWP best practices and their benefits to ensure successful implementation.
* Identify and appoint champions within the organization who can facilitate adoption and drive cultural change.
* Establish a comprehensive planning process that integrates with existing project processes and includes early engagement with the engineering team.
* Provide training and guidance to stakeholders about the importance of effective planning, including lessons learned from previous projects.
* Monitor progress and assess the effectiveness of AWP implementation, making adjustments as needed to ensure successful execution.
• Ensure effective materials management, document control, and project control systems, and consider electronic management
* Develop a comprehensive materials management plan to ensure the timely delivery of required materials.
* Establish a centralized document control system to track and manage all project-related documents.
* Implement an integrated project control system that includes scheduling, budgeting, and reporting tools.
* Consider implementing an electronic management system for tracking and managing project data and documentation.
• Designate a separate workface planner/planning lead to ensure success in all project phases
* Appoint a dedicated workface planning lead to oversee front-end planning and the transition to jobsite coordination.
* Ensure that this workface planning lead has sufficient understanding of engineering, procurement, and construction processes.
* Assign multiple workface planners under the lead workface planner to prepare discipline-specific IWP with required support from other departments.
* Require these workface planners to have a deep understanding of construction practices for effective project execution.
* Empower the workface planning team to provide essential coordination among engineering, procurement, and construction personnel throughout all project phases.
• Recognize that all projects include some level of work packaging
* Identify: Determine the scope and complexity of each project to understand its unique requirements.
* Define: Establish clear expectations with stakeholders about the components that constitute a complete project deliverable.
* Develop: Create a comprehensive work breakdown structure (WBS) for each project to ensure that all tasks are taken into account.
* Coordinate: Collaborate with construction management, engineering, and other departments to align the work packages and execution plans.
* Verify: Regularly review and validate the completeness of projects against their respective WBS.
• Do not implement AWP midstream or without thought, preparation, and the commitment of adequate resources
* Plan: Develop a comprehensive project plan that includes all necessary steps and timelines before implementing AWP.
* Prepare: Ensure that all stakeholders, including planning team members, engineers, and contractors, are informed and committed to the implementation of AWP.
* Assess: Conduct a thorough assessment of current processes and resources to determine the changes that will be needed to support the successful implementation of AWP.
* Resource: Commit adequate resources (e.g., personnel and budget) to support the implementation of AWP, including training for planners and other stakeholders as necessary.
* Validate: Regularly validate that all steps are being taken to ensure a smooth transition to AWP, and make adjustments as needed.
• Prepare a rollout plan for AWP.
* Develop an implementation timeline to roll out AWP across all projects and teams.
* Identify key stakeholders who will be involved in the AWP process and provide training regarding definitions and procedures.
* Establish clear communication channels with project managers, planners, and other team members to ensure a smooth transition.
* Define the roles and responsibilities for each stakeholder group to avoid confusion or duplication of effort.
* Conduct regular progress monitoring and reporting to track implementation success and to identify areas for improvement.
• Align with all project disciplines, with emphasis on coordination between the engineering and construction teams
* Develop a comprehensive understanding of each discipline's requirements and expectations to ensure effective integration.
* Collaborate with engineering contractors, supply chain teams, and other stakeholders to develop CWP that aligns with the scope of work.
* Review and approve CWP deliverables to ensure that they meet the project execution plan and WBS requirements.
* Establish clear communication channels with all disciplines to facilitate information sharing and minimize misunderstanding.
* Conduct regular progress monitoring and reporting to track alignment across all project disciplines.
• Tool: Advanced Work Packaging: Design through Workface Execution, Version 3.1 (IR272-2)
• Vol1: Advanced Work Packaging: Design through Workface Execution
* Develops an IWP process that includes a work package summary, description of work, location, system or facility code, originator, contact information, sequenced work steps, reference documents, estimate of work hours and quantities, cost codes, witness or hold points, and special comments.
* Creates a flow chart for IWP development, execution, and closeout, with each stage having its own narrative explanation.
* Mitigates any constraints before issuing IWP to the field by involving responsible stakeholders in the process.
* Provides further narrative detail to support each process step, including scope, assumptions, and recommendations, as part of the IWP creation process.
* Closes out the IWP process by ensuring that all deliverables are met, lessons learned are documented, and a final report is submitted.
• Vol2: Advanced Work Packaging: Implementation Guidance
* Identifies revision history elements for CWP, including identifier, description, date created, and signature/approval process.
* Uses a CWP template as the basis for creation and reference, accommodating varying amounts of detail or formatting.
* Develops consistent practices regarding detail and style to meet client or stakeholder requirements by using formats such as narrative text, lists, references, or diagrams.
* Organizes the EWP template per guidance found in this tool reflect commonly accessed information in sequence, with contact information at the end for quick reference.
* Considers EWP as a deliverable that provides engineering and procurement support throughout the project’s lifecycle.
• Vol3: Advanced Work Packaging: Implementation Case Studies and Expert Interviews
* Tracks work packaging using appropriate rules of credit to accurately measure progress and earned value.
* Develops a physical document for IWP for distribution to the field; each IWP document contains a one-to-two page cover sheet that shows the required steps.
* Creates sub-IWP documents that are labeled by area using alphanumeric notation, thereby dividing the content into separate binders, such as IWP 100-A, B, and C.
* Uses IWP to assist superintendents in carrying out their work, not as a measure for punishment if target dates are not met.
* Includes relevant reference information, such as drawings, specifications, and work steps, which are required for IWP.
RS272-1 takeaway summary
(3). AWP Execution Planning Guide for Projects and Organizations (FR-390)
• Advanced Work Packaging (AWP) Review and Owner’s Guide
* Align engineering, procurement, and construction (EPC) processes early in the project to support seamless advanced work packaging (AWP) and enhance project coordination.
* Define clear construction work packaging (CWP) and installation work packaging (IWP) to ensure constraint-free work fronts for efficient field execution.
* Implement a robust Path of Construction during the planning stage to maintain a logical work sequence throughout the project’s lifecycle.
* Establish constraint management processes to proactively address and mitigate potential issues before they impact the construction schedule.
* Include AWP requirements in contracts and involve all stakeholders in early planning to foster alignment and accountability across project phases.
• Handbook A: Preliminary Planning and Design
* Define the project scope, contracting, and procurement strategies to establish clear project boundaries and objectives.
* Align EPC and start-up sequences to streamline workflow and avoid misalignment.
* Develop a work breakdown structure (WBS) to support coherent work packages across disciplines​​.
* Identify and incorporate early constraints, such as permitting and logistics, to mitigate potential project delays​.
* Conduct Path of Construction planning to ensure effective sequencing and coordination of work packages​.
• Handbook B: Detailed Engineering
* Integrate engineering schedules with AWP deliverables to align with the Path of Construction and to reduce delays​​.
* Formalize 3D model organization by CWP to support seamless EWP and IWP creation​.
* Identify engineering deliverable dependencies to synchronize engineering with procurement and to avoid schedule conflicts.
* Assign responsibility for tracking engineering progress based on CWP milestones.
* Standardize data formats to ensure compatibility and to ease the information transfer between the engineering and construction teams​.
• Handbook C: Construction Execution, Testing, and Completions
* Develop constraint-free IWP by coordinating EPC activities to ensure that all resources are available before fieldwork starts.
* Track IWP progress and manage closeout to maintain alignment with the construction schedule​.
* Engage a Workface Planning lead to oversee IWP preparation and manage resource allocation effectively​.
* Utilize 3D and 4D visualization tools to enhance work package planning and progress tracking​​​.
* Collect lessons learned from each completed IWP to refine and improve the AWP implementation process.
• Handbook D: Commissioning and Start-up
* Define boundaries for safe work practices (SWP) and the work scope to ensure safe and efficient commissioning.
* Identify and manage SWP constraints to streamline the transition from construction to start-up.
* Track completion of prior IWP to confirm readiness before issuing SWP​.
* Automate SWP tracking using digital tools for better visibility and control over the commissioning progress​​​​.
* Develop a commissioning and startup (CSU) punch list and track closure to prepare systems for operational start-up.​​.
• Handbook E: Procurement and Supply Chain Process
* Define procurement timelines for long-lead items that are aligned with the Path of Construction to support critical project stages​.
* Establish Procurement Work Packages (PWPs) if necessary to facilitate material alignment with construction priorities​.
* Track vendor data and shipment schedules by CWP and IWP for visibility of material readiness on-site.
* Integrate procurement systems with project management tools to streamline tracking and constraint management across the EWP, CWP, and IWP processes.
* Synchronize the procurement and construction schedules to ensure the timely delivery of materials without delays to fieldwork​​.
• Enterprise Guide
* Secure top leadership support to drive AWP adoption across projects, and ensure organizational alignment to AWP adoption by identifying challenges, such as alignment with existing processes, to streamline enterprise-wide implementation.
* Establish an AWP program with clear knowledge transfer mechanisms to standardize practices across all projects.
* Implement mandatory AWP training to facilitate consistent knowledge and skills across project teams​.
* Develop centralized data system metrics and track project progress, thereby enabling continuous improvement and accountability.
FR-390 takeaway summary
2. ALIGNMENT (3)
(1). Pre-Project Planning Tools: PDRI and Alignment (RS113-1)
• Ten critical alignment factors (in order of importance)
* 1) Stakeholders are appropriately represented on the project team.
* 2) Project leadership is defined, effective, and accountable.
* 3) The priority among the cost, schedule, and required project features is clear.
* 4) Communication within the team and with stakeholders is open and effective.
* 5) Team meetings are timely and productive.
* 6) The team culture fosters trust, honesty, and shared values.
* 7) The pre-project planning process includes sufficient funding, schedule, and scope to meet objectives.
* 8) The reward and recognition system promotes meeting project objectives.
* 9) Teamwork and team building programs are effective.
* 10) Planning tools (e.g., checklists, simulations, and work flow diagrams) are effectively used.
• Five categories to achieve and maintain alignment
* Execution processes: Project systems, processes, and procedures
* Company culture: Attitudes, values, behavior, and environment of the company and team.
* Information: Data elements, including project objectives, used to define the scope of the project.
* Barriers: Obstacles to creating and maintaining alignment.
* Tools: Software programs, checklists, and aide-memoirs that are typically used to develop and manage projects
• Achieving and maintaining alignment are critical to project success
* Clearly define project objectives that meet the business requirements and overall corporate strategy.
* Ensure that stakeholders are appropriately represented on the pre-project planning team.
* Establish clear priorities among the cost, schedule, and required project features.
* Foster open and effective communication within the team and with stakeholders.
* Appoint defined, effective, and accountable project leadership to drive alignment.
• Tool: Alignment During Pre-Project Planning: A Key to Project Success, Version 2.1 (IR113-3)
* Highlights the importance of alignment: Emphasizes alignment in pre-project planning as critical to project success, particularly in complex, multiple stakeholder projects.
* Identifies key areas for improvement: Outlines five categories that impact alignment, i.e., culture, execution processes, information, tools, and barriers.
* Introduces the Alignment Thermometer: Provides a diagnostic tool to measure and maintain team alignment throughout the pre-project planning phase.
* Stresses effective leadership and communication: Underscores the role of clear leadership and open communication in building a cooperative team environment.
* Suggests best practices: Recommends practices such as stakeholder inclusion, structured processes, and appropriate reward systems to foster alignment and reduce project risks.
• Refer to the following Best Practices for other takeaways in this report that are relevant to pre-project planning: 7. Front-end Planning and 16. Team Building
RS113-1 takeaway summary
(2). Front End Planning: Break the Rules, Pay the Price (RS213-1)
• Define the project scope prior to moving forward with the design and construction phases
* Use front-end planning tools such as the Project Definition Rating Index to aid in defining the project scope.
* Conduct thorough stakeholder identification and partnering to ensure that all project elements are defined early in the project.
* Develop a clear team charter that outlines the project goals, objectives, and roles for all stakeholders.
* Ensure that the technical scope is identified and agreed upon by all parties involved in the project.
* Verify that adequate resource expenditures (3% to 5% of total installed cost) have been made during the front-end planning phase.
• Align the project team members, including key stakeholders
* Define clear goals and objectives with all stakeholders to ensure a common understanding of the project scope.
* Identify and involve key stakeholders in front-end planning activities to prevent later project problems.
* Develop accountability and responsibility among team members through regular meetings and progress updates.
* Use the Construction Industry Institute’s Alignment Thermometer tool to measure stakeholder alignment and identify potential issues early in the project.
* Foster open communication channels with all stakeholders, including consultants and contractors, to ensure that everyone is working towards the same objectives.
• Build the project team, including owner, stakeholders, and consultants
* Define the project’s goals and objectives with all stakeholders to ensure a common understanding of the project scope.
* Develop accountability and responsibility among team members through regular meetings and progress updates.
* Involve key stakeholders in front-end planning activities to prevent later project problems.
* Foster open communication channels with consultants, contractors, and other stakeholders to ensure that everyone is working towards the same objectives.
* Establish a clear understanding of the roles and responsibilities of each team member within the project team.
• Involve both owners and contractors
* Engage with consultants early in the planning process to ensure that their expertise is incorporated into the project goals.
* Foster open communication channels with contractors by scheduling regular meetings and progress updates.
* Collaborate with contractor representatives on front-end planning activities, such as developing the project scope and schedules.
* Encourage contractor involvement in stakeholder identification and risk assessment exercises to prevent later project problems.
* Establish a clear understanding of the roles and responsibilities of the members within the project team through joint owner-contractor communication.
• Staff critical project scoping and design areas with capable and experienced personnel
* Assemble a team of experts in piping design, equipment design, and construction to ensure the thorough understanding of the project requirements.
* Assign experienced professionals to lead project teams that are responsible for the scope definition, schedule development, and budgeting.
* Recruit skilled staff members who are familiar with unique project characteristics, such as new technologies or locations, to mitigate risks.
* Ensure that key personnel are involved in front-end planning activities from the outset to provide valuable insights.
* Utilize contractors' expertise by incorporating their experienced professionals into the project team during the scoping and design phases.
• Refer to the following Best Practices sections in this report for other takeaways that are relevant to front-end planning: 7. Front-end Planning and 14. Project Risk Assessment
RS213-1 takeaway summary
(3). Effective Project Alignment for Construction Success (RS310-1)
• Advance project execution plans (PEPs)
* Ensure provisions for elements such as scope definition and interface management.
* Extend provisions for leading execution strategies such as advanced work packaging and modularization.
* Dedicate resources for the competent creation of the PEP, as a PEP is a front-end planning deliverable.
* Ensure handover of the PEP to subsequent phases.
* Make the PEP serve as a living document.
• Engage suppliers earlier and more effectively in the project
* Engage suppliers in the planning activities.
* Do not assume that the supplier will not participate or will not add value.
* Review requests for proposals, requests for quotes, and purchase orders to ensure clear definitions of scope, data needs, and data delivery dates.
• Improve alignment procedures; ensure consistent execution
* Ensure inclusion and consistency of procedures for alignment, team building, on-boarding, and continuity of the team.
* Ensure that procedures are not lacking in one or more areas across all project phases.
* Incorporate procedures that involve all appropriate stakeholders in the development and sign-off of key project deliverables and tasks.
* Ensure effective transitions between project phases.
• Tool: Effective Project Alignment for Construction Success (IR310-2)
* Standardizes PEPs: Establishes a consistent PEP structure to align stakeholders from the front-end planning phase through the project execution and turnover phases for effective coordination.
* Implements alignment procedures: Utilizes an alignment checklist to ensure systematic alignment across the engineering, procurement, and construction phases, thereby addressing common gaps.
* Engages suppliers early in the project: Utilizes a detailed supplier engagement checklist to foster strong supplier relationships and clarify deliverables, thereby enhancing project outcomes.
* Promotes alignment behaviors: Cultivates collaborative behaviors across all project phases to improve information flow, accountability, and engagement among stakeholders.
* Leverages automation for consistency: Uses automated tools to streamline data sharing, enhance alignment, and improve project performance across the project’s lifecycle.
RS310-1 takeaway summary
3. BENCHMARKING & METRICS (2)
(1). Benchmarking Associates Guide (IR-BMM-2 v2)
• Obtain organizational commitment to benchmarking as a basis for improvement
* Schedule meetings with executive leadership to discuss the importance of benchmarking and its alignment with business strategies.
* Develop a clear plan that outlines the goals, objectives, and expected outcomes of the benchmarking initiative.
* Communicate the benefits of benchmarking, such as identifying best practices and areas for improvement, to stakeholders across the organization.
* Ensure that all project managers understand their role in providing data and participating in the benchmarking process.
* Obtain a formal commitment from executive leadership to support the benchmarking initiative, and provide necessary resources.
• Identify a person to be responsible for benchmarking coordination
* Designate an individual to serve as the Benchmarking Associate, and provide that person with necessary training.
* Ensure that the Benchmarking Associate has access to relevant data and tools that are needed for effective benchmarking coordination.
* Communicate with the Benchmarking Associate regularly to ensure that they understand their role in supporting both upper management and project management.
* Provide guidance on ways to integrate benchmarking results into organizational decision-making.
* Monitor the Benchmarking Associate's progress and provide feedback to help them optimize their performance.
• Ensure that the Benchmarking Associate learns the basics of the Construction Industry Institute’s benchmarking program
* Schedule time for the Benchmarking Associate to attend 60- 90-minute Data Warehouse training.
* Have the Benchmarking Associate review learning objectives that cover data usage to improve projects, data submissions, and project performance metrics.
* Ensure that the Benchmarking Associate completes the mandatory prerequisite training for accessing the Data Warehouse portal.
* Verify the Benchmarking Associate’s comprehension of data usage in order to submit project details and assess project performance.
• Identify project managers to be responsible for project benchmarking and improvement
* Clearly explain to project managers that their role is crucial in providing accurate and complete data for benchmarking.
* Remove projects with incomplete or unreliable data to ensure high-quality submissions.
* Highlight the importance of continuous monitoring and evaluation of project performance during project execution.
* Explain the purpose of benchmarking to project managers, emphasizing that benchmarking is not a punitive exercise but rather an opportunity for improvement.
• Determine levels of use in terms of the activities to benchmark and their quantity
* Identify a diverse set of projects that represent typical work performed by the organization.
* Eliminate projects with incomplete or unreliable data to ensure accurate results.
* Select only an assortment of projects, not necessarily only the best performing ones, to set realistic benchmarks.
* Choose projects that are representative of the organization to provide a realistic benchmark of performance.
* Communicate clearly to project managers about the purpose and benefits of benchmarking.
• Enter project data during project execution
* Submit project data over time using the Integration Toolkit, or submit data after project closeout.
* Use an easy-to-use Excel-based input form to enter project data into the Data Warehouse format.
* Document the location of data obtained from internal project controls and construction management systems while inputting project data in the Integration Toolkit.
* Develop reports that extract data in the Data Warehouse format to facilitate analysis.
• Finalize and submit the project questionnaire at project closeout or by phase
* Review the project data online to ensure accuracy and completion.
* Complete the project questionnaire once a project phase is complete.
* Ensure that all required information has been submitted before submitting the project questionnaire.
* Submit the completed project questionnaire within the Data Warehouse.
* Validate and review the submitted project with the Construction Industry Institute benchmarking & metrics.
• Generate a project and/or enterprise report
* Obtain a Performance Assessment Key Report once all project data have been submitted.
* Using the metrics entered, analyze the project’s performance against that of hundreds of similar projects in the industry.
* Browse project performance across industries, project types, cost categories, practices, etc. via the Data Miner.
• Repeat Nos. 5 through 8 as part of a continuous improvement program
* Repeat benchmarking and project excellence by submitting other projects.
* Benchmark internally across the company against best-in-class company performance.
* Understand and commit to the efforts required to become successful and excellent in future projects.
• Engage with the Data Analytics Community for Business Advancement (DA CBA) to stay abreast of benchmarking initiatives and industry trends
* Check the DA CBA webpage on the Construction Industry Institute website for information about benchmarking initiatives.
* Review metrics scores for basic project controls, such as cost growth and schedule growth, to stay informed about performance benchmarks.
* Participate in discussions with other construction professionals through the DA CBA to share lessons learned and best practices.
IR-BMM-2 v2 takeaway summary
(2). Productivity Benchmarking Summary Report (BMM2011-1)
• Assist companies/projects in setting project objectives for future assessment using the data mining tool
* Define clear productivity metrics that are aligned with project goals to enable accurate benchmarking and tracking.
* Establish data collection protocols to gather relevant productivity data throughout the project phases.
* Set target benchmarks for productivity based on industry standards and comparable projects.
* Use the data mining tool to analyze past project performance and identify improvement areas.
* Regularly review and adjust objectives based on evolving project conditions and productivity insights.
• Help participants of the benchmarking effort to identify productivity problems on their projects through the use of key reports
* Review key report quartiles to pinpoint areas with low productivity relative to comparable projects.
* Analyze the percentile bars in the key reports to determine specific productivity metrics that fall below industry standards.
* Identify recurring productivity bottlenecks across project phases using aggregated key report data.
* Focus on metrics in the lowest quartile to address critical productivity weaknesses that negatively impact project outcomes.
* Compare project performance against similar project types to refine productivity improvement strategies.
• Provide data analysis results to help participants of the benchmarking effort understand the relationship between their work processes and productivity
* Conduct comparative analyses between the work processes and productivity metrics to highlight impactful activities.
* Identify specific work processes that are associated with high and low productivity to guide targeted improvements.
* Use data visualizations to show ways that process adjustments affect productivity outcomes.
* Benchmark productivity across similar projects to reveal process-driven productivity variations.
* Review process inefficiencies in low-productivity areas and suggest best practices to enhance performance.
BMM2011-1 takeaway summary
4. CHANGE MANAGEMENT (1)
(1). Quantitative Effects of Project Change (RS43-2)
• Measure the relationships between the overall project change ratio and productivity, both in terms of engineering and construction
* Track any changes to the original scope work, by craft, throughout the project.
* Monitor the overall project change ratio and its impact on engineering and construction productivity.
* Analyze the obtained data to identify trends and correlations between the change ratios and productivity declines.
* Develop predictive models to forecast the potential productivity impacts associated with future changes.
* Implement process improvements to minimize or mitigate the negative effects of high-change periods.
• Measure the relationships and ratio between the change work and original scope work
* Forecast expected changes by craft and period (e.g., months) to predict or minimize productivity declines.
* Track actual changes against forecasted changes to identify trends and areas for improvement.
* Analyze the impact of high-change periods on labor costs, material usage, and overall project schedule.
* Develop strategies to manage change work efficiently, such as phasing construction activities or adjusting the resource allocation.
* Regularly review and adjust forecasting methods to ensure accuracy and effectiveness in managing future changes.
• Measure relationships and ratio between the total change dollars and the material dollars
* Track the ratio of the total change dollars to material dollars over time to measure implementation efficiency.
* Analyze trends and patterns in this ratio to identify areas for improvement and optimize the change management process.
* Use data to forecast potential impacts on the project schedule, budget, and resource allocation that are due to changes.
* Develop strategies to minimize waste and inefficiencies by optimizing the use of materials and resources during change implementations.
* Regularly monitor and adjust these metrics to ensure continuous process improvements and better decision-making.
• Analyze the probability of on-time project completion relative to reported progress at key project milestones
* Review and analyze close-out reports from completed projects to identify trends in project schedules.
* Plot the probability of completing projects on time against reported progress at key milestones (e.g., 25%, 50%, 75% complete).
* Identify patterns or correlations between reported progress and actual completion dates to inform future project planning.
* Use these analysis results to develop strategies for improving schedule performance, such as adjusting the resource allocation or implementing a more effective change management process.
* Regularly update and refine the probability of on-time project completion based on new data from completed projects.
• Analyze the probability of completion on or under budget relative to reported cost trends
* Review and analyze close-out reports from completed projects to identify trends in project costs.
* Plot the probability of completing projects within budget against reported cost trends at key milestones (e.g., 25%, 50%, 75% complete).
* Identify patterns or correlations between reported cost trends and actual completion dates to inform future project planning.
* Use these analysis results to develop strategies for improving budget performance, such as adjusting the resource allocation or implementing a more effective change management process.
* Regularly update and refine the probability of on-budget completion based on new data from completed projects.
• Analyze the amount of change for projects of varying size and type
* Categorize completed projects by size (e.g., small, medium, large) and type (e.g., revamp, new construction).
* Analyze close-out reports to identify trends in the amount of change experienced across the different project categories.
* Calculate the ratio of total change dollars to material dollars for each project category to measure implementation efficiency.
* Compare the results from various project categories to identify patterns or correlations between the amount of change and the project size and type.
* Use these comparative analysis results to inform future project planning, resource allocation, and risk management strategies.
• Tool: Project Change Management (SP43-1)
* The tool is designed to:
* Establish a good up-front baseline agreement that allows all team members to recognize and measure change.
* Use a classification process to determine whether the change is required or elective.
* Generate a measurable outcome that indicates successful achievement of some quality objective.
* Use this metric to enable the appropriate management level to implement or reject the change in a timely manner.
* Use analysis results to inform future project planning, resource allocation, and risk management strategies.
* Clearly define the person who will be responsible for taking the necessary action, based on the metrics supplied.
* Collect and store data that are relevant to management decision-making and change measurements, and to make these data accessible.
* Use the data collection system to facilitate the timely presentation of analyzed data to the appropriate decision-makers.
* Use established benchmarks to monitor project performance.
* Ensure that all team members consistently use the recording or reporting system to document all changes.
* Establish a recognition/reward system for those who initiate beneficial change.
* Establish agreements between the project participants at the different levels of the project.
RS43-2 takeaway summary
5. CONSTRUCTABILITY (1)
(1). Preview of Constructability Implementation (RS34-2)
• Commit to implementing constructability
* Understand constructability objectives, methods, concepts, and barriers.
* Perform self-assessment and identify barriers.
* Assess and recognize constructability benefits.
* Develop implementation policy.
• Establish a corporate constructability program
* Identify constructability sponsor/champion.
* Establish functional support organization and procedures.
* Develop lessons learned database.
• Obtain constructability capabilities
* Assemble key owner team members.
* Define constructability objectives and measures.
* Select a project contracting strategy.
* Secure contractors, vendors, and consultants.
• Plan constructability implementation
* Develop a constructability team.
* Identify and address project barriers.
* Consult the applications matrix and lessons learned database.
* Develop constructability procedures and integrate them into project activities.
• Implement constructability
* Apply constructability concepts and procedures.
* Monitor and evaluate project program effectiveness.
* Document lessons learned.
• Update the corporate program
* Evaluate the corporate program’s effectiveness.
* Modify the organization and procedures.
* Update lessons learned databases.
• Tool: Constructability Implementation Guide, Second Edition (SP34-1)
* Promote constructability for efficiency: Implementing constructability can significantly reduce project costs, schedules, and improve quality, thereby offering a high return on investment.
* Follow the constructability roadmap: The guide outlines a roadmap with six milestones (golden nuggets above) for establishing and sustaining corporate and project-level constructability programs.
* Utilize constructability tools: The guide provides 17 tools to evaluate, plan, and implement constructability to address barriers and enable continuous improvement.
* Focus on training and support: Emphasis on training, team-building, and management support is critical to embedding constructability in an organizational culture.
* Document lessons learned: Maintaining a lessons learned database is essential for capturing insights and refining future projects.
RS34-2 takeaway summary
6. DISPUTES PREVENTION & RESOLUTION (1)
(1). Disputes Prevention and Resolution Techniques in the Construction Industry (RS23-1)
• Focus on dispute prevention as well as dispute resolution and emphasize the need to resolve issues on-site in a timely manner
* Implement structured training in negotiation and conflict resolution skills for project managers to enhance their on-site issue resolution capabilities.
* Establish formalized on-site dispute resolution mechanisms, such as Dispute Review Boards (DRBs), to address conflicts promptly and avoid escalation.
* Facilitate early intervention by project sponsors or advisors to resolve issues at the project level before involving external parties.
* Promote honest, transparent communication among all project stakeholders to prevent misunderstandings and encourage collaborative problem-solving.
* Regularly review project documentation and contracts to ensure clarity in responsibilities and minimize potential sources of dispute.
• Move away from the concept of a claim as the product of a dispute
* Encourage the early and proactive identification and resolution of potential claims to prevent escalation into formal disputes.
* Treat claims as a routine part of project management, addressing them constructively to avoid adversarial outcomes.
* Document issues thoroughly and consistently to provide clarity and support collaborative problem-solving rather than adversarial claims.
* Develop clear communication channels for reporting and discussing claims to maintain transparency and mutual understanding.
* Focus on continuous improvement in contract administration practices to mitigate claim occurrences and strengthen project relationships.
• Demonstrate conviction through the systematic use of dispute prevention and resolution techniques throughout the design and construction phases
* Integrate dispute prevention clauses in contracts to set clear expectations for resolving issues collaboratively and efficiently.
* Apply constructability reviews during the design phase to identify and mitigate potential issues that could lead to disputes during construction.
* Establish risk-sharing mechanisms that allocate responsibilities fairly, thereby reducing misunderstandings and minimizing claims during the project.
* Use partnering agreements to promote trust and open communication, aligning all parties toward common project goals.
* Schedule regular check-ins among project teams to address emerging issues proactively and reinforce a cooperative approach to conflict resolution.
• ‘Start right’: Implement strategies during the preconstruction engineering stage to reduce project uncertainties and minimize process problems
* Deploy competent engineering and documentation.
* Perform constructability analysis.
* Conduct realistic risk allocation.
* Identify disputes resolution clauses.
* Enhance partnering.
* Implement incentive programs.
• ‘Stay right’: Implement partnering agreements and team building to improve interpersonal skills, responsiveness, and negotiating ability
* Cultivate project partnering.
* Implement training and development.
* Ensure honest negotiation.
• Provide for resolution: Implement procedures to facilitate the quick and efficient on-site resolution of disputes, and keep project managers involved in the process
* Glean advisory opinion.
* Ensure fact-based mediation.
* Encourage mini-trials.
* Implement nonbinding arbitration.
* Implement binding arbitration.
* Encourage private judging.
• Tool: Prevention and Resolution of Disputes Using Disputes Review Boards (IR23-2)
* Document disputes: The process for dispute prevention and resolution is intended to be documented with written submittals to the DRB.
* Resolve quickly: Disputes shall be considered as quickly as possible, taking into consideration particular circumstances and the time required for documentation.
* Present complete arguments: Neither owner nor contractor should rely on the DRB to develop arguments. Presentations must be complete and questioning between parties must be allowed.
* Minimize formality: The key to success lies in the trust among all parties; therefore, a simple consensual process with minimal formalities should be employed.
* Focus on facts: Disputes shall be resolved as quickly as possible by focusing on record or fact.
• Tool: Disputes Potential Index, Version 2.0 (SP23-3)
* The tool is designed to:
* Evaluate disputes potential via logistic regression analysis.
* Develop the Disputes Potential Index (DPI) model from 21 project variable questions into eight input variables.
* Calculate a model score as the probability (percentage) for good, average, or poor dispute performance.
* Use the DPI to ‘start right’ and ‘stay right’ in terms of contract readiness review and periodic monitoring.
* Provide insights into the potential for disputes based on the owner's management, contractor's organization, project complexity, project size, financial planning, scope definition, and risk.
RS23-1 takeaway summary
7. FRONT END PLANNING (3)
(1). Front End Planning: Break the Rules, Pay the Price (RS213-1)
• Identify the following typical cost elements during the front-end planning phase
* Planning team personnel expenses
* Conceptual and detailed design costs
* Consultant fees and expenses
* Environmental permitting costs
* Project manager/construction manager fees
* Licensor fees
• Determine the following typical activities and products of front-end planning
* Option analysis
* Scope definition and boundaries
* Life-cycle cost analysis
* Cost and schedule estimate
* Site investigation
* Environmental analysis
* Process design basis
* Initial equipment design
* Space planning, including room data sheets and stacking diagrams
* Site layout
* Project execution approach, including project control plan
* Procurement plan
* Architectural renderings
* Appropriation submittal package
• Develop and consistently follow a defined front-end planning process
* Establish a structured front-end planning process that guides the organization through various planning efforts.
* Create checklists to ensure that all necessary steps are taken during each phase of the planning process.
* Conduct regular gate checks to provide defined deliverables and track progress against project goals.
* Facilitate front-end planning techniques, such as charter development, partnering, scope definition, stakeholder identification, and alignment.
* Incorporate a well-defined front-end planning process into the organization's standard operating procedures
• Use front end planning tools
* Utilize the Project Definition Rating Index (PDRI) to aid in defining the project scope and to ensure that project elements are well-defined.
* Implement a structured process that includes checklists and gate-checks to guide the organization through various planning efforts.
* Leverage stakeholder identification and partnering tools to facilitate effective communication among all parties involved in the project.
* Apply technical scope identification tools to ensure the clear understanding of the project’s goals, objectives, and roles for all stakeholders.
* Conduct thorough front-end planning using a gated process that includes reviews and approvals at each stage to prevent costly rework later.
• Address labor force skill and availability during planning
* Conduct a thorough analysis of local labor market conditions to identify potential shortages or surpluses.
* Engage with contractors and suppliers to gather information about their anticipated workforce needs and any concerns they may have about labor availability.
* Develop contingency plans for addressing potential labor force skill gaps, such as training programs or recruitment strategies.
* Incorporate contract clauses that address labor issues, including provisions for labor shortages or surpluses.
* Conduct area labor surveys to gain a better understanding of local labor market conditions and identify areas where additional support may be needed.
• Provide leadership at all levels for the front-end planning process, including executive and project owner and contractor
* Establish a dedicated team to oversee the front-end planning process.
* Appoint an executive sponsor to champion the importance of effective front-end planning.
* Ensure that project managers are trained in front-end planning best practices and are empowered to lead the process.
* Develop clear communication channels with contractors to ensure seamless collaboration during front-end planning.
* Conduct regular progress updates and reviews to monitor the effectiveness of the front-end planning process.
• Tool: Front End Planning Toolkit 2014.1 (IR213-2)
* Define front-end planning as developing strategic information to address risk and to commit resources for project success.
* Indicate that well-performed front-end planning can reduce costs, minimize variability, and increase the likelihood of meeting environmental and social goals.
* Identify the correlation between percent design completed and project success at the end of the front-end planning process.
* Recognize alignment during pre-project planning as an important factor in successful front-end planning.
* Identify schedule and budget limitations, as well as business stakeholders’ views on front-end planning, as barriers to its implementation.
• Refer to 2. Alignment and 14. Project Risk Assessment for other golden nuggets in this report.
RS213-1 takeaway summary
(2). Pre-Project Planning Tools: PDRI and Alignment (RS113-1)
• Properly define the scope and align it with business needs during pre-project planning to improve both the cost and cycle time needed to design and construct capital facilities
* Identify: Clearly define project objectives, goals, and deliverables through stakeholder input and collaboration.
* Develop: Create an adequate scope statement that outlines all work required for the project, including exclusions and assumptions.
* Align: Ensure alignment among project team members by establishing clear roles, responsibilities, and expectations.
* Measure: Use tools such as the Project Definition Rating Index (PDRI) to measure the completeness of the scope definition and identify areas of risk.
* Verify: Validate the scope definition through regular reviews with stakeholders and the project team to ensure that it remains accurate and relevant.
• Use the PDRI to measure the completeness of the scope definition and to identify areas of risk
* Utilize: Apply the PDRI as a checklist to determine the necessary steps in defining the project scope.
* Measure: Use the PDRI to assess the completeness of the project scope definition and identify potential risks and areas for improvement.
* Identify: Analyze the results from the PDRI to pinpoint specific aspects of the project that may be prone to risk or uncertainty.
* Review: Regularly review and update the project scope definition based on new information or changes in project requirements.
* Validate: Verify the accuracy and relevance of the project scope definition through stakeholder input and ensure that it remains aligned with business needs.
• The PDRI serves as the following:
* A checklist that the project team can use in determining the necessary steps needed to define the project scope.
* A listing of standardized scope definition terminology throughout the construction industry.
* An industry standard for rating the completeness of the project scope definition to facilitate risk assessment, predict escalation, and evaluate the potential for disputes..
* A means to monitor progress at various stages during the pre-project planning effort and to focus efforts on high risk areas that need definition.
* A tool to aid in communication between owners and design contractors by highlighting poorly defined areas in a scope definition package.
* A means for project team members to reconcile differences using a common basis for project evaluation
* A training tool for companies and individuals throughout the industry
* A benchmarking tool for companies to use in evaluating the completion of the scope definition versus the probability of success on future projects.
• Use the following four excellent Construction Industry Institute resources to address critical pre-project planning implementation issues
* Publication 12-1 is an agreement matrix for identifying, communicating, reinforcing, and controlling project objectives. This tool quantifies the agreement among the various project participants.
* SP 39-2 provides a pattern for an organization’s pre-project planning process and identifies performed tasks.
* IR 113-2 describes the PDRI for industrial projects that can be used to measure the completeness of the scope definition and to manage the pre-project planning process.
* IR 113-3 contains an Alignment Thermometer to determine whether the team is focusing on the issues and processes that have a substantial effect on team alignment.
• Tool: Project Definition Rating Index (PDRI): Industrial Projects, Version 5.0 (IR113-2)
* Evaluate project readiness: The PDRI assesses the maturity and accuracy of the front-end planning process to improve decision-making and project outcomes.
* Define the scope effectively: This feature includes 70 scope elements and 27 accuracy factors to identify front-end planning scope gaps.
* Boost performance: Projects with high maturity and accuracy scores improve cost control and minimize changes.
* Support multiple phases: The PDRI is usable across project phases as a checklist, risk tool, and progress tracker.
* Foster collaboration: The PDRI encourages communication among owners, designers, and contractors for aligned project goals.
• Refer to 2. Alignment and 16. Team Building for other golden nuggets in this report.
RS113-1 takeaway summary
(3). Compass: An Assessment Tool for Improving Project Team Communications (RS105-1)
• Ensure effective communication for successful project completion
* Develop an assessment tool to measure communication effectiveness during engineer-procure-construct (EPC) project phases.
* Implement clear communication protocols across all project phases.
* Train project team members on effective communication strategies.
* Evaluate the relationship between communication effectiveness and project success.
* Regularly monitor communication effectiveness to identify and address communication issues promptly.
• Identify opportunities to improve communication effectiveness
* Measure communication effectiveness using a tool such as Compass.
* Identify specific communication areas that need improvement based on effectiveness scores.
* Allocate resources to enhance communication in weak areas identified by the assessment tool.
* Track changes in communication effectiveness over the project lifecycle to gauge improvements.
* Implement strategies based on data to improve overall project success.
• Leverage Compass to aid in measuring and improving project team communications
* Use Compass at the project's start to establish a baseline for communication effectiveness.
* Conduct regular reassessments using Compass to monitor progress.
* Analyze data from Compass to identify strengths and weaknesses in communication.
* Compare project communication scores against benchmarks from other Construction Industry Institute projects.
* Develop targeted improvement strategies based on insights gleaned from Compass.
• Tool: Compass: Communications Project Assessment Tool, Version 2.1 (IR105-2)
* Define key enablers for project success, focusing on tools and best practices for improved outcomes in construction.
* Highlight collaboration and technology as critical drivers for efficiency and risk mitigation.
* Recommend standardized procedures to streamline processes and improve project consistency.
* Emphasize the importance of data integration and interoperability to support real-time decision-making.
* Encourage stakeholder engagement to enhance alignment, accountability, and project transparency.
• Refer to 16. Team Building for other golden nuggets in this report
RS105-1 takeaway summary
8. IMPLEMENTATION OF CII RESEARCH (3)
(1). The Implementation Planning Model: An Overview (RS246-1)
• Place emphasis on obtaining communications assistance to convey the implementation message to respective organizations
* Identify experienced implementers who can provide guidance and support in developing effective communication strategies.
* Engage with new implementers to understand their current communication mechanisms and identify areas where additional resources are needed.
* Utilize e-mail distributions, staff meetings, and other existing communication channels to disseminate information about Construction Industry Institute (CII) -related activities.
* Develop a comprehensive communications plan that incorporates the perspectives of both new and experienced implementers.
* Collaborate with the Implementation Champion to establish clear lines of communication and ensure consistent messaging across all levels of the organization.
• Understand the value of the link between the Implementation Champion and the network of experts in the organization
* Identify experienced implementers who can provide guidance and support to the Implementation Champion in developing effective implementation strategies.
* Recognize the importance of establishing a strong connection between the Implementation Champion and networks of experts within the organization for successful implementation.
* Foster open communication channels between the Implementation Champion, network experts, and other stakeholders to ensure consistent messaging and collaboration.
* Develop training programs or workshops that educate Implementation Champions on ways to leverage expert knowledge and resources in their organizations.
* Encourage Implementation Champions to seek input from subject matter experts when developing implementation plans to increase the likelihood of successful outcomes.
• Consider the geographic deployment of an organization to be a primary indicator of the focal points that an organization should consider
* Identify: Determine the organization's geographic scope and distribution across different regions or divisions.
* Assess: Evaluate how this geographic deployment affects the organization’s implementation needs, such as regulatory requirements or local cultural differences.
* Prioritize: Focus on implementing processes that are most critical to each region or division based on its specific needs and challenges.
* Customize: Tailor the implementation approach for each region or division according to its unique characteristics, resources, and constraints.
* Monitor: Continuously monitor progress across different regions or divisions and adjust the implementation strategy as needed.
• For implementation success, acknowledge minimal differences between contractors and owners in terms of their experience-based needs and their perspectives
* Recognize: Acknowledge that the contractor organizations and the owner organization share similar experiences and perspectives regarding implementation success.
* Align: Ensure that the implementation approach is aligned with the commonalities identified between contractors and owners, such as emphasis on the importance of understanding the proposed practice for Implementation Champions.
* Collaborate: Foster collaboration opportunities to leverage shared knowledge and best practices that are used by both contractor organizations and owner companies.
* Focus: Prioritize factors that are critical to implementation success, regardless of whether they are for the contractor or owner organization, by focusing on key attributes such as understanding the proposed practice.
• Tool: The Implementation Planning Model: Steps to Success, Version 1.2 (IR246-2)
* Establish a structured process: Follow the 10-stage model to implement new practices systematically, beginning with needs analysis and ending with benchmarking.
* The 10-stage model steps are to conduct needs analysis, obtain management buy-in, establish steps, adapt matrix, develop plan, communicate plan, perform change audit, implement tasks/plan, perform step evaluations, and benchmark.
* Adapt and customize: Use the Implementation Matrix to tailor each implementation phase according to organizational needs, which include specific tasks, barriers, and success metrics.
* Emphasize communication and support: Secure buy-in and continuous support from management and staff, employing clear communication to reduce resistance.
* Thoroughly prepare: Conduct a change audit to assess readiness across eight key areas including vision, support, communication, roadmap, necessity, champion, empowerment, and education to address gaps before implementation.
* Monitor and evaluate: Utilize tools such as Step Evaluations to measure progress at each stage, thereby ensuring that goals are met before advancing to the next phase.
• Tool: Support for the Implementation Champion: The Experience Reference Index (IR246-3)
* Define implementation needs based on the organization’s experience with CII practices using the Experience Reference Index (ERI) for better-focused strategies.
* Emphasize the role of an Implementation Champion with strong organizational connections and adapt support as experience levels evolve.
* Adjust implementation plans with a focus on communication, resources, and leadership requirements at each level of organizational maturity.
* Use the ERI’s structured levels, New, First, Repeat, and Integrated, to guide the implementation process and adapt the scope and support over time.
* Address additional considerations, such as organizational size and geographic scope, to refine implementation strategies effectively.
RS246-1 takeaway summary
(2). Measuring Organizational Implementation Status: Development of the CII Knowledge Implementation Index (RS166-1)
• Recognize: Organizational implementation of project knowledge varies widely among the Construction Industry Institute (CII) organizations, which indicates room for improvement in terms of consistency
* Provide resources for the implementation effort, including time, money, focus, and incentives.
* Develop better documentation of processes and provision of results of implementation efforts.
* Use benchmarking and metrics extensively to understand opportunities for improvement.
* Employ self-auditing programs to ensure that processes are being used and continuously improved.
• Cultivate: Organizations with better implementation practices perform better on capital projects
* Develop a comprehensive project management plan that incorporates best practices and expert knowledge to ensure successful execution of capital projects.
* Implement proven processes and procedures for managing capital projects, including regular monitoring and control mechanisms to identify potential issues early.
* Foster open communication channels with stakeholders, including contractors, suppliers, and team members, to facilitate collaboration and address concerns promptly.
* Leverage expertise from industry organizations such as the CII to access valuable resources, best practices, and research findings that can improve project outcomes.
* Regularly monitor project performance using key metrics and indicators to identify areas for improvement and make data-driven decisions accordingly.
• Leverage: Organizations should use the CII Implementation model to order their implementation efforts and the CII Knowledge Structure model to identify best practices that can provide benefits
* Utilize the CII Implementation model as a roadmap to guide the organization's implementation of best practices, thereby ensuring a structured approach to improvement.
* Leverage the CII Knowledge Structure model to identify relevant best practices and catalog them for future reference, thereby enabling informed decision-making and process improvements.
* Prioritize key areas for improvement by analyzing the relationships between organizational implementation and company success, focusing on initiatives with high potential impact.
* Implement proven processes and procedures from identified best practices into the organization's workflow, thereby ensuring consistent application of best practices across projects.
* Regularly monitor progress using key metrics and indicators to measure the effectiveness of implemented changes and to make data-driven decisions for future improvements.
• Tool: Implementation Model + Knowledge Structure Guide (IR166-2)
* Establish a systematic approach for implementing CII best practices using the CII Implementation model.
* Address barriers to implementation, such as low familiarity and commitment, through structured corporate support.
* Organize CII’s research and tools within the CII Knowledge Structure model, which consists of 13 Knowledge Areas and 47 Focus Areas.
* Promote key best practices, such as pre-project planning and zero accidents techniques, to enhance project performance.
* Regularly update the Knowledge Structure model to support the efficient adoption of best practices and improve industry-wide knowledge sharing.
• Tool: CII Best Practices Guide: Improving Project Performance, Version 5.0 (IR166-3)
* Promote project success: Emphasize early planning, clear scope definition, and risk management to enhance project success, cost-effectiveness, and schedule predictability.
* Implement CII Best Practices: Utilize CII Best Practices, such as advanced work packaging and front-end planning, to improve efficiency and safety.
* Benchmark and measure performance: Regularly benchmark project metrics to assess performance, compare against industry standards, and drive continuous improvement.
* Address change and disputes: Establish a structured process for managing change and resolving disputes early to avoid costly delays and escalations.
* Leverage constructability and safety practices: Integrate constructability and zero-accident techniques to reduce rework, enhance quality, and ensure a safe project environment.
• Tool: CII Best Practices Handbook (SP166-4)
* Define best practices: Establish processes to improve project cost, schedule, and safety by using proven best practices in areas such as planning, risk assessment, and quality management.
* Implement advanced work packaging: Enhance project efficiency and predictability by structuring planning from the early stages and aligning engineering and construction efforts.
* Ensure effective front-end planning: Improve project success through comprehensive early-phase planning, addressing risks, and aligning with strategic goals.
* Leverage change management: Proactively manage project changes to minimize disruptions, maintain schedule, and control costs, especially by engaging in the early project phases.
* Adopt constructability and partnering efforts: Optimize design and construction integration and strengthen project relationships to improve overall project outcomes.
RS166-1 takeaway summary
(3). From Vision to Action: Igniting the Passion and Imagination of an Organization to Introduce Positive Change (IS31-1)
• Prepare to cross the bridge from vision to action. Focus on management buy-in and development of the appropriate vision for implementation
* Identify key stakeholders who will be impacted by the Construction Industry Institute (CII) research implementation.
* Engage with these stakeholders to gain their understanding and support for the project.
* Develop a clear and compelling vision statement that outlines the benefits and goals of the CII research.
* Communicate this vision to all relevant parties, including employees, clients, and partners.
* Obtain commitment from senior management to provide necessary resources and sponsorship for the implementation.
• Get on the bridge. Establish metrics and needs statements to ensure the organization’s understanding of reasons that the implementation is needed and its evaluation process
* Define key performance indicators (KPIs) that will measure the success of the CII research implementation.
* Identify specific business objectives that the implementation aims to achieve, such as cost savings or improved project delivery times.
* Develop a clear needs statement that outlines the reasons the organization needs to implement the CII research and its potential benefits.
* Establish metrics for evaluating the effectiveness of the implementation, including measures of process improvement and return on investment.
* Communicate these KPIs, objectives, and metrics to all relevant stakeholders to ensure that everyone understands the measures and the reasons for them.
• Start the journey. Ensure that a team is in place to guide the implementation and to gather resources to support the implementation
* Assemble a cross-functional team to guide the implementation and gather resources.
* Identify key stakeholders who will be impacted by the change and involve them in the planning process.
* Develop a project charter that outlines the scope, goals, and objectives of the implementation effort.
* Determine the necessary skills and expertise required for successful implementation and recruit and train personnel accordingly.
* Establish clear roles and responsibilities among team members to ensure effective communication and collaboration.
• Check the supports. Determine whether the appropriate cultural, managerial, and technical support are in place for successful implementation
* Assess whether the organizational culture is conducive to change and willing to adopt new practices.
* Evaluate the availability of necessary managerial resources, such as personnel with relevant expertise.
* Verify that technical infrastructure and equipment meet the requirements for successful implementation.
* Determine if any existing policies or procedures need to be updated or modified to accommodate the research implementation.
* Identify potential barriers to adoption and develop strategies to overcome them.
• Identify the main crossing. Ensure that the organization has a defined plan and roadmap for completing the implementation effort
* Develop a comprehensive project plan that outlines key milestones, timelines, and resource allocation.
* Establish clear roles and responsibilities among team members to ensure effective communication and collaboration.
* Identify potential risks and develop mitigation strategies to minimize the impact of those risks on the implementation process.
* Create a detailed budget and financial plan for the implementation effort, including contingency planning.
* Define measurable performance indicators and key performance metrics to track progress and evaluate success.
• Address the barriers. Determine whether the implementation will encounter common barriers and if the team is prepared to address these barriers
* Identify potential barriers that may hinder successful implementation, such as resistance to change or lack of resources.
* Develop a contingency plan to mitigate each identified barrier, including strategies for overcoming obstacles and addressing concerns.
* Establish open communication channels with stakeholders to ensure the timely identification and resolution of issues.
* Foster a culture of collaboration and continuous learning within the team to adapt to changing circumstances and address emerging barriers.
* Conduct regular risk assessments to monitor progress and adjust mitigation plans as needed.
• Exit to action. Ensure that the organization can communicate its accomplishments, ways it will build on new actions, and reasons that the new practice is important to the organization
* Develop a clear and concise communication plan that outlines accomplishments and any implemented new practices.
* Identify key stakeholders who need to be informed about the new practices.
* Prepare a brief report that highlights the benefits of the new practice and its importance to the organization.
* Schedule regular updates with senior management to ensure that progress is tracked and communicated effectively.
* Create a visual representation (e.g., an infographic) that illustrates ways that the new practice will improve organizational performance.
• Tool: The Implementation Process Action Tool (IS31-2)
* Define ‘vision to action’: Establish a clear vision to initiate organizational change and bridge the gap between planning and effective implementation.
* Use IMPACT: Apply IMPACT to evaluate organizational readiness for implementation through a structured, phased approach.
* Assess progress: Use IMPACT’s seven phases to monitor readiness, identify potential weaknesses, and highlight improvement areas.
* Analyze and improve: Conduct weakness analysis and obtain recommendations that are tailored to strengthen the transition from vision to action.
* Promote collaboration: Share the IMPACT results organization-wide to foster discussion, integrate feedback, and set specific action items for improvement.
• Tool: The Vision to Action Hot List (IS31-3)
* This implementation resource provides a list of key items from the IS 31 research data that can guide innovation champions through the vision to action process. This short-form tool brings into focus the ideas gathered throughout this and previous research efforts, to ensure that any organization can successfully implement innovative processes and practices.
IS31-1 takeaway summary
9. LESSONS LEARNED (1)
(1). Effective Management Practices and Technologies for Lessons Learned Programs (RS230-1)
• Establish leadership, both top-level and tactical, for success of the lessons learned program
* Develop a clear vision for the lessons learned program and communicate it throughout the organization.
* Assign a dedicated coordinator or champion to oversee and manage the lessons learned program.
* Integrate lessons learned into mainstream business processes to ensure consistent application and value.
* Provide necessary resources, including training and time allocation, to support active participation in the program.
* Regularly assess and improve the program using metrics and feedback to maintain its effectiveness and relevance.
• Become a ‘teaching’ organization rather than one that only collects or learns from the past in an ad hoc or passive manner
* Establish formal training programs to actively educate employees on best practices and lessons learned.
* Integrate lessons learned into daily operations and decision-making processes.
* Encourage experienced employees to mentor and share knowledge with newer personnel.
* Implement regular reviews and discussions of lessons learned in project meetings.
* Promote a culture of continuous improvement by recognizing and rewarding knowledge sharing.
• Adopt an active implementation strategy for ensuring that lessons are used
* Conduct regular lessons learned reviews during project development meetings.
* Update internal work processes to incorporate past lessons.
* Develop situation-specific booklets and training based on acquired lessons.
* Address requests for information by pushing relevant lessons to the field.
* Establish mentoring by experienced personnel to reinforce the implementation of lessons learned.
• Recognize that, although technology is important in developing and using a lessons learned program, the importance of organizational culture should not be underestimated
* Encourage employees to actively participate in lessons learned programs.
* Develop a shared vision of the lessons learned program that includes all departments.
* Address cultural differences within the organization to ensure consistent program use.
* Recognize and reward employees who contribute valuable lessons.
* Facilitate open communication and collaboration across different teams and locations
• Prioritize the quality of lessons learned over the quantity of lessons in the database
* Establish criteria for validating the quality of the lessons before their inclusion in the database.
* Assign subject matter experts to review and validate submitted lessons.
* Regularly update and refine lessons to ensure relevance and accuracy.
* Focus on capturing detailed, actionable lessons that can drive improvement.
* Implement a feedback loop for users to report the effectiveness of implemented lessons
• Engage owners and contractors so that both can benefit from lessons learned programs, focusing captured lessons in different areas based on the organization's business needs
* Focus lessons on front-end planning, project control, and operational issues.
* Regularly share insights from both owner and contractor perspectives.
* Align lessons learned with specific business needs and goals.
* Utilize mutual lessons to foster collaboration between owners and contractors.
* Customize lessons to address distinct project phases and responsibilities.
• Tool: Implementation of Lessons Learned Programs (IR230-2)
* Establish a lessons learned program to document and share project experiences, aiming for continuous improvement and competitive advantage.
* Conduct a self-assessment using the Maturity Model Matrix and Self-Assessment Questionnaire to evaluate program effectiveness.
* Develop a Jump Start Guide to provide steps for creating or enhancing a lessons learned program, including leadership engagement and process mapping.
* Utilize a transactional workflow diagram to structure the collection, analysis, and implementation of lessons learned.
* Consider special factors, such as leadership roles, legal aspects, cultural differences, and resource allocation, to ensure program success and sustainability.
RS230-1 takeaway summary
10. MATERIALS MANAGEMENT (9)
(1). AWP “Digital Threads” to Enable Supply Chain Visibility on Capital Projects (FR-TC-03)
• Advanced work packaging (AWP) is a structured process that aligns engineering, procurement, and construction (EPC) activities into work packages and uses digital threads (DTs) to improve supply chain visibility (FR-TC-03, p. 15, Table 7, Figure 3)
* DT020 Project Schedule: Capture core information that is related to schedule management for a capital project.
* DT150 Procurement: Capture core information that is related to project procurement visibility.
* DT270 Site Materials: Capture core information that is related to site materials management for a capital project.
* DT170 Structural Detailing: Capture core information that is necessary to finalize the planning of the steel structures to be changed or constructed.
* DT180 Steel Fabrication: Capture core information that is necessary to track the steel fabrication of structural piece marks.
* DT190 Pipe Detailing: Capture core information that is related to pipe detailing work.
* DT200 Pipe Fabrication: Capture core information that is necessary to track the fabrication of pipe spools.
• The Materials Responsibility Matrix (MRM) is a structured tool that assigns accountability for procurement, tracking, and handling across a project’s supply chain. The MRM is used to:
* Increase alignment among stakeholders who are connected to the supply chain.
* Enhance the visibility of supply chain information through the implementation of digital threads.
* Improve data sharing among stakeholders across the supply chain.
* Clearly define project stakeholder responsibilities for materials.
• Leverage the Digital Threads List in TC-03 Appendix A (FR-TC-03, p. 23)
* Each section in Appendix A begins with a table that provides the fields for that digital thread.
* A second table provides remarks concerning the digital thread overview, associated work processes, and team roles.
* The remaining tables in the section provide the variable categories for each digital thread field and sample entries.
FR-TC-03 takeaway summary
(2). Costs and Benefits of Materials Management Systems (SD-17)
• Plan and execute materials management properly to optimize schedules and improve labor productivity for project management
* Analyze project schedules to identify opportunities for materials management optimization and labor productivity improvement.
* Develop a comprehensive plan to streamline material delivery, storage, and issuance processes to reduce waste and minimize idle time.
* Collaborate with contractors to establish clear goals and metrics for measuring labor cost savings, and monitor progress regularly.
* Implement process improvements, such as just-in-time delivery and optimized scheduling, to reduce waste and minimize idle time.
* Conduct regular reviews and analysis of schedules and labor costs to ensure continued optimization and to identify opportunities for further improvement.
• Understand the benefits of materials management
* Improved craft labor productivity.
* Reduced bulk materials surplus.
* Enhanced vendor performance.
* Streamlined project planning and communication.
* Optimized takeoff and engineering interface.
* Improved purchasing and expediting processes.
* Better field material control and warehousing.
* Cost savings through cash flow optimization.
* Reduction in management manpower requirements.
* Effective use of computer systems.
• Secure top management support to overcome potential resistance to the upfront costs of effective materials management, which are always lower than the hidden costs of poor handling and control
* Develop a compelling business case for implementing a materials management system to demonstrate cost savings and efficiency gains.
* Identify key stakeholders and build relationships with top management to understand their concerns, and address those concerns proactively.
* Establish clear metrics and benchmarks to measure the success of materials management initiatives, and communicate progress regularly.
• Train all levels of the project management team, including users and the materials management team itself, to ensure the successful implementation of the materials management system
* Provide comprehensive training sessions for all project management team members to ensure their understanding of the materials management processes and system.
* Offer hands-on experience with the new system through simulations or pilot projects to build confidence and competence.
* Develop a user’s manual and online resources to support ongoing learning and reference needs.
* Conduct regular workshops and refresher courses to maintain skills and address any questions or concerns that arise during implementation of the materials management system.
* Establish a help desk or technical support team to provide assistance with the new system, addressing issues promptly and efficiently.
* Foster a culture of continuous improvement by recognizing and rewarding employees who contribute to the successful implementation and ongoing optimization of the materials management system.
SD-17 takeaway summary
(3). Project Materials Management Primer (RS7-2)
• Obtain the best value for purchased materials
* Research and compare prices among multiple vendors to ensure competitive pricing.
* Evaluate product quality, durability, and performance in relation to price and specifications.
* Negotiate with suppliers to secure discounts or favorable terms based on volume purchases.
* Verify that all materials meet project requirements and specifications before making a purchase decision.
* Monitor material usage and adjust purchasing strategies as needed to optimize value for money.
• Provide efficient, low-cost transport, security, and storage of materials within construction sites
* Coordinate with vendors to arrange timely and cost-effective transportation methods.
* Identify secure locations on site for material storage and ensure that these locations meet project specifications.
* Implement a system for tracking and monitoring material inventory levels and movement.
* Negotiate with logistics providers to obtain discounts or favorable rates based on volume usage.
* Conduct regular inspections of stored materials to prevent damage, theft, or loss.
• Assure that quality materials are on hand when and where required
* Confirm with vendors that test dates, forms, and certifications will be established before actual inspections take place.
* Ensure that shop documentation is meaningful by verifying that the data reflect the actual fabrication and testing results.
* Coordinate transportation logistics for equipment movement to ensure the timely arrival at construction sites.
* Verify that all necessary materials have been procured and delivered to the site prior to inspections.
* Conduct regular inventory checks to guarantee that quality materials are on hand when required.
• Reduce surplus to the lowest level possible
* Ensure that procurement practices and inventory management systems are in place to minimize excess materials.
* Work with the contractor to establish clear guidelines for material usage and tracking.
* Regularly review and adjust min/max inventory limits to prevent overstocking.
* Identify opportunities to recycle or reuse excess materials whenever feasible.
* Hold regular meetings with the contractor to monitor progress, and make adjustments as needed.
• Tool: Project Materials Management Handbook (SP-4)
* Provides comprehensive guidance on materials management for construction projects. This handbook helps users optimize material planning, procurement, and logistics to minimize delays, reduce costs, and improve productivity.
* Establishes integrated materials management to enhance productivity and cost-effectiveness by reducing delays, improving quality, and minimizing surplus.
* Emphasizes planning as a critical factor and integrates various organizational functions for successful materials management across construction project phases.
* Details materials responsibilities by defining roles for owners, contractors, and vendors via responsibility matrices that help prevent confusion and duplication.
* Emphasizes the use of technologies, such as automated systems, barcoding, and standardized codes, to streamline materials tracking, control, and reporting.
* Recommends adapting materials strategies for unique project needs, including international, small-scale, and prefabricated construction considerations, to manage logistics and optimize resources.
• Tool: Procurement and Materials Management: A Guide to Effective Project Execution (IR7-3)
* Helps construction projects streamline material planning, procurement, and logistics to reduce costs, avoid delays, and enhance efficiency.
* Defines materials management as an integrated system for timely, cost-effective, quality materials supply.
* Highlights the significance of planning in materials management for reducing costs, ensuring availability, and preventing delays.
* Stresses corporate support for materials management through standardization, alliances, and training for optimal efficiency.
* Promotes emerging technologies, such as barcoding, electronic data interchange, and integrated computer systems, for tracking and control.
* Emphasizes metrics, including cycle times, availability, surplus reduction, and supplier performance improvements, for evaluating a materials management system.
RS7-2 takeaway summary
(4). Global Procurement and Materials Management (RS257-1)
• Conduct comprehensive market studies early to identify cost-effective sources of equipment and materials, considering logistics complexity
* Identify potential suppliers of equipment and materials through online research, industry associations, and trade shows.
* Analyze supplier profiles to determine their reputation, capacity, and pricing strategies.
* Request quotes from multiple suppliers to compare prices, delivery times, and logistics options.
* Evaluate shipping costs, insurance requirements, and customs regulations for each supplier's proposal.
* Verify the authenticity of suppliers' certifications, licenses, and compliance with industry standards.
• Integrate sustainability considerations into project planning to meet owners' requirements and develop contractors' capabilities in this area
* Develop a comprehensive sustainability plan that aligns with the owner’s requirements and industry best practices.
* Engage stakeholders to identify key environmental, social, and governance (ESG) issues that may affect the project.
* Integrate ESG metrics into project performance monitoring and reporting systems.
* Collaborate with contractors to develop their capabilities in sustainable construction methods and materials.
* Establish a sustainability management system that tracks progress and ensures compliance with regulatory requirements.
• Streamline IT system interfaces by carefully selecting and integrating the optimal IT system(s) during pre-project planning and ensure continuous improvement via training programs
* Collaborate with project stakeholders to identify key IT systems that are the most appropriate for project success.
* Ensure the best choice of IT systems during pre-project planning by evaluating vendors’ capabilities and compatibility.
* Ensure the seamless integration of the new IT system into existing infrastructure through thorough testing and training programs.
* Develop a comprehensive training program for construction personnel to use the integrated IT system effectively.
* Continuously monitor and evaluate the performance of the integrated IT system, making adjustments as needed to ensure optimal functionality.
• Proactively address quality issues in global sourcing by importing from qualified suppliers or developing a local supply base before a project begins
* Identify qualified suppliers via thorough research and evaluation before the project begins.
* Develop a local supply base by partnering with regional vendors to ensure the timely delivery of high-quality materials.
* Conduct regular audits of selected suppliers to verify their compliance with quality standards and regulations.
* Establish clear communication channels with suppliers to address any quality concerns or issues promptly.
* Implement a robust tracking system to monitor supplier performance, thereby ensuring accountability for quality deliverables.
• 1) Core function: Materials requirements planning
* Establish project-specific procedures to align materials acquisition strategies with project requirements.
* Gather specifications and define standard material requirements to streamline procurement negotiations.
* Develop a comprehensive materials and equipment list, prioritizing long-lead and mission-critical items.
* Determine preliminary material quantifications, sizing, and cost estimates to support procurement planning.
* Implement a tracking and monitoring plan to ensure seamless material flow and timely procurement.
• 2) Core function: Project acquisition strategy
* Define sourcing strategies by determining domestic or international procurement process and assessing modularization needs.
* Identify and evaluate potential suppliers based on the project’s requirements and quality standards and the suppliers’ past performance.
* Conduct supplier assessments, including qualification checks, audits, and compliance verification.
* Establish procurement responsibilities across project stakeholders and ensure clear roles for owners, contractors, and suppliers.
* Analyze and mitigate risks by developing contingency plans for critical materials and equipment procurement.
• 3) Core function: Purchasing and subcontracting
* Develop a procurement plan that outlines purchasing strategies, supplier selection criteria, and contract requirements.
* Prepare and issue inquiry packages to potential suppliers and subcontractors to ensure clarity regarding project specifications.
* Evaluate and shortlist suppliers and subcontractors based on technical, commercial, and compliance assessments.
* Negotiate and finalize contracts, ensuring alignment with project timelines, budget, and quality standards.
* Monitor supplier and subcontractor performance and enforce compliance with contractual obligations and project milestones.
• 4) Core function: Expediting
* Review purchase orders and establish expediting strategies to ensure timely material delivery.
* Communicate with suppliers to confirm production schedules and identify potential delays.
* Conduct regular progress checks, inspections, and site visits to verify supplier performance.
* Develop and implement recovery plans for delayed materials to mitigate project disruptions and schedule delays.
* Perform final inspections and issue expediting reports to document supplier compliance and delivery performance.
• 5) Core function: Supplier quality management
* Conduct supplier capability evaluations to ensure the supplier’s compliance with quality, capacity, and financial stability requirements.
* Define and communicate quality assurance requirements, including inspection plans and performance expectations.
* Implement supplier surveillance plans to monitor the supplier’s quality performance and adherence to project specifications.
* Perform inspections and quality audits before shipment to verify the supplier’s compliance and identify potential material defects.
* Address nonconformance by enforcing corrective actions and tracking supplier quality performance over time.
• 6) Core function: Transportation and logistics
* Develop a transportation and logistics plan that addresses cargo origin, shipping terms, and site delivery requirements.
* Procure logistics service providers, including freight forwarders, export packers, and customs clearance agents.
* Manage import/export compliance by identifying regulatory requirements and coordinating customs procedures.
* Monitor shipment progress and update schedules based on the supplier’s production status and transportation timelines.
* Inspect received materials for completeness and damage, ensuring proper handling and documentation.
• 7) Core function: Site materials management
* Establish materials control systems, storage facilities, and handling procedures to ensure efficient site operations.
* Receive and inspect materials upon arrival and verify content accuracy against purchase orders and contracts.
* Maintain real-time inventory tracking to monitor material availability and prevent shortages.
* Implement material preservation and maintenance measures to prevent damage and ensure usability.
* Manage surplus materials by identifying reuse opportunities, resale options, or proper disposal methods.
• 8) Core function: Planning for operations and maintenance turnover
* Define roles and responsibilities for the operations and maintenance teams during the commissioning and start-up phases.
* Identify and procure necessary spare parts to ensure long-term equipment reliability and maintenance readiness.
* Develop warehousing and inventory management plans for efficient storage and accessibility of critical materials
* Implement a spares delivery strategy, including vendor support agreements and transportation planning.
* Conduct final reconciliation and handover of materials, documenting surplus inventory and providing operational guidelines.
• 1] Support function: Corporate Strategy
* Establish company-wide policies and standards for materials management, procurement, and supplier relationships.
* Align corporate procurement strategies with project execution goals and global market conditions.
* Develop strategic sourcing agreements to optimize costs, quality, and supplier reliability.
* Integrate materials management planning into the overall corporate strategy for enhanced efficiency and risk mitigation.
* Promote continuous improvement by adopting emerging technologies and best practices in procurement and logistics operations.
• 2] Support function: Personnel and organization
* Define clear roles and responsibilities for materials management personnel within the project structure.
* Recruit and train qualified personnel to ensure expertise in procurement, logistics, and supplier management.
* Establish communication channels to enhance collaboration among the materials management, engineering, and construction teams.
* Implement continuous training programs to improve personnel competencies in materials management systems and technologies.
* Foster a proactive culture that emphasizes efficiency, accountability, and alignment with corporate materials management strategies.
• 3] Support function: IT systems
* Implement an integrated IT system to streamline materials management, procurement, and logistics operations.
* Ensure interoperability between materials management platforms and external systems for seamless data exchange.
* Develop user training programs to maximize IT system efficiency and adoption.
* Enhance real-time tracking and reporting capabilities for improved decision-making and project control.
* Continuously update and refine the IT system to incorporate emerging technologies and industry best practices.
• 4] Support function: Materials requirements planning
* Establish project-specific procedures to align materials acquisition with project needs and schedules.
* Identify, quantify, and prioritize materials and equipment based on project specifications and criticality.
* Develop procurement schedules to ensure the timely ordering and delivery of materials.
* Implement tracking systems to monitor material status, availability, and lead times.
* Coordinate with the engineering and procurement teams to adjust materials plans based on project changes.
• Tool: Global Procurement & Materials Management: An eGuide to Effective Project Execution (IR257-2)
* This tool is designed to enhance effective construction project execution. It helps manage procurement, logistics, supplier quality, and materials tracking for improved efficiency and cost savings.
* Suppliers must submit documentation in a prescribed format that matches the purchase order line items.
* Submitted documents must include descriptions, item numbers, and part numbers from the purchase orders.
* The supplier-submitted documents must align with the line item sequences on the purchase orders.
* Accurate records of received materials must be maintained to facilitate inventory management.
* Material quantities must be verified against purchase order totals for accuracy.
• Tool: Materials Management Planning Guide (IR257-3)
* This tool is a guide for developing a materials management plan for a construction project. It helps to ensure the efficient procurement, logistics, inventory, and site management to optimize costs, minimize delays, and improve project execution.
* This guide is intentionally general, but requires project-specific planning to address each project’s unique needs.
* Stakeholders must consider owner/contractor responsibilities, site location, existing facilities, and contracting methods in materials management planning.
* A tailored plan will reflect these factors and ensure effective materials management for the project.
* Successful implementation requires coordination among the stakeholders to achieve desired outcomes.
* This guide serves as a foundation for implementing a comprehensive materials management strategy that meets project requirements.
RS257-1 takeaway summary
(5). The True Impacts of Late Deliverables at the Construction Site (RS300-1)
• Understand the features of the Late Deliverable Risk Catalog (LDRC). The LDRC does the following:
* Categorizes late deliverables into ten distinct types for streamlined risk assessment.
* Identifies project risks and impacts across cost, schedule, safety, quality, and organizational capacity.
* Provides an interactive database tool for querying and filtering late deliverable risks.
* Recommends mitigation strategies and best practices for preventing late deliverables.
* Supports knowledge sharing through case studies and survey-based industry insights.
• Follow the recommendations for LDRC deployment. The areas for LDRC deployment are:
* Project risk assessment
* Dispute prevention and resolution
* Knowledge sharing and transfer
* Lessons learned
• Incorporate and implement the LDRC in the construction organization
* Integrate the LDRC into project risk assessment workflows to identify and mitigate late deliverable risks proactively.
* Train project teams on LDRC usage for better recognition, prevention, and management of late deliverables.
* Utilize the LDRC during the planning phase to anticipate potential delays and optimize resource allocation.
* Leverage LDRC insights for contract negotiations to ensure accountability for deliverable timelines.
* Review LDRC data post-project to refine risk management strategies and improve future performance.
• Understand the definitions of the LDRC’s ‘project pillars’. The LDRC does the following:
* Defines cost as the financial resources that are required to complete the project within budget.
* Measures the schedule by tracking project timelines, milestones, and deadlines for timely project completion.
* Ensures quality by maintaining standards, specifications, and performance expectations.
* Prioritizes safety to prevent accidents, protect workers, and comply with regulations.
* Enhances organizational capacity by optimizing teamwork, morale, alignment, and resource efficiency.
• Understand the definitions of the LDRC’s late deliverable categories. The LDRC does the following:
* Classifies engineering documents, approvals, and responses as critical information that is required for design, procurement, and construction decisions.
* Describes engineered equipment as custom-built machinery that is essential for project operations and long-lead procurement.
* Defines fabricated materials as premanufactured components that are required for assembly and construction activities.
* Recognizes external permits as regulatory approvals that are necessary for legal compliance and project continuation.
* Views human resources as skilled labor, supervisors, and specialists who are essential for project execution.
• Understand the definitions of negative impacts. Negative impacts on a project can do the following:
* Influence scope changes by altering the project requirements, work sequences, or deliverables that are due to late inputs.
* Disrupt productivity by causing inefficiencies, rework, or downtime from missing resources.
* Increase indirect/overhead costs through extended project durations, resource waste, and additional expenses.
* Delay critical path management by negatively impacting the key activities that are essential for timely project completion.
* Strain on-site team dynamics by increasing stress, misalignment, and communication breakdowns.
• Tool: Late Deliverable Risk Catalog, Version 2.0 (IR300-2)
• Volume 1: Late Deliverable Risk Catalog: A User Guide
* Highlights risks: Emphasizes the impact of late deliverables on project pillars such as cost, schedule, quality, safety, and organizational capacity.
* Introduces the LDRC: Presents the LDRC as a tool for identifying and managing late deliverable impacts across projects.
* Facilitates communication: Encourages use of the LDRC for better alignment between owners and contractors, thereby supporting effective dispute prevention and resolution.
* Enhances training: Suggests using the LDRC to teach less-experienced staff to recognize and mitigate late deliverable risks.
* Recommends proactive measures: Advises adopting preemptive planning, coordination, and contingency strategies to prevent and reduce late deliverable impacts.
• Volume 2: The True Impact of Late Deliverables: Case Study Summaries
* Highlights costly delays: Late deliverables, such as late permits, materials, and equipment, extend project timelines and budgets, thus leading to increased costs and schedule overruns.
* Stresses the negative impacts of late deliverables on workflow: Delayed resources lead to work resequencing, increased safety risks, and frequent crew relocations, which negatively affect productivity and morale.
* Emphasizes risk management: The case studies reveal a need for proactive risk assessments, especially for logistics, safety, and resource availability.
* Advocates for clear communication: Effective stakeholder communication and transparent contracting are crucial for managing unexpected changes and minimizing conflicts.
* Recommends strategic planning: Lessons learned emphasize comprehensive front-end planning to handle potential delays and ensure efficient project execution.
RS300-1 takeaway summary
(6). Mitigating Threats of Counterfeit Materials in the Capital Projects Industry (RS307-1)
• Reference resources and training materials, including:
* Compiles industry handbooks that are relevant to counterfeit materials and mitigation strategies.
* Develops structured training modules to identify and mitigate counterfeit materials.
* Curates case studies that highlight past counterfeit incidents and successful mitigation efforts.
* Creates an accessible knowledge repository for guidelines, reports, and risk assessment tools to target counterfeit materials.
* Regularly updates materials knowledge repository to reflect evolving threats and mitigation strategies.
• A qualitative risk rating approach to address counterfeit, fraudulent, and suspect items (CFSI). RT-307’s risk rating approach does the following:
* Defines key risk factors, such as probability, consequence, and mitigation prioritization, for counterfeit materials.
* Develops a structured rating scale to assess CFSI risks based on expert judgment and project drivers.
* Includes a risk heat map to visualize consequence-probability relationships for prioritizing CFSI mitigation efforts.
* Standardizes assessment criteria across projects to ensure consistency in evaluating CFSI risks.
* Integrates ongoing feedback to refine and improve CFSI risk rating accuracy over time.
• A catalog of risk mitigation strategies. RT-307 provides a catalog that does the following:
* Identifies and documents 19 key risk mitigation strategies that are tailored to CFSI threats in capital projects.
* Describes implementation guidelines for each strategy, including scope, objectives, and challenges.
* Classifies strategies based on effectiveness, applicability, and industry relevance.
* Provides a decision framework to guide organizations in selecting appropriate strategies based on risk level.
* Updates and refines the catalog periodically based on industry trends and case study insights.
• Standardized format/tool for an internal, company-level database. RT-307 does the following:
* Provides a structured database to log CFSI incidents, including product details, detection methods, and mitigation actions.
* Standardizes data entry fields to ensure consistency in reporting and analysis across projects.
* Incorporates risk assessment metrics to quantify and prioritize CFSI threats.
* Enables data sharing protocols while maintaining confidentiality and legal compliance.
* Regularly updates and audits the database to enhance accuracy and usability.
• Tool: Counterfeit Materials Database (IR307-2)
* Identifies CFSI threats: Highlights the threat of CFSI in capital projects, emphasizing increased safety, cost, and schedule risks.
* Develops a risk mitigation framework: Proposes a structured framework for CFSI risk identification, assessment, mitigation, and communication that is tailored to construction projects.
* Encourages industry collaboration: Suggests a phased, industry-wide initiative for data sharing of CFSI incidents, with the Construction Industry Institute as the central coordinator.
* Implements mitigation strategies: Presents a catalog of 19 specific CFSI mitigation strategies that cover detection, reporting, and awareness improvement.
* Promotes data exchange and training: Advocates for data exchange and enhanced CFSI training to address the dynamic and pervasive nature of counterfeit risks in supply chains.
RS307-1 takeaway summary
(7). Achieving Zero Rework through Effective Supplier Quality Practices (RR308-11)
• Use the supplier quality process map (RR308-11, p. 124)
* 4.2.1 Planning and Selection.
* 4.2.2 Execution.
* 4.2.3 Stages to Measure the Production Process Quality.
* 4.2.4 Accept Package or Corrective Action Needed.
* 4.2.5 Post Execution Reporting.
• Best practices are extremely effective in the supplier quality arena (RR308-11, p. 235)
* Develop supplier partnerships and long-term agreements with suppliers.
* Develop supplier quality management systems.
* Provide regular performance feedback to suppliers.
* Involve fewer, higher quality, and more dependable suppliers.
* Include supplier quality surveillance.
* Create a common product life cycle management platform among the involved parties, owners, contractors, and suppliers to enable the secure sharing of relative project information.
* Evaluate cultural barriers for global suppliers.
• Highly effective contractors already employ certain practices to achieve zero rework in their projects (RR308-11, p. 235)
* Use nonconformance reports (NCRs) as learning opportunities.
* Ensure that top management is aware of and is involved with the supplier quality process.
* Engage in supplier partnerships.
* Invest in appropriate training for inspectors.
* Drive supplier development and control from other industries, with a shift from quality control (inspection) to development and improvement (prevention).
* Bundle products to send to suppliers.
* Carry out discussions with suppliers about plans for increasing capacity.
* Share forecasts with suppliers for better planning.
* Adapt/justify the supplier quality process in each country; that is, they adjust the process to fit specific geographic locations.
* Manage data in consistent quality management system and central repositories of information.
* Track and report data, including documenting NCRs and taking corrective actions.
• Utilize supplier quality management practices in a consistent manner
* Implement a standardized process for evaluating and selecting suppliers based on their quality performance.
* Develop and maintain a comprehensive list of approved suppliers using documented quality standards.
* Conduct regular audits to ensure compliance with established quality procedures and protocols.
* Establish clear communication channels with suppliers to address any quality concerns or issues promptly.
* Monitor and track supplier performance metrics, such as defect rates and delivery times, to identify areas for improvement.
• Utilize the decision support tool presented in IR 308-2, Chapter 3 to project the cost of defective materials and to make optimal decisions regarding supplier selection
* Utilize the decision support tool to analyze potential costs associated with poor quality materials or equipment.
* Project the financial impact of selecting a low-cost but potentially lower-quality supplier versus a higher-priced option with better quality.
* Evaluate the cost-benefit analysis provided by the tool to make informed decisions regarding which suppliers to select based on their quality performance.
* Use the tool's recommendations to optimize supplier selection, considering factors such as total life-cycle costs, risk assessments, and potential long-term consequences.
* Regularly review and update the decision support tool with new data and insights to ensure ongoing optimization of the supplier selection process.
• Tool: Achieving Zero Rework through Effective Supplier Quality Practices (IR308-2)
* Define high-risk suppliers to focus quality improvement efforts on critical components.
* Establish clear communication protocols with suppliers to ensure consistent expectations and gain feedback.
* Conduct regular supplier audits and assessments to evaluate performance and identify areas for improvement.
* Develop corrective action processes for nonconforming products or services to ensure the timely resolution of issues.
* Collaborate with suppliers on continuous improvement initiatives to drive zero rework and optimize quality.
RR308-11 takeaway summary
(8). Improved Integration of the Supply Chain (FR-344)
• Recommendations to improve visibility: Self-assess supply chain visibility (FR-344, Appendix E)
* Review existing tools and documentation to identify current levels of supply chain visibility.
* Define desired visibility based on specific business requirements and industry standards.
* Analyze case studies and examples of successful supply chain visibility implementations.
* Identify gaps in current supply chain visibility and prioritize areas for improvement.
* Develop a plan to address identified gaps and improve overall supply chain transparency.
• Recommendations to improve visibility: Close the gaps in supply chain visibility (FR-344, Appendices A and B)
* Implement new tools and technologies to improve supply chain visibility.
* Develop standardized processes and procedures for data sharing and collaboration.
* Establish clear communication channels with stakeholders to ensure timely issue resolution.
* Conduct regular audits and assessments to identify and address potential risks.
* Foster a culture of transparency and accountability throughout the organization.
• Recommendations to improve visibility: Align with other efforts, such as advanced work packaging and federal enterprise procurement
* Collaborate with stakeholders to identify and leverage existing initiatives.
* Review industry best practices and benchmarks to inform supply chain visibility improvements.
* Engage with relevant organizations and associations to stay informed about emerging trends.
* Develop a plan to integrate supply chain visibility into the overall business strategy.
* Establish metrics and key performance indicators to measure progress.
• Four-step decision process: Step 1 Estimate direct holding costs
* Review historical data to estimate direct labor and staffing costs that are associated with inventory storage.
* Calculate the provision of laydown space and related expenses as a percentage of the total project costs.
* Consider industry benchmarks and best practices when estimating direct holding costs.
* Develop a range for the estimated direct holding costs, taking into account variability in project requirements.
* Refine the estimates based on actual project data and lessons learned from previous projects.
• Four-step decision process: Step 2 Establish the applicable cost of capital for the project
* Determine the type of financing used to fund the project (e.g., loans, equity).
* Research and identify the borrowing costs associated with each funding source.
* Calculate the corporate rate or sponsor's weighted average cost of capital.
* Consider industry benchmarks and best practices when establishing the applicable cost of capital.
* Verify the accuracy of the established cost of capital through consultation with financial experts.
• Four-step decision process: Step 3 Explore alternatives for holding inventory
* Identify potential locations for laydown yards and assess their feasibility.
* Research options for supplier kitting to reduce storage needs.
* Evaluate the costs associated with each alternative (e.g., land acquisition, infrastructure development).
* Consider industry benchmarks and best practices when selecting an inventory holding strategy.
* Develop a plan to implement the chosen alternative(s) and monitor its effectiveness.
• Four-step decision process: Step 4 Decide on planned inventory based on costs and risks
* Determine the optimal level of inventory to minimize costs and maximize efficiency.
* Assess the risk associated with holding too little or too much inventory (e.g., stockouts, overstocking).
* Evaluate the impact of changing market conditions on inventory levels and adjust plans accordingly.
* Consider industry benchmarks and best practices when determining planned inventory levels.
* Develop a plan to implement and monitor the chosen level of inventory.
FR-344 takeaway summary
(9). Modernizing the Supply Chain and Increasing the Value of AWP (FR-363)
• Improving the quality of orders to suppliers could be a major industry opportunity and low-hanging fruit
* Clarify the scope and requirements: Standardize order details, specifications, and drawings to prevent misinterpretations.
* Prioritize deliveries: Establish required-at-site dates and priorities to minimize disruptions.
* Improve communication: Establish a single contact, streamline Requests for Information, and use digital tracking.
* Standardize data exchange: Implement structured procurement data formats and digital integration.
* Engage suppliers early: Involve suppliers during the early project phases to optimize procurement and explore alternatives.
• Involving suppliers early in the project better leverages their capabilities and ensures timely delivery
* Engage suppliers early: Include suppliers in front-end engineering design (FEED) to optimize procurement and design decisions.
* Define supplier roles: Clarify expectations, deliverables, and collaboration points during the project planning phase.
* Leverage supplier expertise: Consult suppliers about material alternatives, fabrication methods, and logistics solutions.
* Improve information flow: Proactively share project schedules, priorities, and design updates with suppliers.
* Establish early contracts: Use framework agreements to secure supplier commitment and ensure production readiness.
• Improving information systems assures the smooth exchange of information across the supply chain and supports better and more timely decision-making
* Integrate digital platforms: Use centralized supply chain systems for real-time data sharing and tracking.
* Standardize data formats: Implement consistent procurement and logistics structures for seamless data exchange.
* Enhance visibility: Provide suppliers with clear, real-time project schedules and priority updates.
* Automate processes: Utilize radio frequency identification (RFID), barcoding, and artificial intelligence (AI) for material tracking and inventory management.
* Assign coordinators: Establish a Digital Supply Chain Coordinator to manage data flow and system interoperability.
• Recommendations for advanced work packaging (AWP) processes (FR-363, pp. 44-65)
* Define supply chain processes: Establish procurement work packages (PWPs) to align procurement with AWP execution.
* Enhance supplier integration: Involve suppliers early in AWP planning to improve coordination and material readiness.
* Optimize material tracking: Implement digital tools for the real-time visibility of materials across work packages.
* Improve communication workflow: Streamline data exchanges among the engineering, procurement, and construction teams.
* Assign digital coordinators: Establish a Digital Supply Chain Coordinator to manage AWP data integration and tracking.
• Desired capabilities of an ideal supply chain system (FR-363, pp. 70-78)
* Enables real-time tracking: Implements RFID, barcoding, and the Internet of Things for material visibility across the supply chain.
* Integrates data systems: Connects procurement, logistics, and project management platforms for seamless information flow.
* Standardizes data formats: Uses consistent data structures to ensure compatibility across stakeholders.
* Automates procurement workflow: Leverages AI and analytics for demand forecasting and order optimization.
* Enhances collaboration: Provides shared digital platforms for suppliers, contractors, and owners to improve coordination.
• Role of the Digital Supply Chain Coordinator (FR-363, pp. 78-79)
* Manages data integration: Ensures seamless information exchange among the procurement, logistics, and construction systems.
* Monitors material tracking: Oversees RFID, barcoding, and digital tools for real-time supply chain visibility.
* Standardizes data formats: Implements consistent structures for procurement, inventory, and logistics data.
* Optimizes communication: Facilitates real-time updates among the suppliers, contractors, and project teams.
* Enhances decision-making: Uses analytics to improve procurement planning and mitigate supply chain risks.
FR-363 takeaway summary
11. PARTNERING (1)
(1). Model for Partnering Excellence (RS102-1)
• Phase 1: Owner's Internal Alignment
* Identify business drivers by assessing the company’s key objectives, such as cost reduction, fast market delivery, and improved project efficiency.
* Evaluate partnering feasibility by analyzing industry benchmarks, costs and benefits, and the company’s alignment with its strategic business goals.
* Conduct internal alignment by assessing the company’s culture, work processes, and readiness for partnering implementation.
* Appoint a champion to lead the partnering initiative and ensure leadership commitment throughout the process.
* Integrate partnering into strategic plans by fostering internal trust, educating employees about the partnering initiative, and establishing clear communication channels.
• Phase 2: Partner Selection
* Form a diverse and empowered selection team to evaluate potential partners and ensure alignment with the company’s business objectives.
* Develop selection criteria based on business drivers, core competencies, and compatibility with the partnering vision.
* Identify and screen potential partners by assessing their company’s culture, business practices, and ability to align objectives.
* Conduct thorough evaluations through interviews, reference checks, and open communication to ensure mutual understanding and trust.
* Finalize the partner selection process by aligning expectations, defining roles, and establishing a foundation for long-term collaboration.
• Phase 3: Partnering Relationship Alignment
* Develop trust by fostering open communication, collaboration, and mutual respect through workshops, joint meetings, and shared experiences.
* Define aligned objectives that support each party’s strategic goals and establish a clear partnering charter.
* Establish performance measures and incentives to track progress and encourage commitment to shared goals.
* Create a separate team that is empowered to focus exclusively on achieving the partnering objectives and enhancing team unity.
* Develop a conflict resolution process that promotes early issue resolution at the lowest level possible to maintain project momentum.
• Phase 4: Project Alignment
* Develop project objectives, incentives, and performance measures to align goals and track success.
* Ensure consistency of key personnel to maintain leadership, trust, and project continuity.
* Strengthen the project team by entrusting them with decision-making authority and cultivating a culture of accountability.
* Provide the necessary tools and resources to optimize efficiency, communication, and project execution.
* Implement a dispute resolution process to address conflicts quickly and effectively at the lowest level possible.
• Phase 5: Work Process Alignment
* Communicate project objectives clearly across all levels to ensure alignment and accountability.
* Analyze work processes to identify inefficiencies and implement improvements for better productivity.
* Effectively allocate resources to optimize scheduling, material availability, and workforce efficiency.
* Implement innovative ideas and processes to enhance performance, reduce costs, and streamline operations.
* Empower employees at all levels to take ownership of decisions and improve overall project execution.
• Six Key Factors for Implementing and Managing Successful Partnering Relationships
* Establish trust.
* Earn the support of top management.
* Establish win-win objectives.
* Address internal barriers.
* Appoint a champion to direct the process.
* Develop measures that are linked to objectives.
• Tool: Partnering ToolKit (IR102-2)
* This tool allows users to follow and check details regarding the five phases of the partnering process model: Owner's Internal Alignment, Partner Selection, Partnering Relationship Alignment, Project Alignment, and Work Process Alignment, and associated templates.
RS102-1 takeaway summary
12. PLANNING FOR MODULARIZATION (2)
(1). Industrial Modularization: How to Optimize; How to Maximize (RS283-1)
• Apply a modularization business case process at the earliest opportunity in the project
* Adopt the modularization business case process presented in IR283-2 as standard procedure.
• Identify planning and execution differences between modular and stick-built projects
* Review and address planning and execution differences between modular and stick-built projects according to project phase-oriented planning topics, including Selection, Basic Design, and Engineering, Procurement, and Construction (EPC). Refer to IR 283-2. Incorporate all relevant differences into the modular project execution plan.
* Review the execution plan to ensure that the Selection, EPC, and other relevant phases are taken into account for a modular project.
* Factor in early estimates of module envelope sizes and weights as inputs for fabrication and transportation planning.
* Address differences between modular and stick-built projects in four critical areas: planning and cost estimating, scoping, basic design standards, and detailed design deliverables.
* Apply these execution plan differences to ensure comprehensive modular project preparation.
• Identify critical success factors (CSFs) and incorporate enablers into the planning and execution stages
* Review the 21 critical success factors found in IR 283-2, which also includes information regarding enablers, optimal timing for implementation, and different coordinators’ responsibilities.
* Special attention should be given to CSFs that are difficult to achieve, including the owner’s planning resources and processes, a timely design freeze, early completion, cost savings, contractor leadership, investment in studies into modularization opportunities, vendor involvement, owner delay avoidance, data for optimization, and transport delay avoidance.
• Develop a strategy and follow eight steps that effectively integrate design standardization with modularization
* 1. Assess market needs, establish objectives, and create an implementation plan for design standardization and modularization integration.
* 2. Create standardized designs for targeted plant types and repeat this step as needed to achieve desired outcomes.
* 3. Create the modular standard design(s).
* 4. Repeat Steps 2 and 3, as needed.
* 5. Firm up agreements with vendors/packagers and involve them in refinements of the modular standard design(s).
* 6. Implement the execution of a modular standard plant for each client.
* 7. Assess and benchmark key performance indicators to assess the effectiveness of the modular standard plant effort.
* 8. Learn from modular standard plant projects and update/modify the standard design(s) only after thorough analysis and with confident justification.
• Review the ten enablers that will help to buoy or elevate levels of modularization across the industry
* Background (RS283-1, p. 36): A modularization business case, well-prepared execution plans, attention to CSFs, and use of a standardization strategy should all facilitate a more effective modularization process. However, to truly maximize modularization, leaders must directly address a variety of industry-wide barriers that can have (and have had) the effect of creating a ceiling that restricts the levels that modularization can achieve. Higher levels of modularization will be fully achievable in the future only if industry and project conditions and actions are more compatible with, or supportive of, modular approaches. The ten enablers for modularization are as follows:
* 1. Expand comfort zones: Encourage owners, designers, and contractors to broaden their familiarity with modularization, adjust selection criteria for service providers, and adopt new risk management approaches.
* 2. Redefine project needs: Owners/operators should adopt new paradigms regarding their needs and ways to accomplish or deliver projects. They need sufficient in-house work practices, resources, and expertise to freeze the process design, conduct necessary studies in a timely manner, and effectively exploit modularization opportunities (RS283-1, p. 47).
* 3. Prioritize early collaboration: Early and repetitive collaboration and coordination among project disciplines are keys to success. Implement proactive, multidisciplinary collaborations that involve planning, engineering, fabrication, construction, commissioning, operations, and project control to achieve optimal planning and design solutions.
* 4. Promote modular design education: Engineering schools should teach the modular design approach alongside traditional methods, and seek to make the integrated modular approach routine in the design of capital projects.
* 5. Leverage data for optimization: Owners and contractors must capture and exploit data to support modularization optimization studies that will address all aspects of modularization costs, schedule savings, and other benefits.
* 6. Increase module density and completeness: Design modules that are denser (in terms of fabrication work hours per cubic foot) and more complete (in terms of number of systems and functional components incorporated) while preserving safety, operational, and maintenance requirements, and consider related asset loss prevention tactics.
* 7. Modify equipment for modularization: Enhance equipment design with modularization-friendly configurations through collaborations among stakeholders, including manufacturers, owners, process engineers, designers, contractors, and economic analysts.
* 8. Standardize modular components: The industry should expand the inclusion of off-the-shelf modular components and assemblies with compatible interfaces. Package units should be compatible as submodules within a larger module. Component-to-component physical interface standard protocols should be expanded.
* 9. Improve transportation infrastructure: Upgrading ports, roads, and bridges to accommodate modular transport should be considered for capital investment projects. This effort will likely require collaboration among local parties and may involve some master planning by regional authorities.
* 10. Advance fabrication technology: The industry should develop advanced technologies that facilitate fabrication, transport, and installation/connection. For example, stronger, lighter materials, easier connections, and site connection methods that are fully compatible with fabrication tolerances are needed.
• Tool: Industrial Modularization: Five Solution Elements, Version 1.1 (IR283-2)
* The five solution elements in the Industrial Modularization tool are:
* 1. Define the business case: Evaluate the project’s feasibility for modularization, focusing on cost, schedule, and risk to optimize project outcomes.
* 2. Adapt the execution planning phase: Adjust project planning to reflect the unique requirements of modularization versus traditional stick-built approaches.
* 3. Identify CSFs: Determine the essential factors, such as schedule adherence, site logistics, and design adaptability, for successful modularization.
* 4. Standardize the design strategy: Apply standardization across project phases to enhance modularization efficiency and integration.
* 5. Enable industry maximization: Overcome industry-wide barriers through the use of the ten strategic enablers (see ‘(5) Review the ten enablers. . .’ above), thereby promoting widespread modularization adoption and benefits.
RS283-1 takeaway summary
(2). Business Case Analysis for Industrial Modularization (FR-396)
• Standardize modularization terminology and definitions
* Develop clear definitions for key modularization terms to ensure consistency of understanding among stakeholders. For reference, note that RT-396 developed Definitions of Key Modularization Terms (see FR-396, Appendix A) and a list of Module Types by Size (see FR-396, Table 1 on p. 14).
* Establish standard terminology across all project phases to facilitate effective communication.
* Identify industry-recognized standards or best practices for defining modularization concepts.
* Create a centralized repository for storing and updating modularization-related documentation.
* Regularly review and update the standardized terminology and definitions as needed.
• Identify modularization barriers and barrier breakers
* 1) Barrier: Early scope and design freeze are required. Barrier Breakers: (a) Understand that the business case for modularization includes the benefits of an upfront design cost with the overall benefits of modularization, i.e., a minimal upfront cost for maximum modular benefits. (b) Invest in thorough design during the early project phases prior to detailed engineering. (c) Freeze the design after the basic design phase to avoid changes during the engineering process. (d) Choose proven licensors and technology.
* 2) Barrier: Vendor data are not available to support modular project execution. Barrier Breakers: (a) Strategize alternative contracting methods to meet the early engineering requirements. (b) Identify critical vendor data that are necessary for a modular design. (c) Involve vendors in the early stages of the project and establish data availability expectations. (d) Understand the value of implementing a high-priority vendor data management program.
* 3) Barrier: No compelling business case for modularization is evident. Barrier Breakers: (a) Collaborate with experienced modularization subject matter experts to develop a project modularization business case that uses RT-396 tools. (b) Understand the benefits of modularization and ways that those benefits align with the project’s business drivers. (c) Understand ways to execute and design a modular project effectively, as the execution and design of a modular project differ from those of a traditional stick-built project.
* 4) Barrier: Modularization is not part of the project design. Barrier Breakers: (a) Consider modularization as the standard execution strategy for a project until and unless the business case states otherwise. (b) Highlight the value of the modularization business case to the management team. (c) Engage modularization experts and assess the modularization concept, strategy, and options in the early stages of project planning (i.e., during the Opportunity Framing or Assessment phase). (d) Provide project and company-wide training on modularization execution and design.
* 5) Barrier: The project delivery method prevents effective modularization planning/execution. Barrier Breakers: (a) Educate the management, including both the owner and the engineering, procurement, and construction (EPC) contractor, about the benefits of the modularization project delivery methods and contracting strategies, and help them understand the impacts of each of these factors on the project’s modular execution and design (and ultimately on the project’s cost and schedule). (b) After the decision is made to modularize based on the business case, and prior to deciding which contracting strategies to use, align the project delivery method with the contracting strategy that supports modular execution. (c) Evaluate and update the contract terms and conditions to ensure that they suit modular execution. (d) Revise internal and project contracting and supply chain work practices to align with modular execution objectives.
* 6) Barrier: The owner is reluctant to apply modularization. Barrier Breakers: (a) Develop a modularization business case process to gain approval from management and/or the project execution team. (b) Explain modular project execution and its benefits and methods to the owner’s management team and the project execution team. (c) Identify a key advocate and/or team within the owner organization that is experienced with modular execution and design and can effectively promote the benefits of modularization. (d) If no one within the company has modular execution and design experience, consider a third party to help with the modular project business case and further develop the company’s modular execution and design methods.
* 7) Barrier: Major financial or business drivers necessary for modularization are lacking. Barrier Breakers: (a) Develop a project modularization business case estimating method to identify the financial drivers that are needed for modularization using the RT-396 tools and historical modular project metrics. (b) Identify the estimating factors and metrics for quantifying the benefits of modular execution and design using the RT-396 tools and historical modular project metrics. (c) Highlight the benefits and drivers of modularization at the executive management level.
* 8) Barrier: Early fabricators and supplier involvement are lacking. Barrier Breakers: (a) Develop supplier involvement, module fabrication, and assembly contractor agreements for early engagement prior to the full purchase order or contract award. (b) Create long-term agreements with module fabrication and assembly contractors and suppliers to establish a stable and efficient partnership. (c) Establish a clear interface responsibility matrix for all project phases to ensure that all stakeholders, including the supplier and module fabrication and assembly contractors, are engaged throughout the project lifecycle. (d) Partner with an EPC contractor with a proven track record of experience in module design, fabrication, and assembly to ensure successful modular project execution.
* 9) Barrier: The project is customized, with no standardization or repetition. Barrier Breakers: (a) Explain to company management and project teams that custom, nonstandard projects do not necessarily preclude the use of modularization or limit the extent of modularization. (b) Explain to company management and project teams that modularization can complement the standardization of components, equipment, packages, and/or facilities. Refer to RT-UMM-01 (CII, 2020). (c) Establish a standardized execution and design strategy across the portfolio, program, and/or project.
* 10) Barrier: A guide or process to execute modular projects successfully is lacking. Barrier Breakers: (a) Develop industry standards and practices for modularization. (b) Collaborate with experts in modular execution, design, and construction who can provide their knowledge to the company and project teams. (c) Implement a modular execution and design training program for internal program and project teams. (d) Establish a modular execution and design team within the organization to support modular projects. (e) Study modular execution, design, and construction methods to ensure up-to-date knowledge.
• Review the recommended timing for activities and decisions that are related to modularization
* 1) Early decision and assumptions around key factors
* 2) Minimum information required to make informed/quality decisions
* 3) Site selection and associated infrastructure requirements
* 4) Modular concept development
* 5) Modular concept selection
* 6) Modular execution and design strategy development – execution decision starts to be “locked-in” or frozen
* 7) Basic design matures and time to implement modularization, without execution and design recycle, reduces as the end of the Basic Design phase (FEL3) approaches.
* 8) Implementation of opportunities identified by the EPC contractor
* 9) Basic design complete
• Tool 1: Modularization Business Case Analysis Tool for Opportunity Framing
* Leverage this tool during the early project phases to determine whether a project should be modularized.
* Review the expected results, details, and recommendations provided by this tool to inform business case analysis discussions with stakeholders.
• Tool 2: Modularization Business Case Analysis Tool for Assessment and Selection
* Leverage this tool to inform decision-making about the optimal extent of modularization for a project. This tool provides comprehensive analysis of costs and savings that are linked to varying percentages of modularization to help users identify the optimal level that will result in successful project completion.
* Review the expected results, details, and recommendations provided by this tool to inform business case analysis discussions with stakeholders during the Assessment phase.
• Tool 3: ESG Modularization Assessment Tool
* Leverage this tool for guidance in finding an appropriate modularization strategy that can mitigate issues and maximize benefits related to Environmental, Social, and Governance (ESG) principles.
* Use the assessment results to inform decision-making about the optimal extent of modularization that aligns with ESG principles.
FR-396 takeaway summary
13. PLANNING FOR STARTUP (3)
(1). Planning for Startup: Overview of Research (RS121-1)
• Ensure management’s commitment to start-up planning
* Define start-up objectives by taking a lead role in defining the project’s scope and goals.
* Ensure that plant operations and maintenance personnel are involved in the front-end engineering and detailed design phases to inform planning activities.
* Oversee the start-up planning process as the owner's project manager and take responsibility for its successful execution.
• Identify start-up objectives
* Define start-up objectives by identifying specific goals and the scope of work to be achieved during the start-up phase.
* Establish clear expectations with stakeholders regarding which components, including key performance indicators (KPIs) and metrics, constitute a successful start-up.
* Develop a comprehensive project charter that outlines the purpose, scope, and overall approach for achieving the defined start-up objectives.
* Ensure alignment between the start-up objectives and overall project goals by integrating them into the project management plan.
* Review and update the start-up objectives regularly to reflect any changes in project scope or schedule.
• Develop a start-up execution plan
* Develop a comprehensive start-up execution plan that integrates all start-up planning activities and serves as a guide for project stakeholders.
* Define schedule drivers and phase transitions to ensure effective work packaging and the recognition of unique project phases.
* Establish clear expectations with stakeholders regarding which components, including KPIs and metrics, constitute a successful start-up.
* Develop a comprehensive project charter that outlines the purpose, scope, and overall approach for achieving defined start-up objectives.
* Review and update the start-up execution plan regularly to reflect changes in project scope, schedule, or stakeholder expectations.
• Develop ‘quality gates’ or time-outs for analysis
* Recognize the impact of start-up planning on project progress and schedule regular quality gates to ensure timely project completion.
* Treat each activity in the Start-Up Planning Model as a quality gate (see RS121-1, Table 3) to maintain focus and momentum throughout the planning process.
* Establish clear expectations with stakeholders regarding which components, including KPIs and metrics, constitute a successful start-up.
* Schedule time-outs for analysis at specific points during the project lifecycle to ensure that the start-up planning stays on track and does not trail other project developments.
* Use quality gates as reminders for project and start-up managers to prioritize planning activities and avoid falling behind schedule.
• Tool: Planning for Start-Up (IR121-2)
* Highlight the importance of the start-up phase: Emphasizes start-up as a vital project phase by bridging construction completion and operational readiness for successful commercial outcomes.
* Outline a start-up planning model: Introduces a model that has 45 activities across eight project phases, focusing on a systematic approach to enhance predictability and efficiency.
* Detail key phases: Covers phases from requirements definition to initial operations, and includes activities such as risk assessment, resource allocation, and system turnover.
* Identify key quality gates: Includes critical checkpoints, or quality gates, to ensure thorough planning at each stage and verify readiness before proceeding to the next stage.
* Provide essential tools: Offers 26 tools to aid in planning, including the SuPER tool for tracking start-up readiness and an execution plan template to integrate the start-up steps.
RS121-1 takeaway summary
(2). Critical Success Factors for Project Commissioning and Startup (RS312-1)
• Ensure that the importance of commissioning and start-up (CSU) is widely recognized among all key project participants
* Communicate clearly to stakeholders about the critical role that CSU plays in achieving project objectives and ensuring successful facility operation.
* Collaborate with construction planners to develop a comprehensive plan for CSU, highlighting its significance and interdependence with other project activities.
* Educate team members about the benefits of effective CSU, which include improved safety, reduced risk, and enhanced overall performance.
* Incorporate CSU considerations into all aspects of project planning, from design to commissioning, to ensure CSU’s seamless integration and coordination.
* Regularly monitor progress using metrics that track CSU success to provide transparency and accountability for all stakeholders.
• Work diligently and collaboratively to achieve all 16 of the critical success factors (CSFs), listed under (7) below
* Establish joint meetings with the Construction and CSU managers when construction is about 50% complete to ensure a collaborative approach to the project.
* Conduct joint system walk-downs that involve both the Construction and CSU managers to facilitate their thorough understanding of the systems and to identify potential issues early on in the project.
* Establish short-term scheduling priorities at both the construction area and system/subsystem levels, with input from both the Construction and CSU managers’ teams.
* Involve CSU staff in construction planning when the system construction is approximately 60% to 80% complete for each single major system to mitigate punch list items, with particular focus on utility systems early in the process.
* Transition from construction progress tracking on an area basis to a systems completion basis. Involve CSU staff in this process to ensure the effective redirection of construction forces as needed.
• Be attentive to the six ‘laggard’ CSFs that appear to be particularly challenging in the construction industry
* Include system milestone acceptance criteria and deliverables, CSU value recognition, adequate funding for CSU, CSU systems engineering during front-end engineering design (FEED), systems focus in detailed design, and CSU leadership continuity.
* Identify the six laggard CSFs mentioned in RS312-1 and understand their relevance to the project.
* Analyze and assess ways that these CSFs may impact the project’s schedule, budget, and overall success.
* Prioritize the CSFs by determining which are the most critical to address for the specific project needs.
* Develop a plan to mitigate or overcome any challenges posed by the laggard CSFs identified in the analysis.
* Execute the developed plan to ensure that the laggard CSFs do not hinder the project's progress and success.
• Make use of the CSF achievement indicators identified in RS312-1
* Review RS312-1, Table 3 to become familiar with the top 30 CSF indicators and their descriptions.
* Assess and evaluate the project's current status against these indicators to identify areas for improvement or to maintain existing good practices.
* Prioritize the most critical CSF achievement indicators that align with the project's specific needs and goals and implement them.
* Create a plan to incorporate these indicators into the construction management process, ensuring effective communication and collaboration between the Construction and CSU managers’ teams.
* Regularly monitor and measure progress against these indicators throughout the project’s lifecycle, making adjustments as needed to ensure successful outcomes.
• Consider applying the five innovative commissioning technologies identified in RS312-1
* Smart piping and instrumentation diagrams (P&IDs): Enable accurate, accessible, and integrated P&IDs for effective CSU system planning and understanding.
* Building Information Modeling (BIM) design models/3D models: Provide accurate, digital models that improve safety, quality, and collaboration throughout the CSU project’s lifecycle.
* Asset data management/ wireless instrumentation: Enable easy asset management and commissioning through automated processes to reducing human interaction and speed up the start-up phase.
* Simulation-based virtual commissioning and operator training: Simulate life-like tests and training environments to improve engineering checkout and operator training and to reduce start-up costs and time.
* Completion management system: Allow remote field data collection and consolidated documentation to reduce errors and costs and improve project handover efficiency.
• Seek out lessons learned from past CSU failures and share these broadly among project and CSU managers
* Review IR312-2 to identify key takeaways from mini-case studies of past CSU failures.
* Conduct interviews with previous CSU teams to gather insights into failure and errors and determine ways to improve the process.
* Analyze industry reports and research papers on common causes of CSU delays or failures.
* Develop a lessons learned database to store and share best practices, pitfalls, and CSFs for future projects.
* Organize workshops or training sessions to disseminate the gathered knowledge among project managers, CSU staff, and other stakeholders.
• Become aware of and exploit the full suite of knowledge and implementation guidance provided in IR312-2, including the 16 CSFs
* Review IR312-2 to gain insights into commissioning and start-up best practices.
* Become familiar with the 16 CSFs (see the list below) identified by RT-312 for successful CSU planning.
* Study the case studies provided in IR312-2 to learn from past failures and successes in CSU projects.
* Explore the implementation guidance offered in IR312-2, which includes tools and checklists, to enhance the project's chance of success.
* Utilize the information and resources provided in IR312-2 to develop a comprehensive CSU plan for the project.
• CSF 1. CSU Value Recognition
* Establish the business case (including the CSU staffing plan) for effective CSU leadership.
* Recognize the value added from a successful CSU (e.g., the value of one day of successful operations).
* Avoid being ‘dollar foolish’. The Owner and all contractors must buy into, and be aligned with, the economics of effective planning and the investment required.
• CSF 2. Critical Interfaces on Brownfield Projects
* Identify all critical interfaces with existing plant facilities and operational approaches early in brownfield projects.
* Include examples such as isolation design, system controls, worker access, permitting, and interim operations.
• CSF 3. Adequate Funding for CSU
* Ensure that project funding for CSU is adequate, budgeted up-front, and preserved.
* Recognize that a common threat from insufficient funding is the lack of operators, which leads to delays in CSU progress.
• CSF 4. Alignment among Owner, Project Manager, Operations, CSU, Engineering, and Construction
* The project and CSU will benefit substantially by obtaining early alignment among the CSU, operations, project management, engineering, construction, and other key stakeholder representatives regarding CSU terminology, CSU success drivers, and CSU strategies. Lack of such alignment may pose a threat to CSU success.
* Sustained alignment between these entities can be achieved only with effective collaboration throughout the life of the project.
* Recognize that lack of alignment may be a risk that threatens CSU success.
* Achieve sustained alignment through effective collaboration throughout the project’s lifecycle.
• CSF 5. CSU Leadership Continuity
* Ensure continuity of CSU management leadership throughout the project.
• CSF 6. System Milestone Acceptance Criteria and Deliverables
* Establish specific detailed systems/subsystems acceptance criteria and associated deliverables for each major milestone: mechanical completion, turnover, precommissioning, commissioning, and handover.
* Ensure that all project parties understand these expectations.
• CSF 7. CSU Systems Engineering during FEED
* Conduct CSU systems engineering during FEED to define CSU systems within a facility.
* Focus on effective FEED efforts to reduce CSU challenges, as the facility design significantly impacts fabrication, testing, integration, and start-up.
* Use preliminary P&IDs as key documents for this effort.
• CSF 8. Recognition of CSU Sequence Drivers
* Coordinate the planned sequence of commissioning with construction planners.
* Consider factors such as construction sequence, plant operations philosophy, ramp-up objectives, plant controls automation, HAZOP awareness, modularization scope, clean build procedures, flushing sequence, leak/hydro testing, preservation steps, system tagging, and loop check sequence.
• CSF 9. Detailed CSU Execution Plan
* Ensure CSU success through timely and thorough execution planning that integrates project and CSU planning.
* Address the appropriate skill mix that is required in both CSU craft and CSU management within the execution plans.
* Involve plant operations as an effective contributor to the planning effort, and tackle common challenges such as Operations staff availability, continuity, authority, experience breadth, and timeliness of input.
• CSF 10. Systems: Focus in Detailed Design
* Adopt a systems-focused approach during the design phase that involves CSU and Operations to raise awareness of system handover, testing, and start-up procedures.
* Increase design attention to key issues such as high/low point drains, removable spools for critical inline equipment, critical isolation points, lockout/tagout requirements/supports, and access for operations and maintenance.
• CSF 11. CSU Check Sheets, Procedures, and Tools
* Ensure that the component and system function checkouts include adequate check sheet criteria, detailed system commissioning procedures, and certifications.
* Enhance implementation through the application of innovative CSU technologies.
• CSF 12. CSU Team Capability
* Ensure that the CSU team thoroughly understands the operations performance metrics-oriented requirements as well as the CSU activities and deliverables needed to achieve those results.
• CSF 13. Integrated Construction/CSU Schedule
* Develop a fully integrated construction, precommissioning, and commissioning schedule to achieve CSU objectives.
* Integrate all checks, tests, and approval milestones for each component and system into the schedule, and ensure the development of support documentation.
* Avoid CSU acceleration effects that may result from delayed construction.
• CSF 14. Accurate As-Built Information
* Ensure accurate as-built drawings and an asset database to support effective planning, implementation, and closeout of CSU activities.
• CSF 15. Transition to Systems-Based Management
* Plan to transition from construction progress tracking on an area basis to a systems completion basis so that construction forces may be most effectively redirected as needed.
* Involve CSU staff in construction planning when system construction is approximately 60% to 80% complete for each single major system in order to help mitigate construction punch list items, with particular focus on utility systems early in the process.
• CSF 16. Collaborative Approach to Construction to CSU Turnover
* Encourage CSU managers to work collaboratively with construction managers in managing construction completion and systems turnover.
* Implement proactive communications to minimize construction v. CSU conflicts.
• Tool: Achieving Success in the Commissioning and Start-Up of Capital Projects (IR312-2)
• Volume 1: Achieving Success in the Commissioning and Start-Up of Capital Projects: Implementing Critical Success Factors
* Define and implement CSFs: Establish the 16 essential CSFs for effective capital project commissioning and start-up, as validated through industry feedback and project data.
* Align stakeholder objectives early: Ensure alignment among project management, engineering, construction, and operations teams to improve collaboration and prevent conflicts.
* Develop a comprehensive CSU execution plan: Create detailed plans, including milestone acceptance criteria and integrated schedules, to streamline the CSU process.
* Address barriers to CSF achievement: Identify and mitigate common challenges, such as inadequate funding, misalignment, and lack of CSU-specific skills, to improve project outcomes.
* Utilize innovative CSU technologies and checklists: Apply new technologies and a standardized CSF checklist to enhance CSU performance, quality, and safety.
• Volume 2: Achieving Success in the Commissioning and Start-Up of Capital Projects: Mini-Case Studies
* Emphasize the importance of proper CSU planning to avoid costly delays and penalties.
* Highlight common CSU failures, which include inadequate communication, training, and oversight in high-risk settings.
* Identify best practices for addressing CSU-related risks through detailed execution plans, system check sheets, and clear role definitions.
* Stress the value of integrating subject matter experts and comprehensive operator training for optimal system functionality.
* Recommend implementing corrective actions, such as clear testing protocols, thorough as-built reviews, and enhanced inter-team communication, for CSU success.
RS312-1 takeaway summary
(3). Managing Transitions between Construction Completion, Pre-Commissioning, Commissioning, and Startup (SP333-1)
• Demonstrate that frequent, costly commissioning/start-up failures make a clear business case for action
* Quantify commissioning and start-up (CSU) costs by tracking cost overruns and documenting cases of costly delays.
* Pinpoint production losses by calculating the daily revenue impacts caused by start-up delays, emphasizing industry examples.
* Assess the impact of incomplete transitions by examining commissioning ‘hot spots’ that lead to delays and additional costs.
* Present documented industry case studies that illustrate failures and cost overruns in similar projects to validate the necessity of intervention.
* Advocate for preventive planning by outlining critical success factors (CSFs) that mitigate delays and improve project outcomes.
• Ensure smooth transitions across phases by clarifying activities and responsibilities, as organizational handoffs pose significant challenges to project and commissioning success
* Conduct early alignment meetings with construction, commissioning, and operations teams to agree on roles and transition plans.
* Define and document system boundaries and priorities for the phase transitions in the project’s initial planning stages.
* Assign clear responsibilities and accountability for each phase using a RACI (responsible, accountable, consulted, and informed) responsibility matrix to prevent role ambiguity.
* Establish and review transition plans periodically to ensure alignment and to address any changes in personnel or project requirements.
* Integrate contract provisions that promote timely system turnover and reinforce responsibility for critical tasks.
• Integrate the 17-step Construction CSU (CCSU) process by combining key insights from CII Research Teams 121, 312, and 333 on commissioning
* Identify CSU requirements early in the project planning stage to ensure readiness across all phases.
* Use the SP333-1 CCSU flowchart to map critical activities and establish timelines.
* Apply RS312-1’s CSU CSFs to guide team alignment and accountability.
* Establish a RACI responsibility matrix for each activity to clarify roles and ensure efficient handovers.
* Conduct periodic reviews of the CSU budget and schedule to address any emerging hot spots proactively.
• Organize a flowchart of 124 activities by project phase and four thematic swim-lanes
* Sequence activities by project phase, covering construction, precommissioning, commissioning, start-up, and close-out, to facilitate smooth phase transitions.
* Divide activities into four swim-lanes, i.e., planning/scheduling, materials/equipment, subsystems/systems, and data/documentation, to enhance task organization.
* Label activities as early, mid, or late within each phase to guide resource planning and execution timing.
* Highlight critical hot spot activities that commonly have challenges, and ensure that teams prioritize these areas.
* Use the flowchart as a central reference in planning meetings to align team roles and responsibilities across phases.
• Map the CCSU RACI responsibility matrix for 124 activities across 60 functions, assigning key responsibilities as a foundation for project-specific management discussions
* Identify critical CCSU activities and assign responsibility to the relevant project functions based on the RACI responsibility matrix.
* Collaborate with team leaders to clarify the RACI roles, i.e., accountable, responsible, consulted, and informed, for each activity.
* Review and adjust the initial RACI assignments to ensure alignment with project-specific objectives and requirements.
* Use the RACI responsibility matrix as a foundational tool in project kickoff meetings to establish clear responsibilities.
* Periodically audit the RACI responsibility matrix to address any role ambiguity and to adapt to project changes.
• Identify hot spots to highlight CCSU transition challenges, including unclear responsibilities, recurring issues, and unmet expectations in key activities
* Review key activities to spot recurring issues that delay phase transitions and increase project costs.
* Analyze past projects for unmet expectations and poorly defined responsibilities to enhance current planning.
* Identify ambiguities in role assignments and clarify them to prevent responsibility overlaps or gaps.
* Flag high-risk activities in the CCSU process that commonly result in delays, cost increases, or safety risks.
* Develop targeted mitigation strategies for each hot spot based on identified causal factors.
• Highlight 20 CCSU hot spots identified by 49 managers, with 75% in the construction phase, underscoring the need for increased project team oversight
* Focus project team oversight on the construction phase to address the 75% of hot spots that managers identified in that phase.
* Prioritize high-risk activities flagged as hot spots to minimize delays and control project costs.
* Clarify roles and responsibilities to address each hot spot and thus reduce ambiguity and enhance accountability.
* Implement regular audits of hot spots to ensure that issues are promptly addressed during the construction phase.
* Use insights from the 49 managers to refine strategies for preventing recurring issues across projects.
• Characterize each of the 20 hot spots across 10 fields, and include the impacts, causes, and mitigation strategies supported by trend analysis results
* Document qualitative impacts, such as schedule delays and cost increases, for each hot spot to identify recurring project challenges.
* Identify causal factors, such as role ambiguity and staffing issues, to address the underlying reasons for recurring hot spots.
* Outline prevention and mitigation strategies that are tailored to each hot spot to improve project continuity and reduce risks.
* Conduct trend analysis across hot spots to uncover patterns in the challenges and to develop standardized mitigation approaches.
* Use these characterizations as a basis for informed decision-making and team discussions about risk reduction and process improvement.
• Cross-link the hot spots with the 16 CSU CSFs presented in RS312-1, emphasizing the importance of alignment, execution planning, and check sheet factors
* Align project teams with commissioning goals by reviewing CSU execution plans and securing cross-functional sign-offs.
* Integrate detailed CSU execution plans to provide a structured approach for effectively managing hot spots.
* Define and implement comprehensive check sheets for critical activities to ensure thorough documentation and accountability.
* Conduct regular alignment meetings across the owner, project management, operations, CSU, engineering, and construction teams to reinforce team cohesion.
* Conduct trend analysis of past hot spots to proactively adjust execution strategies and improve project oversight.
SP333-1 takeaway summary
14. PROJECT RISK ASSESSMENT (4)
(1). Risk Assessment on International Projects: A Management Approach (RS181-1)
• Organize and formalize a risk management process and keep it as simple as possible
* Identify key stakeholders to participate in the risk assessment and management process.
* Develop a comprehensive risk register by collecting and documenting potential risks associated with the project.
* Establish clear roles and responsibilities among team members for identifying, analyzing, and mitigating risks.
* Determine the level of risk tolerance and develop strategies to manage or mitigate the identified risks.
* Schedule regular meetings to review and update the risk management process throughout the project lifecycle.
• Begin early to gain the most effectiveness
* Allocate resources and time in the project planning phase to identify, analyze, and develop risk mitigation approaches.
* Conduct a thorough risk assessment during the pre-project stage to establish a baseline of potential risks.
* Engage with stakeholders, including designers, contractors, and suppliers, early on in the project to gather information and insights about potential risks.
* Develop a comprehensive risk register that includes all identified risks and their corresponding mitigation strategies.
* Schedule regular meetings throughout the project lifecycle to review and update the risk management process.
• Maintain a broad perspective to obtain the diversified input required
* Conduct regular meetings with project stakeholders to gather diverse perspectives and ideas.
* Invite experts from various fields to share their insights and experiences.
* Encourage open communication among team members to foster collaboration and creativity.
* Establish a risk management committee to identify potential risks and develop mitigation strategies.
* Analyze industry trends, market conditions, and regulatory requirements to inform project decisions.
• Undertake adequate pre-project planning, analysis, and engineering
* Utilize tools such as the Project Definition Rating Index (PDRI) to conduct thorough project definition and rating.
* Conduct comprehensive risk assessments to identify potential risks, and develop mitigation strategies.
* Engage with stakeholders, including architects, engineers, and contractors, to gather input on project requirements and feasibility.
* Perform detailed analysis of the project scope, schedule, budget, and resources to ensure a solid foundation for the project.
* Develop a robust quality assurance plan to ensure compliance with industry standards and regulations.
• Partner with owner and contractor management
* Collaborate closely with project stakeholders to identify potential risks and develop mitigation strategies.
* Engage in open communication with contractors and designers to ensure that all parties understand the project’s requirements and expectations.
* Work together with the contractor to establish a schedule that takes into account local design service approval processes.
* Provide necessary support and resources to help the contractor manage cash flow issues that may result from VAT and tax implications.
* Foster a collaborative environment by recognizing the importance of experience in a jurisdiction for effective risk management.
• Recognize that certain projects are more prone to risk and that experience in a jurisdiction is important
* Identify high-risk projects based on factors such as project type, location, and complexity.
* Assess the importance of local knowledge and expertise when selecting contractors or designers for international projects.
* Consider hiring experienced professionals with knowledge of specific jurisdictions to mitigate risks associated with unfamiliar markets.
* Develop a risk assessment framework that takes into account the experience in a jurisdiction and the potential risks related to the project scope, schedule, and budget.
* Prioritize projects based on their level of complexity and potential risks, allocating more resources and attention to high-risk initiatives.
• Document risk management results to improve project efficiency and reduce costs through sharing information
* Identify and document all potential risks associated with international projects in a centralized risk register.
* Develop a standardized risk assessment framework to ensure the consistent evaluation of project-specific risks.
* Establish clear procedures for documenting and tracking mitigation strategies and their effectiveness.
* Conduct regular reviews of the documented risks to identify trends, patterns, and areas for improvement.
* Ensure that all stakeholders have access to the risk documentation and are aware of their roles in mitigating identified risks.
• Tool: Integrated Project Risk Assessment (IPRA), Version 2.0 (IR181-2)
* Define IPRA’s purpose: Enables project teams to identify, assess, and mitigate risks, especially for complex projects in unfamiliar environments.
* Outline the risk management stages: Implements risk identification, assessment, analysis, and mitigation, serving as a structured guide.
* Highlight risk matrix usage: Uses the IPRA risk matrix to prioritize highly likely, high-impact risks for mitigation.
* Emphasize continuous assessment: Conducts IPRA evaluations throughout the project’s various stages to adjust for new risks as the project evolves.
* Recommend action plans: Implement mitigation strategies such as risk avoidance, retention, control, transfer, and contingency planning.
RS181-1 takeaway summary
(2). Probabilistic Risk Management in Design and Construction Projects (RS280-1)
• Risk management in design and construction projects has three levels:
• Level 1. Risk identification: Identifies risks and opportunities
* Conduct interviews with project stakeholders to gather information about potential risks and opportunities.
* Collect documents related to risk management and probabilistic approaches, including policies, procedures, processes, reports, and forms.
* Review case studies of previous projects to identify common risk attributes that trigger the use of different levels of risk analysis.
* Analyze data collected from interviews and document reviews to visualize the organization's risk management framework.
* Develop a project-specific risk register using probabilistic approaches, including hypothetical examples and level triggers.
• Level 2. Deterministic risk analysis: Analyzes risks through single-point estimates of potential impacts
* Develop a comprehensive risk register using probabilistic approaches to quantify and rank project risks.
* Determine overall contingency by providing an expected value for each identified risk, considering both positive and negative outcomes.
* Calculate mean values for each risk to provide an expected value for the impact of that risk on the project.
* Use these single-point estimates to analyze the potential impacts of each identified risk on the project’s schedule, budget, and quality.
• Level 3. Probabilistic risk analysis: Analyzes risks through probability distribution estimates of potential impacts
* Develop a comprehensive risk register using probabilistic approaches to quantify and rank project risks.
* Collaborate with stakeholders to gather data and information about each identified risk, including its likelihood and impact.
* Conduct sensitivity analysis to test the robustness of the risk assessments against changes in assumptions or inputs.
* Use Monte Carlo simulations or other probability distribution methods to estimate potential impacts and visualize risk scenarios.
* Review and refine the risk assessments regularly throughout the project’s lifecycle to ensure their ongoing accuracy and relevance.
• Tool: Applying Probabilistic Risk Management in Design and Construction Projects, Version 1.2 (IR280-2)
* Promote a probabilistic approach: Advocates using probabilistic risk management to better anticipate project costs, schedules, and potential risks, thereby enhancing decision-making and contingency planning.
* Define a three-level framework: Establishes a three-level (identification, deterministic analysis, and probabilistic analysis) risk management model that is tailored to varying project complexities and uncertainties.
* Utilize Monte Carlo simulations: Recommends Monte Carlo simulations for complex projects to assess the probability and impact of risks, thus offering a clear range of cost and time outcomes.
* Facilitate risk communication: Emphasizes risk visualization tools, such as tornado diagrams and probability density graphs, to improve stakeholder understanding and communication.
* Provide a risk register tool: Offers a customizable Excel-based risk register to track risks and guide project teams in applying the appropriate risk management level.
• Tool: What's the Risk? (IR280-3)
* Identify key risks: Recognizes primary risks, such as poor soil conditions and utility delays, that may impact the project’s cost and schedule.
* Estimate cost and schedule: Project costs range from $15M to $30M, with an expected mean cost of $22.5M. Schedules average 3.6 years.
* Focus the mitigation efforts: Targets risks, such as ‘Historic site’ and ‘Replaced culvert over Wandering Creek’, for significant cost impact reductions.
* Assess contingency needs: Plans contingencies to keep costs and timelines within 80% confidence levels of $26M and 3.8 years.
* Utilize sensitivity analysis: Performs analysis to understand the highest-impact risks and where to prioritize mitigation for cost efficiency.
RS280-1 takeaway summary
(3). Front End Planning: Break the Rules, Pay the Price (RS213-1)
• Thoroughly define existing project site conditions
* Conduct a thorough site evaluation to investigate and document geotechnical, hydrological, environmental, permitting, as-built conditions, and other local information that is needed to plan the job.
* Gather all available data for the project site, including historical records, surveys, and reports, to ensure a comprehensive understanding of the existing conditions.
* Engage experts or consultants if necessary to provide specialized knowledge or services for specific aspects of the site's existing conditions.
* Develop a detailed report that outlines the findings from the investigation and documentation process to serve as a reference guide throughout the project.
* Verify that all stakeholders have access to and understand the defined existing site conditions to ensure alignment across teams and minimize potential conflicts.
• Select the proper contracting strategy early in the project
* Determine the project’s requirements and risks to identify the most suitable contracting approach.
* Evaluate different contracting strategies (e.g., design-build, construction management-at-risk) based on factors such as scope complexity, budget constraints, and stakeholder expectations.
* Consider partnering with contractors or consultants who have experience with similar projects to leverage their expertise and reduce risk.
* Develop a comprehensive Request for Proposal that outlines the project’s requirements, contracting strategy, and evaluation criteria.
* Carefully review proposals from potential contractors and select the best fit based on factors such as qualifications, pricing, and approach.
• Identify and understand the risks of new project types, technologies, or locations
* Assign experienced professionals to lead the project teams responsible for scope definition and design activities.
* Conduct thorough research into the unique characteristics of new projects, technologies, or locations to mitigate potential risks.
* Foster collaboration among team members with diverse expertise to leverage collective knowledge and experience.
* Provide training and support to staff about new project types, technologies, or locations to ensure their adequate understanding and the mitigation of associated risks.
* Develop a comprehensive risk assessment plan that considers all aspects of the project, including scope, schedule, budget, and stakeholders.
• Refer to the following Best Practices sections for other takeaways in this report that are relevant to project risk assessment: 2. Alignment and 7. Front-End Planning
RS213-1 takeaway summary
(4). Equitable Risk Allocation (RS210-1)
• The Equitable Risk Allocation model doubles as a risk learning tool
* Implement training sessions using the Equitable Risk Allocation model to educate project teams about risk allocation from both the business and legal perspectives.
* Use the model's worksheets to identify and evaluate project-specific risks collaboratively between parties.
* Apply decision trees to guide the parties in making informed risk allocation choices based on individual project conditions.
* Conduct internal alignment exercises within each party to prepare for two-party risk assessment and cooperative discussions.
* Utilize contract language tables and legal research to address identified ‘hot-button’ risks to ensure balanced and enforceable agreements.
• Facilitate internal and external risk alignment
* Conduct internal risk assessments using the single-party worksheet to ensure alignment on risk allocation goals before engaging in external negotiations.
* Establish a collaborative risk identification session to capture project-specific risks and prevent oversights prior to making two-party assessments.
* Utilize the two-party worksheet to compare internal risk ratings, identify discrepancies, and align risk priorities between the contracting entities.
* Engage legal and contracting experts to review critical risks that have high rating disagreements for optimal allocation and fair contract terms.
* Monitor and adjust risk strategies through iterative feedback obtained from the two-party assessments to enhance alignment continuously throughout the project’s lifecycle.
• Facilitate a cooperative two-party process
* Utilize the two-party risk assessment worksheet to help identify common high-concern risks and to ensure mutual understanding.
* Address risk-related disagreements by collaboratively analyzing rating discrepancies to establish aligned action plans.
* Engage in decision tree analysis to guide cooperative decision-making and to explore options such as insurance or shared responsibility.
* Refer to the legal research and contract language tools to clarify and allocate high-stakes risks fairly.
* Conduct follow-up discussions post-assessment to verify mutual agreement on risk handling, and monitor adjustments as needed.
• Promote a logical decision-making process
* Use decision trees to guide each party through logical risk allocation steps, balancing factors such as insurability and potential financial impacts.
* Document and assess each risk's likelihood and impact to ensure transparent, data-driven allocation.
* Apply contract language tables and legal research to handle complex risk scenarios based on industry standards.
* Review risk ratings and discrepancies collaboratively to identify high-priority risks that require in-depth analysis.
* Regularly revisit and adjust risk strategies based on real-time project data to improve future risk decisions.
• Transcend and assist multiple construction phases
* Apply the risk assessment worksheets consistently across all project phases to ensure continuity and informed decision-making.
* Review and adjust risk allocation at each phase, from the Request for Proposal stage to post-award, to accommodate evolving project goals.
* Conduct bid-phase risk assessments to align potential contractors with the project’s risk tolerance and priorities.
* Implement risk monitoring during the execution phase to update assessments with real-time data for effective risk mitigation.
* Utilize feedback loops after each phase to refine the risk management practices for future projects.
• Identify 107 risks
* Review the comprehensive list of 107 risks in the model as a baseline to ensure that no major construction risks are overlooked during the planning phase.
* Categorize the identified risks across the project’s lifecycle phases, such as planning, execution, and operations, for targeted risk management.
* Include additional project-specific risks at the start to capture unique threats or liabilities that may not be included in the baseline list.
* Utilize the risk assessment worksheets to systematically evaluate each risk's likelihood, impact, and allocation suitability.
* Regularly update the risk list throughout the project’s lifecycle to ensure adaptive and relevant risk management.
• Eliminate adversarial contracting
* Encourage collaborative contract reviews to identify and address any inequitable risk allocation from the start.
* Avoid unilateral risk-shifting clauses to promote balanced risk-bearing, thereby reducing adversarial contract dynamics.
* Include measurable acceptance criteria to minimize disputes over contract performance and to avoid subjective interpretations.
* Establish mutual indemnity clauses that fairly distribute responsibility for damages, thereby supporting cooperative risk management.
* Define delay-related risk and compensation transparently to foster fair accountability for project delays.
• Save overall project money
* Allocate risks to the party that is most equipped to manage them in order to minimize costly disputes and ensure financial stability.
* Avoid transferring excessive risks to lower-tier contractors to prevent inflated bids, thereby ensuring realistic project costs.
* Regularly review and adjust risk allocations to adapt to project changes, thereby reducing unforeseen financial impacts.
* Implement risk assessment worksheets to preemptively identify high-cost risks and align them with capable parties.
* Foster collaborative risk management to mitigate the potential costs associated with adversarial contractual relationships.
• Tool: Equitable Risk Allocation: Risk Assessment Worksheets Tutorial
* Encourage risk sharing: Promotes cooperative risk allocation to prevent financial strain across all parties in construction projects.
* Encourage usage of the risk assessment worksheets: Guides contracting parties through single-party and two-party worksheets to align risk allocation both internally and externally.
* Identify common risks: Addresses 14 hot-button risks that often lead to disputes if not allocated appropriately.
* Support systematic decision-making: Implements decision trees and principles for structured, fair risk distribution throughout the project phases.
* Minimize financial impact: Allocates risks to the party best positioned to manage them, with the aim to reduce financial and operational disruptions.
• Tool: Equitable Risk Allocation: A Legal Perspective
* Highlight risk assessment: Encourages collaborative risk allocation early in projects to avoid costs associated with inappropriate allocation.
* Identify key risks: Focuses on 14 common hot-button risks, such as ‘No Damages for Delay’ and ‘Consequential Damages’, to streamline contract negotiations.
* Provide contract language guidance: Offers language tables to help define risk clauses clearly, with the aim to achieve equitable terms.
* Use legal references: Supplies flowcharts and case-based guidance to clarify legal perspectives on risk distribution.
* Promote risk allocation model: Recommends the Two-Party Risk Assessment and Allocation Model as a foundational tool for fair risk management.
RS210-1 takeaway summary
15. QUALITY MANAGEMENT (4)
(1). Best Practices in Quality Management for the Capital Facilities Delivery Industry (RS254-1)
• Implement the following six elements for an effective Quality Management System (QMS)
* Leadership support
* Process management
* Measurement, analysis, and improvement
* Supplier QMS
* QMS training
* QMS certification
• Incorporate leadership and management commitment into the QMS
* Develop a quality metrics program to track performance and identify areas for improvement.
* Provide consistent, visible leadership throughout the organization by setting clear expectations and goals.
* Ensure that upper management is committed to implementing the QMS and provide the resources necessary for its success.
* Establish formal training programs to educate employees about the importance of quality and their roles in maintaining it.
* Demonstrate awareness of the need for effective training and provide opportunities for continuous learning.
• Enhance the level of QMS training
* Provide formal training programs to educate employees about quality management principles and their roles in maintaining it.
* Ensure that all employees receive regular training sessions to maintain their knowledge and skills related to QMS.
* Develop an effective training program that covers topics such as process improvement, problem-solving, and continuous learning.
* Conduct periodic assessments to evaluate the effectiveness of the training programs and to identify areas for improvement.
* Consider offering informal training opportunities through workshops, seminars, or online courses to supplement formal training.
• Emphasize supplier and contractor QMS
* Conduct regular audits of suppliers/contractors to ensure compliance with the QMS.
* Develop a comprehensive training program for suppliers and contractors to improve their understanding of the organization's QMS.
* Require all suppliers and contractors to use the organization's quality management approach, and provide assistance when needed.
* Establish clear metrics, measurement, and analysis processes to monitor supplier/contractor performance and identify areas for improvement.
* Collaborate with highly rated organizations that have highly effective QMSs to share best practices and improve overall quality management.
• Use metrics extensively
* Use organization-level metrics more frequently throughout the project phases.
* Consistently apply metrics across all projects and departments
* Establish clear key performance indicators to measure QMS effectiveness.
* Regularly review and analyze metric data to identify areas for improvement.
* Implement a centralized dashboard or reporting tool to track and visualize metric performance.
• Manage work process improvements
* Implement a formal process for identifying and tracking work process improvements.
* Develop strategies such as knowledge management, lessons learned, preventive and corrective actions, and continuous improvement to support the identification, development, and deployment of work process improvements.
* Use internal audits, customer feedback, and training to identify areas for improvement and track the effectiveness of the implemented changes.
* Standardize work processes and metrics across all projects and departments.
* Develop a change management system to ensure the successful implementation of new work processes.
• Work on QMS certification and accreditation
* Obtain ISO certification to demonstrate commitment to quality management.
* Establish a regular QMS review by external reviewers to ensure compliance with industry standards.
* Implement a certified QMS that is regularly audited and reviewed.
* Ensure that contractors are frequently reviewed, including those who do not have ISO certification.
* Utilize the Quality Management/ Business Excellence Systems Correlation Matrix to compare various quality systems.
• Tool: Implementing and Improving Quality Management Systems in the Capital Facilities Delivery Industry (IR254-2)
* Establish a QMS framework: Defines and implements a QMS that is tailored to capital facilities delivery and ensures alignment with ISO 9001 standards.
* Assess QMS maturity: Regularly evaluates the QMS's effectiveness using tools such as the Quality Maturity Matrix and compliance checklists.
* Provide continuous improvement: Focuses on ongoing QMS improvement, guided by key performance metrics and best practices within the industry.
* Encourage leadership commitment: Helps to secure top management’s commitment to support QMS implementation and improvement initiatives.
* Utilize best practices and tools: Applies specific tools, such as the Quality Management/Business Excellence Systems Correlation Matrix, to enhance QMS processes and align with industry standards.
RS254-1 takeaway summary
(2). Engineering Deliverables: Get It Right the First Time (RS320-1)
• Apply the Design Deliverable Quality Assessment (DDQA) tool to proactively identify and eliminate or plan the mitigation of potential quality defects among the 11 problematic deliverables listed in RS320-1
The 11 problematic deliverables are: front-end engineering design (FEED) validation; Level 3 baseline schedule; constructability inputs; piping and instrumentation diagrams (P&IDs); equipment specifications and data sheets; maintainability inputs; vendor data; 3D model + 3D model reviews + clash detection; piping routing and isometrics; nozzles, ladders, and platforms for towers/vessels/tanks; and miscellaneous pipe support drawings.
* Focus first on the 11 problematic deliverables and use the DDQA tool to identify potential quality defects.
* Scrutinize the completeness of each deliverable using the Completeness of Design Deliverables checklist to ensure that all necessary information is included.
* Review and analyze the identified potential defects with project teams, design managers, and other stakeholders to develop mitigation plans or corrective actions.
* Implement and track the effectiveness of the implemented mitigation plans for each problematic deliverable to eliminate or minimize quality defects.
* Monitor and verify that all 11 problematic deliverables meet the required standards and specifications before proceeding with further construction activities.
• Scrutinize the completeness of the 11 problematic deliverables using the Completeness of Design Deliverables Checklist (CDDC) tool, and plan corrective actions for achieving complete deliverables
* Review and analyze each of the 11 problematic deliverables using the CDDC tool to identify incomplete or missing information.
* Identify specific completeness issues for each deliverable type by examining the checklist output and discussing the findings with project teams, design managers, and other stakeholders.
* Develop a plan to address the identified completeness gaps by prioritizing corrective actions, allocating resources, and establishing timelines for the completion of outstanding tasks.
* Implement and track the effectiveness of the planned corrective actions to ensure that complete and accurate deliverables are achieved for each problematic deliverable type.
* Verify that all 11 problematic deliverables meet the required standards and specifications before proceeding with further construction activities.
• Integrate the use of the two tools, the DDQA and the CDDC, into the work processes of design management and project quality management
* Develop a comprehensive training program to educate design managers and project quality managers about the usage and benefits of the two tools.
* Incorporate regular tool-based reviews and audits as part of the design management and project quality management workflows.
* Mandate the use of the DDQA and CDDC for all design deliverables to ensure consistency across projects and teams.
* Establish a centralized repository to store and track the results obtained from the two tools to facilitate data-driven decision-making.
* Conduct regular assessments and evaluations to ensure the effective integration of the two tools into daily operations and identify areas for improvement.
• Incorporate the knowledge gained from RS320-1 in design quality training programs
* Update existing design quality training programs to include the findings and best practices presented in RS320-1.
* Develop new modules or courses that focus specifically on the 11 problematic deliverables, highlighting their common defects and corrective actions.
* Integrate the case studies and real-world examples found in RS320-1 into training materials to enhance learner engagement and retention.
* Ensure that trainers are equipped with the knowledge and tools necessary to effectively convey the information obtained from RS320-1 to design professionals.
* Review and revise existing quality control processes and procedures in accordance with the findings of RS320-1 and incorporate them into future training programs.
• Consider design deliverable defects, their impacts, and causal factors when expanding the DDQA tool in the future to accommodate more deliverables
* Identify potential design deliverable defects that may arise during project execution.
* Analyze the root causes of these defects to develop targeted mitigation strategies.
* Develop expanded DDQA criteria to capture additional design deliverables and their associated quality metrics.
* Review existing design management processes to ensure seamless integration with the updated DDQA tool.
* Refine training programs for designers, engineers, and project managers to use the enhanced DDQA tool effectively.
• Tool: Tools for Enhancing the Quality of Problematic Design Deliverables (IR320-2)
* Identify and address the 11 most problematic design deliverables that have common defects and causal factors.
* Implement the DDQA and CDDC to assess quality and completeness in design deliverables, thereby enabling corrective actions.
* Engage project stakeholders, such as engineering managers and quality directors, in using these tools for improved design quality.
* Utilize leading and lagging metrics for proactive and reactive assessments across the various project phases.
* Be integrated into design management processes to mitigate risks and enhance overall project performance.
RS320-1 takeaway summary
(3). Making Zero Rework A Reality (RS203-1)
• Demonstrate management commitment to zero rework
* Set specific goals for rework reduction, such as meeting specifications or achieving zero defects.
* Ensure that senior project managers participate in regular quality reviews and audits to demonstrate upper management commitment.
* Develop constructability analysis and project-specific quality plans prior to project planning.
* Limit change orders to maintain focus on reducing rework.
• Increase full-time quality staff
* Ensure that personnel who are responsible for quality acceptance have some form of certification to perform their project function.
* Analyze current quality staffing levels and compare them with safety staffing benchmarks.
* Integrate quality management personnel into project meetings and functions to ensure proper integration with other stakeholders.
* Allocate dedicated budget and time for ongoing quality training to improve staff expertise and effectiveness.
• Conduct quality pre-project and pre-task planning
* Develop project/site-specific quality plans before mobilization to ensure alignment with overall goals and unique quality requirements.
* Conduct constructability reviews for quality considerations to identify potential issues early on in the project.
* Require pre-task quality analysis prior to field execution.
* Train workers to conduct pre-task quality checks before starting work.
* Establish checklists and guidelines to ensure consistent pre-project and pre-task quality planning.
• Implement quality training
* Implement monthly quality training sessions, including toolbox talks and specialized workshops.
* Integrate quality procedures into mandatory worker orientation programs.
* Track rework reduction and worker participation to assess training effectiveness.
• Encourage worker participation and involvement
* Encourage worker involvement in pre-task planning by providing necessary information and resources.
* Foster open communication channels with workers to address concerns and resolve issues promptly.
* Provide opportunities for workers to participate in job quality analysis and constructability reviews.
* Empower workers to take ownership of their work processes through regular feedback and recognition.
• Enhance subcontract quality management
* Require subcontractors to submit comprehensive quality plans and track rework or defects.
* Prequalify subcontractors based on their quality performance before awarding contracts.
* Conduct regular audits of subcontractor work processes to ensure compliance with project requirements.
* Implement ‘for cause’ testing for quality incidents, including pre-employment screening.
* Establish clear expectations and incentives for subcontractors to prioritize quality in their work.
• Track quality rework
* Track and record all quality-related rework or defects to identify trends and areas for improvement.
* Conduct regular investigations into the causes of rework or defective work to implement corrective actions.
* Establish clear procedures for reporting and documenting quality issues, including root cause analysis and corrective action plans.
* Monitor and analyze quality performance metrics, such as defect rates and rework percentages, to measure project success.
* Develop a comprehensive database to store and track quality-related data, thereby enabling informed decision-making and continuous improvement.
• Select the contract type
* Consider using cost-plus contracts to improve quality program effectiveness.
* Implement lump-sum contracts only when necessary, as they may not be as effective in promoting high-quality work.
* Ensure that contract requirements include provisions for additional expenditures on quality control measures if needed.
* Develop clear guidelines for project managers regarding the type of contract to use based on specific project needs and goals.
* Monitor and track the effectiveness of different contract types in achieving desired outcomes, such as reduced rework.
• Tool: Zero Field Rework Self-Assessment Opportunity Checklist (IR203-2)
* Promote leadership by example: Fosters a culture of quality and rework minimization through visible, accountable leadership that models best practices.
* Ensure sufficient resources: Maintains capable resources and provides the necessary time and tools for achieving zero rework performance.
* Encourage employee involvement: Actively involves employees in quality improvement, thus fostering ownership and accountability for rework outcomes.
* Enhance communication: Supports open communication across all levels to address quality concerns and to share best practices effectively.
* Implement rigorous quality audits: Regularly conducts quality/rework audits to ensure compliance with established practices and continuous improvement.
RS203-1 takeaway summary
(4). Summary of Standard Industry-wide Quality Metrics (RS313-1)
• Offer a novel but standardized approach to measuring quality using the Quality Pyramid
* Develop a project-specific Quality Pyramid framework that aligns with the organization's capital facilities delivery industry standards.
* Implement the top half of the pyramid across all projects and phases, focusing on unplanned events and outcomes, to measure quality performance consistently.
* Classify key quality outputs at handover points between groups using the Quality Pyramid steps to ensure a standardized approach to measuring quality.
* Apply the principles from the Quality Pyramid to add value by analyzing action items from key reviews within the organization's capital project management processes.
* Monitor the effectiveness of the Quality Pyramid implementation and adjust as needed to ensure continuous improvement in quality performance.
• Use the Quality Performance Rate (QPR) as a quantified and objective indicator of organization- and project-level quality performance to enable benchmarking and continuous improvement of the quality management system (QMS)
* Calculate the QPR by dividing the total number of unplanned events by labor hours spent, using normalization factors to ensure comparable results across projects.
* Benchmark the organization's overall QPR against industry standards and best practices to identify areas for improvement and optimize the organization’s QMS.
* Regularly monitor project-level QPRs to track progress, detect trends, and make data-driven decisions to enhance quality performance and reduce unplanned events.
* Analyze the correlation between the QPR and other key performance indicators to gain insights into the root causes of quality issues and to develop targeted improvement strategies.
* Improve the organization’s QMS by implementing changes based on lessons learned from analyzing QPR data, thereby ensuring continuous improvement and reducing the risk of unplanned events.
• Report quality data to be categorized correctly in the Quality Pyramid
* Collect project data from various sources such as project management software and documentation.
* Translate the collected data into a format that aligns with the Quality Pyramid categories (such as the Valuable/Targets Met? category).
* Categorize reported data according to the Quality Pyramid structure and include unplanned outcomes and events.
* Map company-specific quality metrics to the corresponding levels of the Quality Pyramid for accurate reporting.
* Summarize the categorized data into a comprehensive report, such as a Quarterly Performance Report, to track project performance.
• Quantify quality performance across an entire project or organization using the proposed quality metrics system
* Develop and implement standardized quality metrics that align with the Quality Pyramid structure.
* Collect data on planned outcomes and events to track progress against targets.
* Categorize unplanned outcomes and events into Valuable/Targets Met? category for accurate reporting.
* Calculate performance rates, such as the QPR, using the collected data.
* Analyze and report quality performance metrics regularly to identify trends and areas for improvement.
• Implement the Quality Pyramid definitions in the organization’s QMS
* Define and document organizational quality metrics that align with the Quality Pyramid structure.
* Map existing quality processes to the corresponding levels of the Quality Pyramid (Valuable/Targets Met?).
* Categorize and track unplanned outcomes and events using the top half of the Quality Pyramid.
* Develop training programs for project teams to apply Quality Pyramid principles in their daily work.
* Establish a system to regularly review and update QPRs based on the Quality Pyramid metrics.
• Consistently utilize the metrics practices and the Quality Pyramid
* Classify key quality outputs at points where one group hands off a deliverable to another group using the top half of the Quality Pyramid.
* Review and update QPRs regularly based on the Quality Pyramid metrics.
* Apply the principles of the Quality Pyramid to add value by analyzing action items from key reviews within capital project management processes.
* Use the steps in the top half of the pyramid consistently across projects to measure quality performance.
* Establish a system for tracking unplanned outcomes and events using the Quality Pyramid structure.
• Focus on measuring unplanned events as a standardized measurement of quality performance
* Identify and categorize unplanned events that occur during project execution using the top half of the Quality Pyramid.
* Assign weighted severity levels to each defect or failure based on its consequences.
* Normalize data across different projects sizes and industries for comparison purposes.
* Enter event category information into the reporting system, allowing for tracking and analysis of quality performance.
* Use the metrics practices and the Quality Pyramid as standardized measurements of quality performance.
• Establish goals to continuously improve the QMS and the quality performance of capital projects
* Set specific, measurable, achievable, relevant, and time-bound (SMART) targets for improving quality performance across all capital projects.
* Establish key performance indicators to track progress towards these goals and to identify areas for improvement.
* Conduct regular reviews and assessments of the QMS to ensure that it remains effective in achieving desired outcomes.
* Develop a continuous learning culture by utilizing data from past projects to improve work processes and personnel training.
* Implement changes to the QMS based on lessons learned, best practices, and industry developments.
• Tool: Implementing Standard Industry-wide Quality Metrics (IR313-2)
* Establish a common quality metric: Introduces the QPR to benchmark quality in construction projects, thus promoting industry-wide standardization.
* Define the Quality Pyramid framework: Structures quality issues by severity into the Quality Pyramid, which has categories ranging from preventive actions to failures for consistent reporting.
* Outline the QPR calculation and use: Details the QPR calculation method and incorporates weighted severity levels of unplanned events normalized by labor hours for cross-project comparability.
* Provide implementation steps: Includes a roadmap to implement the QPR, with phases for data collection, categorization, normalization, and quality performance tracking.
* Highlight industry impact: Emphasizes the QPR's potential to drive improvements in cost, schedule, and quality performance across the construction industry.
RS313-1 takeaway summary
16. TEAM BUILDING (3)
(1). Compass: An Assessment Tool for Improving Project Team Communications (RS105-1)
• Prioritize effective communication to ensure successful project completion
* Develop an assessment tool to measure communication effectiveness during the engineering, procurement, and construction project phases.
* Implement clear communication protocols across all project phases.
* Train project team members to use effective communication strategies.
* Evaluate the relationship between communication effectiveness and project success.
* Monitor communication effectiveness regularly to identify and address issues promptly.
• Strengthen communication effectiveness to enhance project success
* Measure communication effectiveness using tools such as Compass.
* Identify specific communication areas that need improvement based on effectiveness scores.
* Allocate resources to enhance communication in weak areas identified by the assessment tool.
* Track changes in communication effectiveness over the project lifecycle to gauge improvements.
* Implement strategies based on data to improve overall project success.
• Assess communication effectiveness using six critical communication categories: accuracy, timeliness, completeness, understanding, barriers, and procedures
* Ensure information accuracy by minimizing conflicting instructions and poor communication.
* Provide timely updates, including design and schedule changes, to all project stakeholders.
* Deliver comprehensive and relevant information to all team members.
* Clarify roles and expectations to improve understanding among team members.
* Identify and address barriers to effective communication, such as interpersonal or logistical issues.
• Conduct regular reassessments throughout the project’s lifecycle to monitor communication improvements
* Schedule periodic reassessments using the Compass tool to track communication effectiveness.
* Compare reassessment results to initial benchmarks to measure improvements.
* Adjust communication strategies based on the reassessment findings to ensure continuous improvement.
* Document all changes and their impacts to build a knowledge base for future projects.
* Engage the project team in discussions about the reassessment findings and improvement plans.
• Tool: Compass: Communications Project Assessment Tool, Version 2.1 (IR105-2)
* Define key enablers for project success, focusing on tools and best practices for improved outcomes in construction.
* Highlight collaboration and technology as critical drivers for efficiency and risk mitigation.
* Recommend standardized procedures to streamline processes and improve project consistency.
* Emphasize the importance of data integration and interoperability to support real-time decision-making.
* Encourage stakeholder engagement to enhance alignment, accountability, and project transparency.
RS105-1 takeaway summary
(2). Team Building: Improving Project Performance (RS37-1)
• Use a team-building process
* Identify a suitable consultant to facilitate the team-building process and to ensure effective communication among project stakeholders.
* Engage the consultant early in the life of the project to establish trust and set clear expectations.
* Facilitate regular meetings and workshops with all project participants, including contractors, architects, engineers, and other relevant parties.
* Encourage open dialogue, active listening, and constructive feedback throughout the team-building process to foster collaboration and resolve conflicts.
* Regularly monitor the progress and outcomes of the team-building process to ensure that it remains aligned with the project’s goals and objectives.
• Use a consultant to facilitate the team-building process
* Use a qualified professional as an external or internal consultant to bring necessary skills and expertise to the team-building process.
* Engage the consultant early in the project’s lifecycle to establish trust and set clear expectations among all stakeholders.
* Facilitate regular meetings, workshops, and discussions with the consultant to ensure effective communication and collaboration among the project participants.
* Select a consultant who has experience in construction projects and understands the unique challenges and complexities of the industry.
* Regularly monitor the consultant's progress and outcomes to ensure alignment with the project’s goals and objectives.
• Begin the team-building process early in the life of the project
* Identify key stakeholders and team members to participate in the team-building process at the onset of the project.
* Schedule a formal team-building session or series of sessions within the first few months of the project timeline.
* Develop a comprehensive plan for team building, including goals, objectives, and activities, early on in the project to ensure alignment with project requirements.
* Establish open communication channels and encourage collaboration among team members from the outset to foster trust and understanding.
* Incorporate team building into regular project meetings or progress updates to maintain momentum and reinforce shared goals.
• Seek broad participation in the team-building process
* Involve all key stakeholders and team members in the team-building process to ensure that everyone is aligned with the project goals.
* Cast a wide net by including representatives from various departments, such as engineering, procurement, and operations, to foster collaboration.
* Encourage open communication channels by inviting all relevant personnel to participate in regular meetings or workshops that are focused on teamwork and collaboration.
* Make an effort to include diverse perspectives by involving team members with different backgrounds, experiences, and skill sets in the process.
* Consider conducting surveys or focus groups to gather input from a broader range of stakeholders and ensure that everyone's voice is heard.
• Make the team-building process an integral part of project management
* Incorporate team building into regular project meetings and progress updates to maintain momentum and reinforce shared goals.
* Integrate team-building activities with existing project management processes, such as planning, execution, and monitoring, to ensure seamless integration.
* Establish clear expectations about ways that team building will be used to drive project success, and communicate these expectations to all stakeholders.
* Develop a plan to recognize and reward individual contributions to the team's overall performance, thereby fostering a sense of shared responsibility and accountability.
* Regularly review and assess the effectiveness of the team-building efforts in achieving desired outcomes, and make adjustments as needed to optimize the results.
RS37-1 takeaway summary
(3). Pre-Project Planning Tools: PDRI and Alignment (RS113-1)
• Develop a culture of trust and honesty to enhance collaboration and team synergy
* Establish clear communication channels to encourage openness and reduce any misunderstandings among team members.
* Promote transparency in decision-making processes to ensure that all team members understand and trust the project goals and strategies.
* Encourage active listening and respect differing viewpoints to build mutual respect and enhance team relationships.
* Set up regular, productive team meetings to provide updates, share challenges, and foster a sense of shared responsibility.
* Recognize and reward honest feedback and contributions to reinforce a culture where team members feel valued and engaged.
• Encourage open communication to break down barriers and foster a supportive environment
* Implement regular check-ins to address concerns and ensure that all team members are informed of the project’s progress.
* Use accessible communication tools to allow team members to provide updates, share ideas, and give feedback.
* Establish clear communication protocols to prevent misunderstandings and ensure consistency across all project phases.
* Encourage open feedback loops to address issues promptly and adapt strategies as needed.
* Provide training on effective communication skills to improve clarity and mutual understanding within the team.
• Promote shared values among team members to align efforts toward common project goals
* Define and communicate core project values to ensure that all team members understand and commit to them.
* Establish a project charter that outlines shared goals and values to guide team decision-making and actions.
* Sponsor workshops to discuss ways that individual roles contribute to the overarching project objectives and values.
* Encourage mutual respect by acknowledging each team member’s expertise and contributions to the project.
* Regularly review progress against shared values to reinforce alignment and address any deviations collaboratively.
• Implement team-building programs to strengthen bonds and improve team cohesion
* Organize regular team-building activities to foster trust and improve collaboration across function groups.
* Conduct workshops on collaboration skills to enhance team members' ability to work together effectively.
* Schedule cross-function sessions to improve understanding of each team member’s role and contributions.
* Facilitate open discussions about the project’s challenges to build resilience and collective problem-solving skills.
* Recognize and celebrate team achievements to boost morale and reinforce a unified project culture.
• Recognize and reward contributions to motivate team members and reinforce commitment to project objectives
* Establish a formal recognition program to highlight exceptional contributions that align with the project’s goals.
* Provide timely rewards for milestone achievements to encourage ongoing commitment and project focus.
* Recognize both individual and team accomplishments to foster a balanced sense of appreciation and teamwork.
* Align rewards with project objectives to reinforce behaviors and actions that directly contribute to project success.
* Offer public acknowledgment during meetings to celebrate contributions, thereby reinforcing a culture of appreciation and motivation.
• Refer to the following Best Practices sections for other takeaways in this report that are relevant to team building: 2. Alignment and 7. Front-End Planning
RS113-1 takeaway summary
17. ZERO ACCIDENT TECHNIQUES (10)
(1). Making Zero Accidents a Reality (RS160-1)
• Ensure management commitment to safety
* Communicate safety expectations and goals to all project stakeholders.
* Allocate resources and funding to support comprehensive safety programs.
* Lead by example, with visible and active participation in safety initiatives.
* Integrate safety into project planning, scheduling, and decision-making processes.
* Regularly review and assess safety performance, implementing improvements as needed.
• Implement a subcontractor safety-related management process
* Prequalify subcontractors based on safety performance.
* Set clear safety expectations in subcontractor agreements.
* Monitor subcontractor safety practices and compliance regularly.
* Provide necessary support and resources to subcontractors for safety initiatives.
* Implement sanctions for subcontractors that fail to meet safety standards.
• Hire workers a few weeks before a short-duration project (which may be due to shutdowns, turnarounds, or outages)
* Conduct thorough safety orientation procedures immediately upon hiring.
* Ensure that workers understand project-specific hazards and safety protocols.
* Provide focused training regarding high-risk tasks that are relevant to the short-duration project.
* Emphasize the importance of adherence to safety guidelines despite the project's brevity.
* Monitor closely for compliance throughout the project duration.
• Select contract types that acknowledge the importance of safety
* Select contract types that incentivize safety performance.
* Incorporate safety clauses and requirements into contract agreements.
* Consider using performance-based contracts that tie payment to safety outcomes.
* Evaluate subcontractors' safety records before awarding contracts.
* Regularly review and update contract terms to align with safety goals.
• Ensure staff safety
* Hire dedicated safety personnel at both corporate and project levels.
* Provide adequate training and resources for safety staff.
* Ensure safety representatives have authority to enforce safety protocols.
* Implement a process for regular safety audits and compliance testing.
* Foster a culture of safety awareness among all staff members.
• Use contracts with safety incentives
* Incorporate safety performance metrics into contract incentives.
* Offer financial rewards or bonuses for achieving safety goals.
* Provide recognition for subcontractors with exemplary safety records.
* Establish clear criteria for earning incentives tied to safety.
* Regularly monitor and evaluate safety performance to ensure compliance with incentivized contracts.
• Conduct pre-project and pre-task planning that incorporates safety concerns
* Conduct pre-project hazard analyses to identify potential risks.
* Develop comprehensive safety plans for each project phase.
* Prioritize safety in pre-task planning meetings.
* Integrate safety considerations into overall project planning processes.
* Review and update safety plans regularly based on project progress and changing conditions.
• Provide safety education (orientation and specialized training)
* Provide comprehensive safety orientation for all workers.
* Offer specialized training on specific safety topics relevant to the project.
* Ensure all workers receive regular safety education updates.
* Utilize various training methods such as in-house sessions and external resources.
* Assess the effectiveness of safety education programs through feedback and evaluations.
• Encourage worker involvement
* Establish channels for workers to report safety concerns and suggestions.
* Encourage active participation in safety meetings and toolbox talks.
* Implement systems for recognizing and rewarding proactive safety behaviors.
* Involve workers in pre-task safety planning and hazard identification.
* Foster a culture of ownership and accountability for safety among all workers
• Deploy safety performance evaluation, recognition, and reward
* Regularly evaluate safety performance against established metrics.
* Recognize and reward individuals and teams for exemplary safety practices.
* Provide feedback and constructive criticism to improve safety culture.
* Implement incentive programs tied to safety achievements.
* Publicly acknowledge and celebrate safety milestones and accomplishments.
• Establish accident/incident investigation process
* Establish a standardized process for accident and incident investigations.
* Ensure prompt and thorough investigations for all accidents and near misses.
* Involve relevant personnel such as foremen, superintendents, and safety representatives in investigations.
* Document findings and implement corrective actions to prevent recurrence.
* Review investigation reports to identify trends and improve safety measures.
• Implement drug and alcohol testing
* Implement a comprehensive drug and alcohol testing policy for all workers.
* Conduct pre-employment screening for drug and alcohol use.
* Clearly define consequences for failing drug tests, including termination or rehabilitation.
* Provide treatment options for employees struggling with substance abuse.
* Regularly review and update the drug and alcohol testing program to ensure effectiveness.
• Plan ahead for projects with shorter work weeks and duration to maintain safety efforts
* Implement rigorous safety measures due to compressed timelines.
* Conduct frequent safety inspections to mitigate rushed work.
* Ensure workers receive adequate rest breaks to prevent fatigue-related accidents.
* Emphasize proper planning to maintain safety standards despite condensed schedules.
* Prioritize communication to address any safety concerns promptly.
• Maintain safety protocols when the project requires smaller crews or worker-to-supervisor ratios
* Increase supervision to maintain safety oversight.
* Provide additional training to supervisors on safety protocols.
* Implement clear communication channels between workers and supervisors.
* Ensure adequate resources for smaller crews to handle tasks efficiently.
* Regularly assess and adjust worker-to-supervisor ratios based on project needs and safety requirements.
• Ensure the safety of workers who have transferred from other projects to perform the project work
* Ensure that transferred workers receive site-specific safety training and orientation.
* Verify that the training and qualifications of transferred workers match project requirements.
* Provide refresher training if necessary to align with project hazards.
* Monitor the adaptation of transferred workers to project-specific safety protocols.
* Encourage open communication between transferred workers and project management regarding safety concerns.
RS160-1 takeaway summary
(2). Owner's Role in Construction Safety (RS190-1)
• Set contractual safety requirements
* Specify safety personnel: Require the contractor to assign at least one full-time safety representative to the project.
* Approve safety personnel: Obtain resumes of key safety personnel for owner approval.
* Mandate training: Ensure that all workers involved in the project receive specified minimum training.
* Obtain contractor’s safety plan: Require the contractor to submit a comprehensive site-specific safety plan.
* Obtain CEO endorsement: Require a safety policy signed by the contractor's CEO.
• Carefully select contractors
* Evaluate past performance: Review Total Recordable Incident Rate (TRIR) on previous projects.
* Assess safety staff qualifications: Evaluate the qualifications and experience of the contractor's safety staff.
* Review project management team: Assess the qualifications and commitment to safety of the contractor's project management team.
* Examine safety program: Evaluate the overall quality and effectiveness of the contractor's safety program.
* Include stringent safety requirements in contracts: Incorporate specific safety requirements in contracts to emphasize the owner's commitment to safety.
• Become involved proactively in the safety practices of projects
* Set safety expectations: Establish clear safety objectives from the project outset, including zero-injury goals.
* Emphasize safety program: Impose stringent requirements on contractor safety programs, emphasizing emergency plans, daily job safety analyses, and substance abuse programs.
* Monitor safety metrics: Regularly track near-miss rates, safety inspection records, and injury statistics to maintain a proactive stance on safety.
* Include contractor injuries: Maintain records of contractor injuries alongside project safety statistics to foster accountability and improve safety performance.
* Implement safety recognition: Institute behavior-oriented safety recognition programs and contribute funds to incentivize safe practices among workers.
• Establish and fund a safety recognition program
* Define program objectives: Clearly outline the goals and objectives of the safety recognition program, focusing on incentivizing safe behavior and promoting a positive safety culture.
* Allocate budget: Allocate sufficient funds to support the implementation and operation of the safety recognition program, ensuring resources are available for rewards and incentives.
* Promote participation: Encourage active participation from all project stakeholders, including workers, supervisors, and management, to maximize the effectiveness of the program.
* Evaluate and adjust: Regularly assess the effectiveness of the safety recognition program through feedback and performance metrics, and making adjustments as needed to enhance its impact on safety outcomes.
• Participate actively in safety training and orientation and verify workers’ comprehension of the training
* Conduct comprehensive training: Deliver thorough safety training and orientation sessions covering all relevant topics and hazards to ensure worker preparedness.
* Verify worker understanding: Administer tests or quizzes post-training to confirm workers’ comprehension and to reinforce key safety protocols.
* Provide refresher courses: Offer periodic refresher training to reinforce safety knowledge and address emerging hazards.
• Assign an onsite full-time safety representative
* Designate a dedicated representative: Appoint a full-time safety representative to oversee on-site safety protocols and ensure compliance with established standards.
* Facilitate communication: Foster open lines of communication between the safety representative, project team, and subcontractors to address safety concerns promptly.
* Enforce safety policies: Ensure the safety representative actively enforces safety rules and procedures to maintain a secure work environment.
RS190-1 takeaway summary
(3). Design for Safety (RS101-1)
• Reduce worker exposure to falls from elevation and being struck by falling objects
* Design components for prefabrication in the shop to reduce worker exposure to falls from elevation and being struck by falling objects.
* Facilitate prefabrication of components on the ground.
* Ensure components can be erected in place as complete assemblies.
• Eliminate the need to connect special guardrail or lifeline connections to facilitate worker safety
* Design steel columns with holes in the web at 21 inches above floor level.
* Add holes in the web at 42 inches above floor level.
* Provide support locations for guardrails and lifelines at these heights.
• Eliminate falls due to unexpected vibrations, misalignment, and/or unexpected loads
* Design beam-to-column double connections for continual support during connection.
* Add a beam seat to support beams during the connection process.
* Include an extra bolt hole for additional support.
* Incorporate other redundant connection points for stability.
• Prevent fall hazards by simplifying the work area for workers
* Minimize the number of offsets in a building plan.
* Ensure offsets are a consistent size.
* Make offsets as large as possible.
• Monitor overhead power lines that are in service during construction
* Allow adequate clearance between the structure and overhead power lines.
* Bury existing power lines around the project.
* Disconnect existing power lines around the project.
* Reroute power lines around the project before construction begins.
• Tool: Design for Construction Safety ToolBox (prompt hazard consideration, offer suggestions, and maintain records)
* Prompt hazard consideration: Identify potential construction hazards across phases like layout, sitework, and structural components to preemptively enhance safety.
* Offer actionable suggestions: Provide best-practice design recommendations for specific safety concerns, such as stable walkways, clear access points, and safety features for elevated structures​.
* Conduct record-keeping for accountability: Maintain a log of safety measures and suggestions that can be applied to aid tracking and verification for future assessments and compliance.
* Optimize planning phases: Integrate safety considerations early in project planning and design to prevent costly modifications later and to streamline construction processes.
* Enhance site safety features: Design components like guardrails, secure scaffolding points, and marked hazards for better control of safety risks throughout construction​.
RS101-1 takeaway summary
(4). Measuring Safety Performance with Active Safety Leading Indicators (RS284-1)
• Implement passive safety strategies before construction begins to set up the project for success
* Develop a pre-construction safety plan.
* Conduct thorough risk assessments for the project site.
* Implement site-specific safety protocols.
* Provide comprehensive safety training for all workers.
* Establish clear communication channels for safety concerns.
* Ensure availability and proper use of personal protective equipment (PPE).
* Regularly inspect and maintain safety equipment and facilities.
• Implement active safety-related practices that can be measured during the construction phase and can trigger positive responses
* Establish a robust system for monitoring leading safety indicators.
* Regularly review safety performance metrics and reports.
* Implement incentives for achieving safety targets.
* Provide resources for immediate corrective actions.
* Encourage open communication channels for safety-related feedback.
* Conduct periodic safety assessments and adjust strategies accordingly.
• Tool: Implementing Active Leading Indicators, Version 1.1 (define leading indicators, establish performance monitoring, enable continuous improvement)
* Define leading indicators as proactive metrics predicting safety outcomes, contrasting them with lagging indicators focused on past incidents.
* Outline a continuous improvement program for active leading indicators, emphasizing steps like selection, metric definition, implementation, and performance evaluation.
* Emphasize the importance of engaging responsible parties, particularly champions, for the successful adoption and consistent implementation of safety programs.
* Stress the need for timely data analysis, recommending prompt action on deviations to maintain effective safety monitoring.
* Advocate publicizing performance metrics to reinforce safety culture and celebrate success to encourage ongoing engagement.
RS284-1 takeaway summary
(5). Using Near Miss Reporting to Enhance Safety Performance (RS301-1)
• Communicate to all project personnel the intent and beneﬁts of the near-miss reporting program, the reporting methods, and the expected feedback regarding reported near misses
* Conduct a comprehensive training session for all project personnel highlighting the purpose and advantages of the near miss reporting program.
* Clearly outline the reporting procedures, including who to report to, how to document near misses, and timelines for reporting.
* Establish open channels of communication for feedback on reported near misses, ensuring workers feel heard and valued for their contributions to safety.
* Regularly reinforce the importance of near miss reporting through ongoing communication and updates during project meetings.
* Provide examples of successful near miss reporting instances to illustrate the program's effectiveness and encourage participation.
• Earn support from all levels of management, including the owner and contractor
* Implement a clear communication strategy to ensure all levels of management understand the importance of the near miss program.
* Allocate sufficient resources for the implementation and maintenance of the near miss reporting program.
* Provide regular training sessions to educate all project personnel about the near miss reporting process and its benefits.
* Foster a culture of transparency and trust where workers feel safe to report near misses without fear of reprisal.
• Obtain the resources necessary to implement and manage the near-miss reporting program
* Allocate sufficient budget specifically designated for implementing and managing the near miss reporting program.
* Provide necessary training and education for all personnel involved in the program.
* Assign dedicated personnel or teams responsible for overseeing and maintaining the program's effectiveness.
* Ensure access to technological resources and tools required for data collection, analysis, and reporting.
• Tool: Using Near Miss Reporting to Enhance Safety Performance (define near misses, promote safety culture, manage data effectively)
* Define program structure by establishing a blame-free environment to encourage near miss reporting and clarify the concept to all participants.
* Ensure effective roll-out with leadership commitment, training, and clear communication across all levels of the organization.
* Streamline data collection through accessible reporting tools, ensuring easy submission of incidents and addressing language or cultural barriers.
* Analyze data to identify root causes, classify risks, and develop corrective actions for reported near misses.
* Encourage continuous improvement by regularly reviewing program effectiveness, communicating results, and promoting a culture of safety awareness.
RS301-1 takeaway summary
(6). Target Safety Programs (RS216-1)
• Initiation: Identify the motivation for starting a Targeted Safety Program
* Assess accident reports and safety data to identify frequent or severe safety issues.
* Solicit input from employees and managers to understand their safety concerns and suggestions.
* Consider the potential benefits of the program, such as reduced injuries and lower insurance costs.
* Determine the most critical safety issues to address first based on risk assessment.
* Ensure the program's objectives align with the overall business strategy and values.
• Benchmark: Establish benchmarks to assess the safety program
* Define clear metrics to measure safety performance improvements.
* Establish baseline data for current incident rates and safety practices.
* Set specific, quantifiable targets for safety improvement.
* Compare performance against industry standards and best practices.
* Schedule regular reviews to monitor progress towards established benchmarks.
• Champion: Appoint a champion to lead the program
* Select a leader with a strong commitment to safety and leadership skills.
* Empower the champion with the authority to implement changes and allocate resources.
* Provide the champion with ongoing training and support in safety management.
* Ensure the champion communicates effectively with all levels of the organization.
* Regularly evaluate the champion's performance in driving the safety program.
• Development: Systematically plan the program's development
* Conduct a thorough risk assessment to identify all potential hazards.
* Collaborate with stakeholders to gather input and ensure comprehensive coverage.
* Develop clear, achievable goals and objectives for the safety program.
* Create detailed protocols and procedures that address identified risks.
* Plan training sessions to educate employees about new safety measures.
• Implementation: Effectively communicate changes to workers
* Distribute comprehensive training materials to all employees.
* Organize interactive workshops to demonstrate new safety practices.
* Utilize clear, consistent messaging across all communication channels.
* Engage team leaders to champion changes on the construction sites.
* Schedule regular feedback sessions to address concerns and adjust strategies.
• Monitoring and Inspecting for Compliance: Regularly monitor and inspect program compliance
* Schedule routine inspections to ensure adherence to safety protocols.
* Implement regular audits to assess compliance and effectiveness.
* Utilize technology for real-time monitoring of safety practices.
* Train supervisors to perform daily compliance checks.
* Review and analyze inspection data to identify trends and areas for improvement.
• Corrective Action: Establish clear corrective actions for noncompliance
* Define specific consequences for non-compliance with company policies.
* Develop a clear escalation process for repeated safety violations.
* Designate a team to handle investigations of non-compliance issues.
* Provide retraining sessions for employees who violate safety protocols.
* Implement a system for anonymous reporting of safety concerns.
• Measure of Success: Measure program success regularly
* Track reduction in incident rates compared to baseline data.
* Conduct employee surveys to gauge satisfaction and awareness of safety measures.
* Analyze audit results to evaluate compliance improvements.
* Review training completion and effectiveness rates.
* Assess the responsiveness of the corrective action system.
• Success Recognition: Recognize and publicize program successes
* Highlight successful outcomes and improvements in company newsletters and meetings.
* Award certificates or bonuses to teams that achieve safety milestones.
* Host appreciation events to celebrate program achievements.
* Publish case studies on successful safety interventions within the organization.
* Share positive safety statistics and stories on internal and external platforms.
• Tool: Targeted Safety Programs (enhance safety protocols, streamline hazard mitigation, optimize project efficiency)
* Identify and address specific construction hazards through tailored Target Safety Programs to achieve a zero-incident objective.
* Implement a structured, nine-step (golden nuggets bullets above) Target Safety Program Template to guide hazard-specific program development and execution.
* Conduct surveys and case studies to explore program initiation, development, and success metrics for reducing construction-related injuries.
* Involve workers and management in safety programs to foster proactive hazard identification and risk mitigation.
* Recommend adopting the Targeted Safety Program template across projects to improve safety outcomes and achieve zero-injury goals.
RS216-1 takeaway summary
(7). Using Precursor Analysis to Prevent Low-Frequency High-Impact Events, Including Fatalities (RS321-1)
• Assess worksite conditions
* Conduct regular onsite observations and interviews to assess work conditions.
* Utilize a structured approach to identify potential hazards and precursors to high-impact, low-frequency (HILF) events.
* Meticulously document the assessment findings to track trends and patterns over time.
* Involve experienced project staff in the assessment process for accurate identification of leading conditions.- Conduct regular onsite observations and interviews to assess work conditions.
• Identify the presence of precursors and quantify them in a structured and methodical manner
* Implement onsite observations and interviews to assess 16 highly effective precursors.
* 16 precursors can be grouped into four principal components: Poor Work Planning, Productivity Safety Stressors, Vulnerability to High Energy, and Outside Safety Influences
* Quantitatively assess precursors to assign an overall score indicating the potential for a HILF event.
* Incorporate precursor analysis into safety management protocols.
• Predict and prevent the potential for a fatal or disabling event
* Assess high-energy conditions to identify work situations with energy levels above 1,500 ft-lb, which increase injury severity risk.
* Identify precursors by analyzing detectable conditions or actions that signal an elevated risk of a HILF event.
* Apply a structured scorecard to systematically evaluate 16 critical precursors, assessing potential risk before work begins.
* Initiate corrective actions when precursor assessments exceed safe thresholds (precursor scores ≥ 4.), stopping work to prevent possible HILF events.
* Use statistical modeling to objectively predict HILF event likelihood, supplementing expert intuition with reliable data-driven tools.
• Tool: Guide to Precursor Analysis for Construction Fatalities
* Develop a rollout strategy for introducing precursor analysis tools to construction projects.
* Design training modules to educate industry practitioners on using the tool effectively.
* Integrate precursor analysis into existing safety protocols and project management processes.
* Establish mechanisms for collecting feedback and iterating on the tool based on user experiences and emerging data.
* Create templates for documenting analysis results and generating actionable reports for stakeholders.
RS321-1 takeaway summary
(8). Safety Performance through Operational Excellence (RS317-1)
• Emphasize owner’s role in safety performance
* Set clear safety expectations for all project stakeholders.
* Establish a safety culture by prioritizing safety in all project aspects.
* Monitor and enforce safety objectives throughout the project lifecycle.
* Lead by example to emphasize the importance of safety.
* Provide resources and support to ensure safety measures are implemented effectively.
• Organize a safe worksite
* Establish clear guidelines for worksite organization.
* Allocate resources for implementing the 5S (Toyota production system) methodology.
* Encourage collaboration between contractors to maintain organization standards.
* Conduct regular inspections to ensure compliance with organization protocols.
* Foster a culture of cleanliness and organization among all stakeholders.
• Establish just and fair practices and procedures with regard to safety protocol adherence
* Establish a just culture that prioritizes accountability and learning from failures.
* Implement procedures to differentiate between unintentional errors and intentional violations.
* Encourage reporting of incidents by fostering a trusting environment without fear of reprisal.
* Use incidents as learning opportunities to improve systems and prevent future failures.
• Implement strategic safety communication
* Develop a comprehensive safety communication strategy.
* Identify key safety messages to be communicated.
* Utilize multiple channels for consistent safety communication.
* Ensure clear, concise, and regular safety communication to all stakeholders.
* Solicit feedback and encourage open dialogue regarding safety concerns and improvements.
• Foster shared values, beliefs, and assumptions regarding safety issues
* Foster a culture that values safety as a core belief.
* Communicate and reinforce shared values through all levels of the organization.
* Encourage open dialogue to address differences in values and assumptions.
* Lead by example to demonstrate commitment to shared values.
* Align organizational policies and procedures with shared beliefs for consistency.
• Reinforce transformational leadership
* Foster a culture of transformational leadership by leading by example.
* Reinvent the organization's culture to prioritize safety and operational excellence.
* Communicate clear values and desired behaviors to all levels of the organization.
* Encourage innovation and continuous improvement in safety practices.
* Provide support and resources for leadership development programs.
• Assess human performance
* Establish a systematic approach to influence human behavior and performance effectively.
* Provide training programs to enhance human performance in safety-critical tasks.
* Implement processes for performance analysis, cause analysis, and intervention selection.
* Ensure equipment and environments are designed to accommodate human abilities and limitations.
* Foster a culture that values continuous improvement in human performance.
• Establish learning organization
* Foster a culture that encourages continuous learning and adaptation.
* Implement formal processes for sharing lessons learned and best practices.
* Encourage open communication channels for workers to share insights and feedback.
* Provide resources and support for training and development initiatives.
* Embrace a mindset of experimentation and innovation to drive improvement.
• Enhance risk awareness, management, and tolerance to improve safety
* Develop a comprehensive risk management plan for the construction project.
* Identify and analyze potential risks associated with the project.
* Implement measures to mitigate identified risks.
* Establish clear protocols for managing risks as they arise during project execution.
* Ensure that all stakeholders understand and adhere to risk management protocols.
• Promote safety training and competence
* Establish comprehensive training programs for all employees.
* Identify necessary safety competencies for each role.
* Regularly assess employee competence and provide additional training as needed.
* Ensure all new hires receive safety training before starting work.
* Promote a culture of continuous learning and skill development with regard to safety protocols
• Deploy subcontractor management to ensure workplace safety
* Establish clear safety requirements and expectations for subcontractors.
* Vet subcontractors based on their safety records and capabilities.
* Provide necessary resources and support to ensure subcontractors adhere to safety protocols.
* Regularly monitor subcontractor performance and provide feedback on safety practices.
* Encourage open communication and collaboration between subcontractors and project teams.
• Encourage employee engagement in safety programs
* Establish a workplace culture that values and encourages employee contributions.
* Implement mechanisms for employees to provide feedback and suggestions.
* Recognize and reward employee engagement and safety initiatives.
* Provide opportunities for safety skill development and career advancement.
* Foster open communication channels between management and employees.
• Promote a safety recognition and reward system
* Establish a comprehensive recognition and reward program for safety achievements.
* Define specific behaviors and performance metrics to be rewarded.
* Ensure rewards are given promptly and fairly to encourage desired safety behaviors.
* Regularly review and update the recognition and reward program based on feedback and performance data.
RS317-1 takeaway summary
(9). Zero Accident Techniques: Implementation Elements (SD-86)
• Conduct pre-project/pre-task planning to ensure workplace safety
* Define and communicate clear safety goals to all project stakeholders.
* Assign dedicated safety personnel for oversight and compliance.
* Conduct comprehensive hazard analysis to identify potential risks.
* Review and integrate subcontractor safety plans and requirements.
* Ensure that all the necessary safety equipment and training are in place before work begins.
• Implement safety orientation and training
* Conduct a comprehensive worksite safety orientation session.
* Involve owner in the safety orientation.
* Provide detailed safety policies and procedures.
* Explain all project-specific information and regulations.
* Schedule and conduct additional periodic formal safety training sessions.
• Provide a written safety incentive program
* Define and document cents per hour incentives for workers.
* Implement spot cash incentives for immediate recognition.
* Award milestone cash incentives for achieving specific safety goals.
* Provide end-of-project incentives to all eligible workers.
• Promote an alcohol and substance abuse program (ASAP)
* Conduct pre-hire screening for alcohol and drug use.
* Implement random alcohol and drug screening.
* Conduct post-accident screening for all employees.
* Perform regular inspections for contraband.
* Require all project contractors to have ASAPs​.
• Deploy accident/incident investigations.
* Promptly investigate all recordable incidents, first aid cases, and near misses.
* Report all incidents to home office.
* Investigate accidents without injuries.
* Establish a project accident review team for all incidents.
* Report project work exposure hours and safety statistics to the home office.
• Tool: Zero Injury Techniques
* Identify five high-impact techniques (golden nuggets bullets above) essential for achieving zero-injury performance in construction.
* Emphasize safety excellence through pre-project planning, orientation, incentives, substance control, and incident investigation.
* Highlight zero-injury feasibility across various project sizes and labor types.
* Emphasize that quality of effort is more important than time spent in implementing safety measures.
* Adopt a "Zero Injury" philosophy, with senior management setting clear expectations and responsibilities.
• Tool: Zero Injury Economics
* Conduct a comprehensive assessment of current safety protocols and workplace hazards.
* Implement robust training programs to ensure all workers are equipped with the necessary safety knowledge and skills.
* Establish clear communication channels for reporting hazards and near-misses promptly.
* Enforce strict adherence to safety regulations and best practices through consistent monitoring and enforcement measures.
* Continuously evaluate and improve safety procedures based on feedback and data analysis.
* Foster a culture of safety and accountability among all employees, emphasizing the importance of injury prevention at all levels of the organization.
• Tool: Construction Safety Self-Assessment Process
* Conduct initial assessment: Evaluate existing safety measures against identified techniques.
* Identify weaknesses: Determine areas lacking significant safety techniques.
* Develop an improvement plan: Outline specific actions to enhance safety performance.
* Implement changes: Integrate new safety measures into project practices.
* Monitor progress: Regularly review safety performance and adjust strategies as needed.
SD-86 takeaway summary
(10). Strategies for HSE Hazard Recognition (RS293-1)
• Evaluate the quality of the pre-job safety meeting using the Safety Meeting Quality Metric (SMQM)
* Deploy nine evaluation criteria, including: 1) identify the job; 2) identify basic steps; 3) hazard identification and mitigation; 4) location of discussion; 5) supervisor leadership; 6) crew participation; 7) documentation; 8) job changes; and 9) evaluation
* Define operational levels for each criterion.
* Assess current mature level for each criterion.
* Identify improvement opportunities from higher achievement case descriptions.
* Implement actions to raise performance to higher levels.
• Deploy the tool, System for Augmented Virtuality Safety (SAVES)
* Provide a risk-free, high-fidelity virtual environment to enhance engagement in safety performance.
* Engage workers through serious gaming and avatar control.
* Identify hazards and associated energy sources in work scenarios.
* Offer immediate and automatic feedback on performance.
* Facilitate small group usage for enhanced engagement and discussion.
• Implement Hazard Identification and Transmission (HIT) Board.
* Use a 36-inch × 36-inch board with magnetic visual-cue display components for hazard identification.
* Review energy sources on the board during pre-task safety planning to identify potential hazards.
* Use the HIT board to communicate additional hazards in real time as work progresses.
* Display permits, Job Safety Analysis (JSAs), and other essential documents in transparent plastic folders on the board.
* Integrate the HIT board into existing work processes for ease of use and enhanced safety.
• Tool: Improving Hazard Recognition: Training, Planning, and Execution Strategies to Enhance Safety Performance
* Initiate training sessions for SAVES, emphasizing game theory and augmented reality in the context of safety.
* Implement the SMQM by incorporating maturity model assessments into pre-job safety meetings.
* Establish HIT boards for visual hazard communication at construction sites.
* Secure management buy-in for deploying these strategies effectively.
* Ensure safety prerequisites are met before implementing each strategy.
* Monitor each strategy’s effectiveness through predefined metrics.
* Continuously integrate feedback for safety protocol improvement.
* Acknowledge limitations and adapt strategies as necessary.
RS293-1 takeaway summary
Note on B2: Definition: The prefeasibility phase is a ‘first look’ to see if the project is worth pursuing. It is the initial stage of evaluating a potential project idea, where a preliminary assessment is conducted to determine if the project is likely to be viable based on high-level factors, such as site conditions, costs, market demand, and potential environmental impacts, before committing to more detailed design and analysis.
Note on C2: Definition: The feasibility phase serves as a preliminary assessment to determine whether or not a proposed project should move forward. Detailed analysis is conducted to determine whether the project is viable and practical to undertake. Factors such as technical feasibility, economic viability, legal compliance, and environmental impacts are considered before full construction begins. PDRI 1 (550-800) can be used to align team/planners with project objectives, ensure good communications, and highlight stakeholders’ expectations.
Note on D2: Definition: The concept phase (also known as the conceptual design or schematic design phase) of a construction project is where ideas are developed into a viable project. PDRI 2 (450-600) can be used to align project objectives and stakeholders’ needs, identify high-priority deliverables, help eliminate late project surprises, and facilitate communication for the project team.
Note on E2: Definition: The detailed scope phase is the project planning stage where the project's scope is thoroughly defined, which includes a breakdown of all deliverables, tasks, specifications, timelines, and responsibilities. This phase provides a comprehensive understanding of the projects and ensures clarity for all parties involved, thereby minimizing the risk of scope creep. PDRI 3 (150-250) can be used to ensure the alignment of project objectives and needs, verify that the scope is aligned with original project goals, confirm that the detailed scope is ready for review, and identify any gaps.
Note on F2: Definition: The detailed design component of this phase involves completing the detailed design and issuing approved project documents. The procurement component of this phase usually beings with identifying project needs, specifying requirements, and then selecting contractors and suppliers, followed by negotiating prices and finally awarding contracts.
Note on G2: Definition: The construction phase is when the structure is being built on-site as per the design plans. This phase involves both mobilization and construction. Mobilization is the initial preparatory stage where a contractor gathers and organizes the personnel, equipment, materials, and resources at the construction site, which sets up all the necessary components to begin active construction work on the project. Mobilization also includes establishing site offices, securing permits, setting up safety protocols, and coordinating deliveries prior to the start of any major construction activities. Construction is the active period where the physical building process takes place. It encompasses all activities, including site preparation, building erection, installation of systems, and finishing work.
Note on H2: Definition: The commissioning component of this phase is the process of ensuring that a building or industrial plant, systems, and components are designed, installed, tested, operated, and maintained as intended. It is a quality-driven process that focuses on verifying and documenting the building and its systems. The start-up component of this phase is where necessary chemicals treatments are introduced, and the system is brought online for performance testing. The system is then turned over to the permanent operations organization.
Note on I2: Definition: The turnover phase is the final stage of a project where the completed building is systematically transferred from the construction team to the building's operations and maintenance team. This phase includes the physical handover of the structure and the transfer of all necessary documentation and knowledge for the proper operation and maintenance of all the building systems.
Note on J2: Definition: The operate facility phase is when the building is being used for its intended purpose. This phase begins after construction is complete and the building is occupied. It continues until the building is no longer in use or is repurposed.
Note on A3: The golden nuggets are organized by project phases. Owners can follow the golden nuggets in its current format. For contractors, the relevant guidance will depend on the chosen project delivery method. For instance, if your project follows a Design-Bid-Build approach, focus on the golden nuggets covering phases from Construction through Turnover. This targeted approach ensures that you access the insights most applicable to your role and responsibilities throughout the project lifecycle.
Note on A9: Work packaging is a method of organizing and defining the scope of work by breaking down the project into manageable tasks, or work packages, for execution. Work packaging is an application of the management principle that a whole can best be managed by breaking it into manageable parts and then assigning responsibility for the detailed management of each level and element. Overall, work packaging provides structure for the efficient integration of engineering, procurement, construction, and startup as well as cost, schedule, and materials control.
Note on A67: Advanced work packaging (AWP) is the overall process flow of all the separate work packages. It is a planned, executable process that encompasses all the work for an engineering, procurement, and construction (EPC) project, beginning with the initial planning and continuing through the detailed design process and construction execution. AWP provides the framework for productive and progressive construction and presumes the existence of a construction execution plan. AWP emphasizes the collaboration of various project stakeholders (engineering, procurement, construction) from the outset of the project to ensure comprehensive planning and execution. It aligns EPC activities by defining and sequencing work packages early in the project. This alignment ensures that all necessary resources and information are available when needed, thereby enhancing project performance and predictability. This research provides a model execution process and detailed recommendations for effective work packaging that can be incorporated into current execution practices, from project definition through construction and turnover. Implementation guidance is provided through assessment tools, templates and checklists, functional role descriptions, elaboration of existing project processes on the AWP interface, and recommendations for contractual requirements also are included. The benefits of this product include improved productivity and predictability of cost and schedule.
Note on A137: This study guides practitioners as they work to adopt or mature their AWP program to gain the benefits from successful implementation. This work contributes to the AWP body of knowledge by providing the following: • Guidance to owners and early implementers. • Guidance to project stakeholders for AWP execution per discipline. • Enterprise-level considerations for AWP implementation. • Supporting evidence of AWP benefits with regard to early planning and execution, and changes during engineering observed through an industry survey. This work consists of seven self-contained modules: (1) Enterprise Guide, (2) AWP Review and Owner’s Guide, (3) Preliminary Planning and Design, (4) Detailed Engineering, (5) Construction Execution, (6) Commissioning and Startup, and (7) Procurement.
Note on A185: This study produced the first project definition rating index (PDRI) for industrial projects. This study also developed the Alignment Thermometer that analyzes the impact of the alignment of business, project management, and operations personnel of owner companies as well as the alignment between owners and contractors. Alignment is the process of incorporating distinct priorities and requirements into a uniform set of project objectives that meet the business needs for the proposed facility. The Alignment Thermometer includes ten critical alignment factors during pre-project planning that show a positive correlation with project success.
Note on A218: Front end planning is often considered the single most important and valuable process in the capital project life cycle. Also known by such terms as pre-project planning and front end loading, it represents the critical underpinning to any capital project. It is focused on a strong, early link between the business or mission need, project strategy, scope, cost, and schedule and maintaining that link throughout the project life cycle. Front end planning mainly covers three sub-phases: 1) Feasibility, 2) Concept, and 3) Detailed Scope. The research team found that upfront investment is required, but the resulting savings are more than worth the investment. The team also developed the following critical “rules” of front end planning: • Develop and consistently follow a defined front end planning process. • Ensure adequate scope definition prior to moving forward with design and construction. • Use front end planning tools. • Define existing conditions thoroughly. • Select the proper contracting strategy early. • Align the project team, including key stakeholders. • Build the project team, including owner stakeholders and consultants. • Include involvement from both owners and contractors. • Staff critical project scoping and design areas with capable and experienced personnel. • Identify and understand risks of new project types, technologies, or locations. • Address labor force skill and availability during planning. • Provide leadership at all levels for the front end planning process, including executive and project, owner and contractor. Projects teams and organizations that break these “rules” will pay the price in terms of disappointing results.
Note on A252: This study investigated alignment for construction success and identified three areas for improvement: (1) project execution planning (as a basis for alignment in the field), (2) project procedures (to ensure effective execution), and (3) supplier engagement (to increase the likelihood of successful execution). The data collected for each of these three areas served to identify many opportunities for improvement. For example, the project execution planning data indicated broad agreement on which elements should be included in plans to increase the likelihood of successful field execution. The findings also indicated that these elements are not fully included in execution planning documents on a routine basis. Similarly, although companies include aspects of alignment in project procedures, they commonly fail to consider alignment in fundamental areas such as team building, information dissemination, and continuity across phases. The RT-310 study also identified opportunities for increased engagement of suppliers in project planning and shortfalls in common practices (e.g., inadequate scope descriptions and unclear requests for supplier information in Requests for Quotations and Purchase Orders). Overall, the results indicate that the industry has difficulty in accomplishing basic alignment with common practices, from front-end planning through construction. Collectively, the research suggests a need for a ‘back to basics’ review of provisions for alignment throughout the project life cycle. General recommendations include that organizations should review their internal procedures and consult Implementation Resource (IR) 310-2, Effective Project Alignment for Construction Success. In short, RT-310 concludes that ‘alignment doesn’t just happen’ and recommends that, for construction success, the industry should revisit and reinvest in its provisions for alignment.
Note on A280: Benchmarking is the systematic process of measuring an organization’s performance against both its own internal project portfolio and industry peers to determine best practices that, when adapted and utilized, lead to superior performance by improving capital efficiency throughout the total project life cycle, including operations and maintenance. The CII Performance Assessment Program measures project performance and monitors the use of CII Best Practices for both small and large capital projects and for small maintenance projects. Project metrics that are input into CII’s Data Warehouse (DW) system are calculated and assessed. The DW provides both quantitative and qualitative data for an inclusive deep dive into ways that project data can directly affect project performance across the organization. Once an organization’s project is entered into the DW, its performance can immediately be compared to similar projects in the industry. The DW is a world-class benchmarking and research platform that includes the following features: • Project assessment and comparisons of a variety of metrics, such as cost, schedule, safety, changes, and rework • Customized industry-specific benchmarking to enable enhanced, focused performance assessment • The ability to assess a project’s performance, team dynamics, and organizational relationships during execution to identify real-time improvement opportunities via the 10-step benchmarking program. The benchmarking process includes the following 10 steps: 1. Obtain organizational commitment to the benchmark as a basis for improvement. 2. Identify a Benchmarking Associate. 3. Attend the CII’s Data Warehouse training. 4. Identify project managers for benchmarking and improvement. 5. Determine levels of use; i.e., what should be benchmarked and to what extent? 6. Input project data during execution. 7. Finalize and submit a project questionnaire by phase or at project close-out. 8. Generate project and/or organization reports. 9. Repeat Steps 5 through 8 as part of a continuous improvement program. 10. Engage with the Data Analytics Community for Business Advancement.
Note on A335: This report provides a summary of the breakthrough approach that CII has developed to benchmark engineering and construction productivity. CII has instituted a secure and robust online system to help users benchmark their productivity— streamlining each step of the process, from data entry to report generation. Preliminary analyses have been presented here to illustrate the great potential uses of the productivity database and to help users better understand productivity benchmarking. The CII productivity benchmarking program gives users the ability to benchmark productivity and, most importantly, it allows them to drive improvement in their work processes. It does this in the following ways: 1) It assists companies/projects in setting project objectives for future assessment through the data mining tool. 2) It helps benchmarking participants identify productivity problems on their projects through the key reports. 3) It provides data analyses to help benchmarking participants understand the relationship between their work processes and productivity. Ultimately, through benchmarking, companies/projects can implement best practices and change their work processes to improve engineering and construction productivity. Overall, the CII productivity benchmarking team will continue to promote the participation of productivity benchmarking and to enlarge the database. The team is now able to refine the metrics to accommodate non-industrial projects if participants from building or infrastructure sectors think it is necessary.
Note on A360: Change management is an organization’s process for incorporating a balanced change culture that recognizes, plans, and evaluates project changes in order to manage them effectively. These changes include those related to scope, error, design development, estimate adjustments, schedule adjustments, and changed conditions, either elective or required. This research concluded that a significant correlation exists between the percentage of change on a project and labor productivity in terms of design, engineering, and construction. The decline in overall productivity due to an environment of excessive change can alter the cost/benefit evaluation of potential changes and should be taken into account in project decision-making. Project management should track the expected amount of change over time to assist decision-makers with timing/scheduling and/or the organization of change implementation. The analysis of the projects submitted for this study also shows that projects have a diminishing ability to recover lost time and costs in their later stages. This effect is expressed in a probability profile. A normalized contingency draw-down curve for the projects submitted suggests that many changes occur late in the project life cycle. Analysis of the data indicates that the timing of the construction start does have an effect on the amount of change in the engineering phase and in the total cost of changes, but that the effect on construction change is negligible. This research also examined the amount of change experienced on projects of different types and with varying contracting strategies. The conclusion drawn is that organizations should analyze and retain project data as well as provide trend information that general management can use as benchmarks to monitor project performance.
Note on A417: Constructability is the optimal use of construction knowledge and experience in the planning, design, procurement, and field operations phases to achieve overall project objectives. Companies with formal constructability programs will likely experience cost-effective construction on their projects due in part to good teamwork and communications. To achieve maximum benefits, the constructability program should be introduced early in the project and continued throughout the design and construction phases. Commitment to constructability is the responsibility of the entire team; however, the owner is the driving force behind the success of the program. Companies should assess their current constructability program, identify barriers, eliminate barriers, and propose methods for overcoming barriers to constructability and evaluate desirable barrier breakers. Most knowledgeable industry professionals agree that constructability is key to project success. Savings associated with effective constructability programs represent a 10:1 return on the owner’s investment in constructability.
Note on A456: Dispute resolution techniques include various methods to prevent and resolve disputes. The most valuable methods are those that prevent or resolve disputes as early as possible at the project level under the control of those directly involved. Three main underlying causes of construction disputes are: • Project uncertainty that stems from pre-existing conditions, outside forces, and/or complexity that may result in changes beyond the parties’ expectations and control. • Problems in the contracting process, such as imperfect contracts, incomplete scope definition, unrealistic expectations with regard to cost or completion dates, and poor performance in executing the work. • Personal issues that result from poor interpersonal skills, poor communication, lack of responsiveness, and unethical or opportunistic behavior. If these causes are not addressed, disagreements could result that may escalate into litigation. This escalating process will involve more people, additional time, and higher costs. However, much can be done during the pre-construction engineering stage to minimize and avoid disputes. Specifics include engagement in: • Competent engineering and documentation • Constructability analysis • Realistic risk allocation • Dispute resolution clauses • Partnering • Incentive programs Dispute resolution techniques include: • Step negotiations • Standing neutral Conflict resolution techniques include seeking the following: • Advisory opinion • Fact-based mediation • A mini-trial • Non-binding arbitration • Binding arbitration • Private judgement
Note on A512: Front-end planning is often considered the single most important and valuable process in a capital project life cycle. Also known by such terms as pre-project planning and front-end loading, front-end planning represents the critical underpinning to any capital project. It is focused on a strong, early link among the business or mission need, project strategy, scope, cost, and schedule, and maintaining that link throughout the project life cycle. Front-end planning mainly covers three subphases: feasibility, concept, and detailed scope. Upfront investment is required for front-end planning, but the resultant savings are more than worth the investment. The critical steps for front-end planning are as follows: • Develop and consistently follow a defined front-end planning process. • Ensure adequate scope definition prior to moving forward with design and construction. • Use front-end planning tools. • Define existing conditions thoroughly. • Select the proper contracting strategy early. • Align the project team, including key stakeholders. • Build the project team, including owner stakeholders and consultants. • Involve both owners and contractors. • Staff critical project scoping and design areas with capable and experienced personnel. • Identify and understand risks of new project types, technologies, and/or locations. • Address labor force skill and availability during planning. • Provide leadership at all levels for the front-end planning process, including executive and project leadership as well as owner and contractor leadership.
Note on A568: RT-113 produced the first project definition rating index (PDRI) for industrial projects and the Alignment Thermometer. The PDRI is a weighted index that is based on industry best practices. It allows users to measure the level of scope definition and to compare that level to anticipated project success. The PDRI consists of 70 elements in a weighted checklist format. The weighted score of a project can range up to 1000 points, with a lower score being better than a higher score. Based on analysis of 40 projects, projects that scored lower than 200 (out of 1000 total points) were significantly more successful than those that scored higher than 200.
Note on A604: Effective communications are essential to the successful completion of engineering, procurement, and construction (EPC) projects. However, effective communications would be of little benefit to the industry without a reasonable means of measurement. This research investigated ways to measure the effectiveness of project communications and, based on the findings, developed Implementation Resource 105-2, Compass: Communications Project Assessment Tool. This tool was designed to enable project managers to assess project team communications during the execution phases of an EPC project. The tool targets three project groups: project management, engineering, and construction. Project teams can realize significant benefits by using the Compass diagnostic tool. Most importantly, project communications effectiveness can now be both measured and monitored, and problem areas can be identified. Benchmarked scores, which are included in the Compass tool for comparison purposes, are based upon a significant number of CII member company responses. Compass gives project teams the opportunity to take advantage of this research while minimizing the administrative burden often associated with such tools.
Note on A635: The requirements for the successful implementation of CII practices change as an organization’s implementation experience increases. Although the fundamentals of implementation remain constant over time, the specific concerns of an organization will change according to the scope of its implementation efforts and its experience with implementing new practices. This research examined an organization’s experience with CII practices as an indicator of needed changes for its implementation efforts over time. Based on survey data, the research team developed the Experience Reference Index (ERI) as a detailed extension of the CII Implementation Planning Model. The ERI recognizes that an organization’s implementation concerns will change over time. Specifically, the ERI addresses five key elements that affect implementation success: (1) characteristics of the Implementation Champion, (2) resource requirements, (3) implementation plan focus, (4) senior leadership requirements, and (5) organizational scope. Each of these key elements has different focal points depending on the level of experience and the geographic deployment of the organization. Implementers can use the ERI to supplement the development of their implementation plan and to ensure that the appropriate focal points are addressed based on the organization’s level of implementation experience. The results of the background survey suggest that implementation concerns change as organizations become more engaged in the implementation of CII practices. For example, due to enhanced engagement with CII practices, the following outcomes can be realized: • Experienced implementers place a greater emphasis on obtaining communications assistance to convey the implementation message to their organization. • Experienced implementers understand the value of the link between the Implementation Champion and the network of experts in the organization. • Experienced implementers consider the geographic deployment of their organization to be a primary indicator of the focal points that the organization should consider. Minimal differences were evident between contractors and owners among the population surveyed in terms of their experience-based needs and their perspectives regarding the primary factors for implementation success. IR 246-2 provides a 10-stage model to systematically implement new implementation practices. Stage 1: Conduct needs analysis. Stage 2: Establish management buy-in. Stage 3: Establish steps. Stage 4: Adapt a matrix. Stage 5: Develop a plan. Stage 6: Communicate the plan. Stage 7: Perform a change audit. Stage 8: Implement tasks/plan. Stage 9: Perform step evaluations. Stage 10: Establish Benchmark.
Note on A675: This research effort developed the CII Knowledge Implementation Index (CKII) as a method to quantify the level of organizational implementation status. The study found a significant and positive relationship between the CKII values and project performance as measured based on various performance variables. Among the conclusions drawn, implementation generally has significant management support and corporate commitment, but the resources, self-auditing processes, and measurement of business results are lacking. In general, CII organizations are implementing many CII Best Practices, but there is room for improvement. Policy implications of the study are discussed, including a path forward to better organizational implementation.
Note on A714: Continuous improvement is the essential component of long-term success. Whether viewed as innovation, progress, or competitive edge, the introduction of new ideas creates a sustainable advantage for engineering, procurement, and construction (EPC) organizations. However, to achieve success, organizations must recognize that introducing new ideas requires the stimulation of interest and curiosity within the organization. Maintaining this motivation throughout the process of implementing innovations is critical to propelling continuous improvement. The ongoing challenge for organizations is to inspire, foster, and expand the passion for innovation and new practices throughout this process. Having conducted a literature search, survey, structured interviews, and a series of case studies, the research team found empirical evidence of a gap between the initial step of establishing a vision for new practices and the overall implementation process. The findings culminated in the development of two implementation resources: (1) Implementation Strategy (IS) 31-2, The Implementation Process Action Tool: Igniting the Passion and Imagination of an Organization to Introduce Positive Change, which is a guide that provides a qualitative and a quantitative foundation for moving from vision to action, and (2) IS 31-3, The Vision to Action Hot List, a laminated reference for motivating executive management to consider new ideas and then act on them. The journey across the vision-to-action gap requires organizations to take the following distinct steps: • Prepare to cross. Focus on management buy-in and development of the appropriate vision for implementation. • Get on the bridge. Establish metrics and statements of necessity to ensure the organization’s understanding of reasons that the implementation is needed and how it will be evaluated. • Start the journey. Ensure that a team is in place to guide the implementation process and to gather resources to support the implementation. • Check the supports. Determine whether the appropriate cultural, managerial, and technical supports are in place for successful implementation. • Conduct the main crossing. Ensure that the organization has a defined plan and roadmap for completing the implementation effort. • Address the barriers. Determine whether the implementation will encounter common barriers and if the team is prepared to address these barriers. • Exit to action. Ensure that the organization can communicate its action, how it will build on this action, and reasons that the new practice is important to the organization.
Note on A771: A lesson learned is knowledge gained from experience, successful or otherwise, for the purpose of improving future performance. A lessons learned program (LLP) comprises the people, processes, and tools that support an organization’s collection, analysis, and implementation of validated lessons learned. The ultimate goal of this program is to add value to the organization by promoting the communication of information. Both owners and contractors can benefit from an LLP. The captured lessons learned will be focused in different areas based on the business needs of the organization. The tenets of success in developing or managing an LLP include the following considerations: • Leadership, top-level and tactical, is probably the most important prerequisite for the success of an LLP. • Organizations should become ‘teaching’ organizations, rather than organizations that only collect or learn from the past in an ad hoc or passive manner. • Organizations should adopt an active implementation strategy for ensuring that lessons learned are used. • Although technology is important in developing and using an LLP, the importance of the organizational culture should not be underestimated. • The quality of lessons learned is more important than the quantity of lessons learned in the database. This research effort developed a Lessons Learned Maturity Model Matrix to assess an organization’s current LLP based on seven characteristics: 1. Leadership 2. Lesson collection 3. Lesson analysis 4. Lesson implementation 5. Resources 6. Maintenance and improvement 7. Culture This model matrix allows an organization to understand its current status and to plan improvements.
Note on A820: This research describes a systematic approach to communicate and visualize advanced work packaging (AWP) ‘digital threads’ that are provided to stakeholders across a capital project supply chain. The seven digital threads with supply chain applications are project schedule, procurement, site materials, structural detailing, steel fabrication, pipe detailing, and pipe fabrication. The research team developed the following products: • A digital thread map associated with supply chain applications. • The Material Responsibility Matrix (MRM) (an Excel-based tool and user manual) to facilitate information sharing across the supply chain. These products enable companies to increase supply chain visibility and incorporate stakeholders for effective supply chain decision-making. The MRM tool and its user manual encourage and facilitate information sharing across a capital project supply chain and promote the use of the AWP ‘digital threads’ concept to better visualize supply chain elements.
Note on A841: Planning and communications are probably the two most important elements of any effective materials management system. The responsibilities for all areas of the project need to be clearly defined early in the project. Further, the owner needs to relay specific project characteristics or constraints that may alter the scope or cost of the project’s materials management effort (e.g., restricted lay-down areas, schedule compression and changes, cash flow requirements, and design changes). The contractor then needs to communicate the exact materials procedures to implement on the project.
Note on A873: This research paper mainly aims to assist owners and contractors (engineering and construction) in using modern materials management systems and techniques which have been proven to be successful. Construction materials management has made major improvements, and indications are that continued advancements will be made through the automation of the many repetitive functions, the ability to communicate information about materials worldwide, and the use of other cost-effective measures. Materials functions must have visibility in the organization and individuals assigned to materials activities must be properly trained, motivated, and recognized for their contributions. With these advancements, materials management can provide better tools to the workforce, improve cost-effectiveness, and have a significant impact on the ability of the U.S. construction industry to compete in both the domestic and the international marketplace. The CII’s Project Materials Management Handbook is a comprehensive guide to improve materials management. Below is a brief list of the Handbook’s recommendations. Readers are encouraged to consult the Handbook’s specific chapters for details. • Ensure that quality materials are on hand when and where required. • Obtain the best value for purchased materials. • Provide efficient, low-cost transport, security, and storage of materials within construction sites. • Reduce surplus to the lowest level possible.
Note on A915: Given the increasing size, variety, and complexity of global projects, materials management must maintain and expand its role in the early phases of capital project planning. Recommendations include the following: • Conduct comprehensive market studies early to identify cost-effective sources of equipment and materials, considering logistics complexity. • Integrate sustainability considerations into project planning to meet owners' requirements and to develop contractors' capabilities in the area of sustainability. • Streamline IT system interfaces by influencing selection and integration during pre-project planning and ensuring continuous improvement through training programs. • Proactively address quality issues in global sourcing by importing materials from qualified suppliers or developing the local supply base before a project begins. Core function for Materials Management Process: • Materials requirements planning • Project acquisition strategies • Purchasing and subcontracting • Expediting • Supplier quality management • Transportation and logistics • Site materials management • Planning for operations and maintenance turnover Support function for Materials Management Process: • Corporate strategy • Personnel and organization • IT systems • Materials Requirements Planning
Note on A1029: This study developed IR 300-2, Late Deliverable Risk Catalog (LDRC), to understand late deliverables and their impacts. The LDRC presents a set of lessons learned about late deliverables along with recommendations to prevent the most common types of late deliverables and suggestions for incorporating the LDRC into company processes. A greater understanding of the true impacts of late deliverables to the construction site will ensure the following improvements: • Personnel that represent all project functions that support construction (e.g., engineering, procurement, startup, contracting, logistics, and business management) will understand that their schedule performance is of critical importance to the overall project success. • Delivery dates to the construction site will be regularly monitored and proactively maintained by the appropriate parties. • Construction personnel will take proactive and more comprehensive actions to mitigate the full range of risks that may arise when a late delivery arrives at the job site. Companies are encouraged to integrate and improve the LDRC in the following ways: • Add new categories of late deliverables that are particular to a company or industry sector. • Complete additional company-specific case studies by adding projects that are affected by late deliverables. • Include costs of specific impacts in the database, either in dollar values or percentages. • Add a new field to the LDRC that identifies a company contact person who has previously dealt with a specific situation. • Incorporate solutions to common problems or company-specific lessons learned that relate to the impacts of certain late deliverables, suppliers, contractors, or subcontractors.
Note on A1081: The threat of counterfeit, fraudulent, and suspect items (CFSI) in the capital projects industry is pervasive, complex, and dynamic and is a critical risk to materials quality. The following major conclusions were drawn from this study: • The construction industry has a critical lack of awareness and training concerning CFSI. • Industry detection of CFSI occurs predominantly after installation, which increases the risk of safety, cost, and schedule impacts. • Industry efforts towards CFSI assessment and mitigation are isolated and inconsistent. • No clear industry method currently is available for reporting CFSI threats. • Construction organizations are reluctant to share data due to perceived legal and market consequences. • The need for collaborative action to address CFSI risk is compounded by perceived internal and external challenges. To mitigate the risk of CFSI, a project team should be able to identify where the counterfeit materials enter the supply chain, prioritize the mitigation actions with a focus on areas with higher levels of criticality, implement risk mitigation strategies, and assess the risk before and after the application of the mitigation strategies. By collecting data on CFSI risk and sharing lessons learned via the mitigating process, project teams will improve the effectiveness of their CFSI mitigation strategies. This research tools provides the following: • Reference resources and training materials • CFSI qualitative risk rating approach • A catalog of risk mitigation strategies • A standardized format/tool for an internal, company-level database
Note on A1115: Companies that report more robust supplier quality work processes and systems tend to capture defects earlier in the manufacturing life cycle rather than later in the field. This early screening has a direct impact on the cost and schedule of each project. The earlier the inspection, the greater the probability that defects will be found and addressed early. Moreover, working with suppliers in the early stages of projects can help ensure that all parties understand product requirements and are prepared to deliver on them. Although rework due to supplier defects will never be totally eliminated, investing in early alignment and inspection of critical equipment and materials will pay dividends in successful project completion.
Note on A1163: Materials are the life blood of projects. If materials cannot flow smoothly from specification to fabrication to site installation, then project performance will be poor. All too often, even well planned and well executed projects face disruptions to materials flow. Indeed, late or missing materials are a common occurrence on almost every project. Site materials management is an extension of the material management processes, procedures, and systems that are initiated in the earliest stages of a project. Site materials management includes receiving, inspecting, warehousing, and controlling the release of incoming materials. The purpose of management programs is to ensure that the right quantities of the right materials and equipment are anticipated as early as possible to ensure that these components are provided at the right time to the project’s construction forces in a cost-effective manner. With proper planning and true system integration, material shortages can be identified a priori. This early notice ensures that required materials are acquired in sufficient time to support the needs of construction forces and surplus inventory is kept to a minimum. RT-344 Part I explores the visibility of materials in the project supply chain and offers recommendations to improve materials tracking and support effective decision-making. The research identified a large number of visibility items and enablers that are associated with common decisions and concluded that project supply chain performance will improve if projects and firms pay closer attention to visibility. Part II explores opportunities for improvement that may stem from improved visibility. A particular focus of this second part of the study is the cost of carrying stocks of materials to the project. Knowing cost information can help teams make better decisions about achieving the right balance of materials as a buffer against the risk of shortages. A better understanding of costs is a prerequisite for improving policies or optimizing behavior. Collectively, these findings make the case that significant opportunities are available for reducing inventory holding costs while making the material on hand more effective. RT-344 Part II also presents metrics for excess inventory and a framework for decision-making to augment project planning processes. Radio frequency identification (RFID) technology for access control is used to help define the high-level needs and benefits of implementing an access control solution for construction sites. This approach not only satisfies project management requirements at the site but also serves to meet the client’s expectations regarding the reliable control of personnel site access and quantifies the daily attendance of the site workforce. RFID is especially helpful when a company experiences an increase in the size of the project and workforce. An overall recommendation from RT-344 is that firms and projects should immediately take steps to improve visibility on their projects. Overall, a three-pronged approach is needed to improve firms and projects: self-assess, close the gaps, and align with other efforts. The following steps should be taken in the planning phase as the basis for a decision framework: 1. Estimate direct holding costs. 2. Establish the applicable cost of capital for the project. 3. Explore alternatives for holding inventory. 4. Decide on the planned inventory based on costs and risks.
Note on A1209: An ideal materials management system will be able to communicate between IT systems and integrate the digital threads of all the materials needed for the project. The principal recommendations from this study are as follows: • Improve the quality of orders to suppliers, which is a major industry opportunity and low-hanging fruit, by (1) reviewing and improving requests for quotations (RFQs) and the order process, (2) ensuring that RFQs and purchase orders are clear in scope and that priorities and information (data required) are delineated, and (3) considering the use of RFID technology when preparing RFQs. • Involve suppliers early in the project, ideally in the front-end engineering design (FEED) stage, to better leverage their capabilities and ensure timely deliveries. • Improve information systems to ensure the smooth exchange of information across the supply chain, thereby supporting better and more timely decisions.
Note on A1252: Partnering is an integral factor in the successful delivery of a construction project. Partnering’s value to the industry lies in its ability to utilize the inherent strengths of all partners for the common and individual good, to speed project completion while observing high standards of safety and integrity, and to strengthen the competitive edge of all partners by producing products that meet customers’ needs. Partnering is a construction industry process that strengthens both projects and partners, tightens schedules, safeguards quality, and enhances each partner’s competitive edge. This study describes a partnering implementation process model, CII Implementation Resource 102-2 (Partnering ToolKit) that presents five implementation phases for partnering, each with its own objectives and key success factors. These five phases are (1) owner’s internal alignment, (2) partner selection, (3) partnering relationship(s), (4) project alignment, and (5) work process alignment. Benchmarks are provided that verify the benefits that are achievable through partnering in the areas of cost, schedule, safety, quality, claims, and others.
Note on A1298: This study compared an idealized all-modular work process for industrial projects with current, largely stick-built work processes and identified key high-value practices that are in need of change. The findings led to the development of the Industrial Modularization: Five Solutions Elements tool (IR283-2), which consists of the following five distinct elements that industry leaders and project managers should consider carefully to achieve higher levels of modularization: • A business case process • Execution plan differences • Critical success factors • A standardization strategy • Modularization maximization enablers
Note on A1341: This study investigated the appropriate time for modularization planning and ways that a company should develop a business case to support its modularization decision. The study’s recommendations are as follows: • Standardize modular terminologies and definitions. • Understand modularization barriers and barrier breakers. • Follow recommended modularization timing points. Three tools were created to support the use of modularization for industrial projects: • Modularization Business Case Analysis Tool for Opportunity Framing. This tool helps users make informed decisions by reviewing key modularization drivers and considerations during early project phases. This tool also helps users understand the enablers and barriers related to modularization and addresses new drivers, such as environmental, social, and governance (ESG). • Modularization Business Case Analysis Tool for Assessment and Selection. This tool identifies the optimal extent of modularization for projects during the later Project Assessment and Selection phase. It provides comprehensive analysis of costs and savings that are linked to various percentages of modularization to help users identify the optimal level that will result in successful project completion. • ESG Modularization Assessment Tool. This tool helps users determine an appropriate modularization strategy that aligns with ESG principles and practices during the Project Assessment and Selection phase. It generates impact scores by assessing the potential impact of the modularization strategy on numerous ESG factors.
Note on A1384: Project success depends not only on pre-project planning and well managed project execution, but also on a successful start-up. The importance of start-up planning is more critical than ever, as pressure to increase profits by reducing costs and demands for shorter project cycle times creates challenges for the business environment. A Start-up Planning Model (IR121-2) was developed in this study to help plan start-up in a thorough, effective, and efficient manner. The model provides details of 45 startup planning activities organized by project phase. Some of the keys to successful start-up identified by the Start-up Planning Model include: • Management commitment • Start-up objectives • A start-up execution plan • ‘Quality gates’ or time-outs for analysis
Note on A1416: Commissioning and start-up (CSU) is the critical last phase of a capital project before the facility is placed into operation to meet commercial objectives. Unfortunately, many project teams do not effectively plan and implement the activities needed to ensure a successful CSU phase. This study identified 16 critical success factors (CSFs), characterized by their specific required actions and positions within the project phase sequence, and firmly demonstrates the need for early CSU planning. Additionally, the study developed a set of unique indicators of CSF achievement to determine whether the CSFs have been implemented effectively. Additional analysis was conducted to determine reasons that certain CSFs are implemented less frequently than others and thus should require the particular attention of project teams. Further, CSFs can complement or be integrated with steps in the CII Planning for start-up best practice model, described in CII IR121-2. CII IR312-2 identified five technologies that add value to the efforts of CSU teams and project stakeholders: (1) smart piping and instrumentation diagrams, (2) building information modeling design/3D models, (3) asset data management/wireless instrumentation, (4) simulation-based virtual commissioning and operator training, and (5) a completion management system. The final product is a user-friendly CSU Critical Success Factor Implementation Checklist, a tool for developing project execution and CSU plans and for managing CSU efforts through to project completion. The checklist is found in IR312-2, Achieving Success in the commissioning and start-up of Capital Projects, which is the second part of a two-volume publication that offers implementation guidance and case study summaries.
Note on A1527: Several prior studies indicate that commissioning failures are too common in frequency and extremely costly in impact. The business case for action is clear, yet the transitions between construction/pre-commissioning/commissioning/startup/close-out (abbreviated CCSU in this publication, emphasizing the construction component) remain challenging for many reasons. This is primarily due to contractual separations and the multitude of organizational interfaces and handoffs during CCSU. Achieving project and commissioning success requires a solid understanding of the CCSU activities to be undertaken and the associated responsibility assignments. CII created Research Team 333 (RT-333), Transition Management between Construction Completion, Pre-Commissioning, Commissioning, and Start-Up, and challenged it to provide answers to the essential question: How can the industry establish or clarify the accountabilities and responsibilities among construction completion, pre-commissioning, commissioning, and operations functions? In response to this essential question, RT-333 developed a 17-step implementation process that integrates the key findings from all three CII research teams that have addressed commissioning: RS121-1, Planning for Start-Up; RS312-1, Best Practices for Commissioning and Start-Up; and SP333-1 itself. The SP333-1 research developed four important deliverables: 1. CCSU Activity Flowchart – a flowchart of 124 CCSU activities, organized by relevant project phase and four thematic categories. 2. CCSU Responsible, Accountable, Consulted, and Informed (RACI) Matrix – builds on the CCSU activity flowchart, defining whether each activity’s manager is Responsible, is Accountable, should be Consulted, or should be Informed. 3. CCSU Hot Spots – insight into the challenges of CCSU transitions by identifying 20 “hot spots” 4. Heidelberg Spar Case Study – an illustrative case study to demonstrate the substantial value that results from timely and effective mitigation efforts for targeted (i.e., project-specific) CCSU hot spots.
Note on A1588: The International Project Risk Assessment (IPRA) tool allows a project team to identify and gauge the level of risk on projects prior to and throughout the project’s life cycle. By design, IPRA focuses specifically on issues unique to international ventures. A significant feature of IPRA is its flexibility to fit the needs of almost any individual project. IPRA elements that are not applicable to a specific project can be ignored, thus eliminating them from further assessment and mitigation actions. For international construction projects, the following risk response is proposed as a critical phase of the overarching risk management process. The following actions can help the project team effectively implement IPRA: • Organize and formalize a risk management process and keep it as simple as possible. • Begin early to optimize effectiveness. • Maintain a broad perspective to obtain the diversified input required. • Undertake adequate pre-project planning, analysis, and engineering. • Partner with owner and contractor management. • Recognize that certain projects are more prone to risk than others and that experience in a jurisdiction is important. • Recognize that risk documentation is critical.
Note on A1640: This study identified a process that organizations can use to implement more advanced project risk management approaches, including probabilistic analysis. This process comprises three levels, each of which offers clear benefits: risk identification, deterministic analysis, and probabilistic analysis. Although more information and confidence are gained as the analysis progresses through the levels, these benefits need to be weighed against the incrementally increasing costs of successfully completing each level. Due to their extra expense, probabilistic approaches are not warranted for every project. To help organizations select the appropriate level for their projects, this study explains the benefits, results, requirements, and limitations of each level.
Note on A1674: Front-end planning is often considered the single most important and valuable process in a capital project life cycle. Also known by such terms as pre-project planning and front-end loading, front-end planning represents the critical underpinning to any capital project. It is focused on a strong, early link among the business or mission need, project strategy, scope, cost, and schedule, and maintaining that link throughout the project life cycle. Front-end planning mainly covers three subphases: feasibility, concept, and detailed scope. Upfront investment is required for front-end planning, but the resultant savings are more than worth the investment. The critical steps of front-end planning are as follows: • Develop and consistently follow a defined front-end planning process. • Ensure adequate scope definition prior to moving forward with design and construction. • Use front-end planning tools. • Define existing conditions thoroughly. • Select the proper contracting strategy early. • Align the project team, including key stakeholders. • Build the project team, including owner, stakeholders, and consultants. • Involve both owners and contractors. • Staff critical project scoping and design areas with capable and experienced personnel. • Identify and understand risks of new project types, technologies, or locations. • Address labor force skill and availability during planning. • Provide leadership at all levels for the front-end planning process, including executive and project leadership as well as owner and contractor leadership.
Note on A1697: The research team developed the “Two-Party Risk Assessment and Allocation Model” that encourages contracting parties to compromise during the risk allocation process. It is designed to assess and allocate risk before project execution so that risk management efforts are minimized. The model is important because it facilitates involvement from any two contracting parties early in a project and helps in appropriately allocating each particular risk to the party that is best equipped to handle it.
Note on A1763: This study provides a three-step process for comparing an organization’s present quality management system (QMS) against those that other organizations report as highly effective. This process allows users to determine methods to improve their systems. Step 1: Define and develop your QMS. • Understand QMS requirements. • Document the process governed by the QMS. • Gain management commitment to implementing the QMS. Step 2: Assess the maturity of your QMS. • Assess compliance to ISO 9001. • Measure compliance using QMS elements, criteria, and attributes against organizational objectives. • Evaluate QMS maturity. Step 3: Improve your QMS. • Understand the key drivers of implementation and improvement. • Understand the practices of organizations that report having an effective QMS. • Identify and act upon improvement opportunities.
Note on A1816: This study developed a uniform definition and method of measurement for engineering/design deliverable quality that is usable by project owners, managers, quality managers, contractor design managers, and discipline leads. High quality design deliverables are complete, correct, and timely. The study identified 11 common detailed design deliverables that often suffer from quality problems and developed a completeness checklist for each of the 11 problematic deliverables. The study also identified leading indicator metrics that can warn of defect-prone deliverables and developed two assessment tools to assess design deliverable quality and completeness throughout the detailed design process, beginning with front-end engineering design (FEED) validation and continuing through issued-for-construction. These two assessment tools are: • The Design Deliverable Quality Assessment (DDQA) tool that identifies threats to deliverable quality by focusing on leading indicators. • The Completeness of Design Deliverable Checklist (CDDC) that provides a method for the consistent measurement of deliverable completeness. The application of these two tools can help project teams achieve complete, correct, and timely results for the 11 commonly problematic design deliverables. By aligning project expectations and better predicting deliverable completeness, projects should benefit from reduced rework and improved cost and schedule performance.
Note on A1857: This study identified the primary components of a comprehensive process for management and quality error-related costs for construction projects. Although many errors and omissions occur in the scope development process and design, the focus of this research is error reduction efforts at the project execution level and within the construction organization. The research team first looked at methods and techniques that have been effective in implementing safety management and reducing accidents and lost workdays in construction projects. It found that management support and pre-project tasks are similar for both safety and quality-related activities. The difference occurs at the implementation level between planning and field execution. Most importantly, worker involvement is needed to resolve the continuing problem of rework. Specifically, increasing training that targets quality-related issues, identifying quality-related rework problem areas, increasing full-time quality staff, and having field personnel analyze pre-task quality efforts all contribute to less rework. Taking a cue from the CII’s research on safety, the research team urges the industry to take a similar look at rework. In addition to zero accidents, the industry needs to adopt the goal of making zero rework a reality. The resultant low percentages of rework could pay for error reduction efforts.
Note on A1910: This study created a quality metric that can be used to effectively measure, categorize, and benchmark quality performance across the project delivery process. The capital facilities delivery industry recognizes the need to measure quality, but its organizations and projects utilize different execution models, which makes it difficult to standardize quality metrics. This lack of standardization leads to variability in performance assessment, which can negatively affect an organization’s bottom line. Project quality activities can be viewed as a series of planned activities, unplanned outcomes of planned activities (unplanned outcomes), and unplanned events, arranged in ascending order commensurate with the severity of their consequences. In this study, worsening potential outcomes were structured into a Quality Pyramid (similar to the Safety Pyramid). Severity levels of unplanned events were used to define a metric called the quality performance rate (QPR). The QPR enables comparative assessments of project quality performance in the areas of front-end engineering, engineering and design, procurement, construction, construction management, and the commissioning and start-up of new or modified facilities. The metric uses currently available data and is scalable, simple to capture, and sustainable.
Note on A1971: Effective communications are essential to the successful completion of engineering, procurement, and construction (EPC) projects. However, effective communications would be of little benefit to the industry without a reasonable means of measurement. This research investigated ways to measure the effectiveness of project communications and, based on the findings, developed Implementation Resource 105-2, Compass: Communications Project Assessment Tool. This tool was designed to enable project managers to assess project team communications during the execution phases of an EPC project. The tool targets three project groups: project management, engineering, and construction. Project teams can realize significant benefits by using the Compass diagnostic tool. Most importantly, project communications effectiveness can now be both measured and monitored, and problem areas can be identified. Benchmarked scores, which are included in the Compass tool for comparison purposes, are based on a significant number of CII member company survey responses. Compass gives project teams the opportunity to take advantage of this research while minimizing the administrative burden often associated with such tools.
Note on A2005: An effective team-building process can bring significant, not simply marginal, improvements in project execution and results. During the design/construction process, it is not uncommon for an adversarial relationship to develop among the parties involved, usually the project owner, designer, and contractor. This type of relationship is seldom constructive and frequently is the cause of problems. This study examined ways that such an adversarial relationship might be minimized. The team-building process (as opposed to ‘teams’) brings together a diverse group of individuals and seeks to resolve differences, remove roadblocks, and proactively build and develop the group into an aligned, focused, and motivated work team that strives for a common mission and shared goals, objectives, and priorities. The following activities can lead to successful team building: • Use of a consultant who does not have a direct stake in the outcome of the project. • At least one retreat type of group meeting at which the shared goals are delineated and essential decision-making and dispute resolution procedures are developed. • Regular job site meetings of the team (the consultant need not be present). • Follow-up meetings to reinforce concepts and to integrate new members.
Note on A2039: This study produced the first project definition rating index (PDRI) (CII IR113-2) for industrial projects and the Alignment Thermometer. The PDRI is a weighted index that is based on industry best practices. It allows users to measure the level of scope definition and to compare the scope definition to anticipated project success. The PDRI consists of 70 elements in a weighted checklist format. The weighted score of a project can range up to 1000 points, with a lower score being better than a higher score. Based on analysis of 40 projects, projects that scored lower than 200 (out of 1000 total points) were significantly more successful than those that scored higher than 200. Alignment is the process of incorporating all of those distinct priorities and requirements into a uniform set of project objectives that meet the business needs for the proposed facility. Using the developed Alignment Thermometer, the research team analyzed impacts of the alignment among business, project management, and operations personnel of owner companies as well as the alignment between owners and contractors. The team interviewed over 100 industry participants and evaluated 20 capital projects in depth. This effort led to the identification of ten critical alignment issues that were shown to correlate positively with project success and must be addressed during pre-project planning. This work is published in Alignment Thermometer Alignment During Pre-Project Planning (CII IR113-3).
Note on A2076: Ten key topic areas that contribute to improved safety performance are listed below in the order of safety initiative priorities: • Management commitment • Stafﬁng for safety • Pre-project and pre-task planning • Safety education (orientation and specialized training) • Worker involvement • Evaluation and recognition and reward • Subcontractor management • Accident/incident investigation • Drug and alcohol testing • Contract type Related CII research focuses on short duration projects, commonly referred to as shutdowns, turnarounds, or outages, to assess the unique characteristics of these projects, particularly the rapid buildup of the required workforce. In addition to the key topic areas listed above, additional factors that inﬂuence safety performance on short duration projects include: • Transferring workers from other projects to perform the work • Hiring workers a few weeks before the short duration project • Shorter work weeks and project duration • Smaller crews and/or lower worker-to-supervisor ratios • Incentivized contracts
Note on A2170: This study examined the role and inﬂuence of owners in terms of construction safety and focused on the owner’s involvement in safety management as demonstrated through the selection of safe contractors, inclusion of safety requirements in the contract, and active participation in safety during project execution. The overall conclusion is that owners set the tone for safety performance on a project and that improved safety performance is possible through the use of the following speciﬁc owner practices: • Careful selection of safe contractors • Contractual safety requirements • Proactive involvement in project safety practices • Establishment of and funding for a safety recognition program • Active participation in safety training and orientation and verifying personnel’s comprehension of the training • Assigning a full-time safety representative to the construction site • Designing for safety
Note on A2205: Incorporating safety measures in the design phase directly improves safety on the job site, and ultimately leads to lower total installed cost due to fewer dollars spent on mediating hazards and acquiring construction insurance. This study involved accumulating a large number of design suggestions that focus on improving construction worker safety and creating the “Design for Construction Safety ToolBox,” (Toolbox) an interactive computer program to aid in planning and designing facilities. ToolBox allows the user to identify potential safety hazards and offers design suggestions that may be used either to control or to eliminate the hazards. ToolBox allows for both the identified hazards and the design suggestions to be documented in a report format. A project history of construction safety design issues and actions is automatically accumulated and can be easily monitored for completeness of review and status of design decisions.
Note on A2237: Many ﬁrms with world-class safety records have been frustrated by the inability to make step-change improvements in construction safety. The traditional monitoring of lagging indicators of safety performance has not achieved the desired step-change of improvement in construction safety. Many safety professionals believe that the careful selection and implementation of safety leading indicators will yield signiﬁcant improvements in safety practices and performance. This study investigated the potential of these critical project metrics and divided the leading indicators into two types: 1. Passive safety strategies that are implemented before construction begins to set up the project for success. 2. Active safety-related practices or observations that can be measured during the construction phase and can trigger positive responses. The results conﬁrm a strong correlation between the implementation of 10 key passive safety leading indicators and a reduction in the project’s total recordable incident rate (TRIR). The study further identiﬁed 14 promising active safety metrics and offers a process for the successful implementation of an active safety indicator program. Ten key passive safety leading indicators are: 1. Owner review and approval of CM’s and GC’s project safety plan 2. Participation of all contractors and subcontractors in safety meetings 3. Site-specific safety orientation for all managers 4. 100-percent steel-toed boots policy 5. Medical facilities on site 6. First aid log maintained 7. Minimum ratio of safety professionals to workers 8. Worker-to-worker observation program 9. Worker involvement in perception surveys 10. Foremen involved in policy creation and implementation
Note on A2262: This study is relevant to construction industry safety programming and covers leadership commitment, employee engagement, and health, safety, and environmental (HSE) personnel involvement. The necessary steps to implement and sustain an effective near miss reporting program are included as well as electronic reporting tools to implement and maintain the program. Three key points must be emphasized for successful program implementation: 1. A project’s near miss program must receive unwavering support from all levels of management, including the owner and the contractor. 2. This support must include the resources necessary to implement and manage the program. 3. The intent and beneﬁts of the program, the reporting methods, and the expected feedback on a reported near miss must be clearly communicated to all project personnel. Near miss reporting was found to lower the OSHA TRIR, increase communication and trust with regard to safety for construction site personnel, and further enable workers to identify hazardous conditions and unsafe worker behavior.
Note on A2288: The focus of a target safety program can vary depending on the focus (e.g., preventing causes of injuries, such as struck-by injuries or trench cave-in accidents, and preventing injuries to the back, eyes, hands, or feet). Clearly, the focus can vary considerably and is determined largely by the nature of the speciﬁc hazards that appear to be plaguing a particular project. This study examined various target safety programs and identified some common elements that led to their effective development and implementation. If a consistent pattern could be identiﬁed, then a model or template was created by which other target safety programs could be developed and implemented. Target safety programs can and should be employed to help projects achieve zero injuries, regardless of the type of work being performed or company size. Nine steps are needed to implement a target safety program: 1. Identify the motivation for starting the program and initiate the program. 2. Establish benchmarks to assess the program. 3. Appoint a champion who leads the program. 4. Systematically plan the program's development. 5. Communicate changes effectively to workers for implementation. 6. Monitor and inspect program compliance regularly. 7. Establish clear corrective actions for non-compliance. 8. Measure program success regularly. 9. Recognize and publicize program successes.
Note on A2352: This study created a precursor analysis protocol for construction that enables practitioners to: • Assess conditions in a leading fashion. • Identify the presence of precursors and quantify them in a structured and methodical fashion. • Predict and prevent the potential for a fatal or disabling event. This protocol provides guidance for (1) identifying conditions that have the potential to lead to severe or fatal injuries based on the concept of energy, (2) identifying the presence of anomalous conditions (precursors) that precede fatal and disabling events through a strategic discussion with a work crew, and (3) correcting deﬁciencies.
Note on A2378: The CII deﬁnes the term ‘operational excellence’ for construction project safety as “doing the right thing, the right way, every time – even when no one is watching.” Using that guiding philosophy, this study developed a rigorous model for operational excellence in construction project safety. The Operational Excellence model breaks into several layers of detail. The thirteen aggregate-level drivers of safety represent broad categories, several based on the CII’s Zero Accident Techniques that outline policies to improve construction safety. The accompanying assessment tool allows CII members to evaluate safety at the project’s corporate level, project level, and site level. The thirteen categories of drivers of safety are: 1. Owner’s role 2. Worksite organization 3. Just and fair practices and procedures 4. Strategic safety communication 5. Shared values, beliefs, and assumptions 6. Transformational leadership 7. Personnel performance 8. Learning organization 9. Risk awareness, management, and tolerance 10. Training and competence 11. Subcontractor management
Note on A2458: This study investigated ways that owners and contractors can achieve zero accidents for construction projects. The study identified techniques that are successful in achieving zero accidents to convince management of the value of an effective safety program. The overall conclusion confirms that zero lost workday injuries are achievable on large projects. The study’s key conclusions are as follows. • Zero injury can be achieved under a variety of project conditions and situations. • Joint owner and contractor management commitment to zero accidents is a key requisite. • An effective safety program that produces good results must contain a broad base of essential techniques. • Attaining zero injuries is significantly more likely on projects that apply the five High-Impact Zero Injury Techniques: (1) pre-project/pre-task planning for safety, (2) safety orientation and training, (3) a written safety incentive program, (4) an alcohol and substance abuse program, and (5) accident/incident investigations. • Success in eliminating accidents is not guaranteed by the use of the five High-Impact Zero Injury Techniques alone. • Time spent data suggest that quality effort is a vital ingredient in reaching zero injuries.
Note on A2510: Recognizing hazards is the most essential component of the safety management process. Unrecognized health, safety, and environmental (HSE) hazards expose workers to unmitigated risks that can result in catastrophic accidents, injuries, and illnesses. CII research indicates that traditional hazard identiﬁcation methods result in workers citing fewer than 50% of the hazards at their workplace on average, with some data showing identiﬁcation rates as low as 20 percent. This study identiﬁed, developed, and tested three transformative hazard recognition strategies that can signiﬁcantly improve hazard recognition performance. These strategies, each based on practices from psychology and behavioral science, were developed to enhance the hazard recognition ability and performance of workers. Empirical testing of these strategies on active construction projects revealed impressive, statistically signiﬁcant improvements. The three strategies may be implemented independently or in combination with one another to provide a multilayered approach to improving hazard recognition. The strategies are: 1. A pre-job safety meeting quality measurement maturity model. 2. The System for Augmented Virtuality Safety (SAVES) tool. 3. A Hazard Identification and Transmission (HIT) board.

## 1. AWP_FAQs
FAQ 1: What is the primary purpose of Advanced Work Packaging (AWP)?
Answer: AWP aims to align engineering, procurement, and construction processes to improve project control and execution. It breaks down projects into smaller, well-defined work packages, facilitating efficient coordination and constraint-free execution.
Source:
• FR-390
FAQ 2: How does AWP support efficient construction execution?
Answer: AWP integrates planning tools like the Path of Construction (PoC) and ensures constraint-free work fronts by defining clear Construction Work Packages (CWPs) and Installation Work Packages (IWPs). It emphasizes early coordination among stakeholders to address potential issues proactively.
Source:
• RS272-1
• FR-390
FAQ 3: Why is early stakeholder engagement critical in AWP implementation?
Answer: Engaging stakeholders early fosters alignment, accountability, and clarity in roles and responsibilities. It ensures that engineering, procurement, and construction processes are synchronized, reducing delays and enhancing overall project efficiency.
Source:
• RS272-1
• FR-390
FAQ 4: What are the key challenges in adopting AWP mid-project?
Answer: Implementing AWP mid-project can lead to disruptions without adequate preparation, resource allocation, and commitment. Proper planning, training, and stakeholder buy-in are essential to minimize misalignment and inefficiencies during transition.
Source:
• RS272-1
FAQ 5: How does AWP improve materials and resource management?
Answer: AWP ensures timely delivery of materials and resources by aligning procurement timelines with project schedules. It integrates tracking systems with CWPs and IWPs to provide visibility and manage constraints effectively.
Source:
• RS6-1
• FR-390
Back

## 2. Alignment_FAQs
FAQ 1: What are the critical factors to achieving alignment in pre-project planning?
Answer: Critical factors include stakeholder representation, effective leadership, clear priority between cost, schedule, and project features, open communication, and fostering a team culture of trust and shared values. Additionally, sufficient funding, effective teamwork, and the use of planning tools are key.
Source:
• RS113-1
FAQ 2: How can alignment be maintained throughout a project’s lifecycle?
Answer: Alignment can be maintained by establishing consistent execution procedures, fostering team continuity, engaging all stakeholders in key deliverables, and ensuring smooth phase transitions. Tools like alignment checklists and automation can enhance consistency and improve project performance.
Source:
• RS310-1
FAQ 3: What tools are available to measure and improve alignment during pre-project planning?
Answer: The "Alignment Thermometer" is a diagnostic tool used to assess and maintain team alignment. It identifies issues early and offers insights into improving communication and accountability within the project team.
Source:
• RS213-1
FAQ 4: Why is front-end planning critical for effective alignment?
Answer: Front-end planning ensures adequate scope definition, aligns the project team with clear goals, involves key stakeholders early, and establishes roles and responsibilities. These steps prevent misalignments and costly issues during later project phases.
Source:
• RS213-1
FAQ 5: What are the five categories impacting alignment in project management?
Answer: The five categories include execution processes (systems and procedures), company culture (values and environment), information (data and objectives), barriers (obstacles to alignment), and tools (software and checklists).
Source:
• RS213-1
Back

## 3. Benchmarking_FAQs
FAQ 1: What is the importance of obtaining organizational commitment to benchmarking?
Answer: Organizational commitment is critical as it aligns benchmarking efforts with enterprise strategies, ensures adequate resource allocation, and fosters stakeholder support. This process includes scheduling meetings with executive leadership, communicating benefits, and obtaining formal commitment for resources.
Source:
• IR-BMM-2 v2
FAQ 2: How can Benchmarking Associates (BAs) enhance the effectiveness of benchmarking initiatives?
Answer: BAs are pivotal for coordination, requiring appropriate training, access to data, and tools. They integrate benchmarking results into decision-making processes, monitor progress, and support project managers and leadership in aligning practices with organizational goals.
Source:
• IR-BMM-2 v2
FAQ 3: What are the best practices for selecting projects for benchmarking?
Answer: Projects should represent typical organizational work and exclude incomplete or unreliable data. Selecting a mix of projects, rather than only top-performing ones, ensures realistic benchmarks that reflect actual performance and identify areas for improvement.
Source:
• IR-BMM-2 v2
FAQ 4: How does the Data Warehouse system contribute to effective benchmarking?
Answer: The Data Warehouse enables seamless submission and analysis of project data using tools like the Integration Toolkit. It facilitates performance assessments against industry benchmarks and provides insights via metrics for cost, schedule, and productivity comparisons.
Source:
• IR-BMM-2 v2
FAQ 5: How do productivity benchmarks help identify and address project inefficiencies?
Answer: Productivity benchmarks use key reports to identify metrics falling below industry standards. Correlation analyses reveal relationships between work processes and productivity, enabling targeted improvements in low-performing areas.
Source:
• BMM2011-1
Back

## 4. Change Management_FAQs
FAQ 1: How does project change impact productivity in construction and engineering?
Answer: Project changes can reduce productivity by altering the planned scope of work and disrupting workflows. Tracking the overall project change ratio and its impact on engineering and construction productivity is vital. Predictive models can help forecast the productivity impacts of future changes, and strategies like phasing activities or adjusting resources can mitigate these effects.
Source:
• RS43-2
FAQ 2: How can the probability of on-time project completion be analyzed relative to reported progress?
Answer: Analyzing the probability of completing projects on schedule involves reviewing close-out reports and plotting reported progress at milestones (e.g., 25%, 50%, 75% complete) against actual completion dates. Identifying correlations and patterns helps develop strategies to enhance schedule performance, such as improved resource allocation and better change management.
Source:
• RS43-2
FAQ 3: What is the relationship between change work ratio and material efficiency?
Answer: The ratio of total dollars spent on changes to material dollars measures implementation efficiency. Analyzing this metric helps forecast potential impacts on schedules, budgets, and resources, enabling strategies to optimize material use and minimize waste during change implementations.
Source:
• RS43-2
FAQ 4: How does project size and type influence the amount of change experienced?
Answer: Trends in change amounts vary across project sizes (e.g., small, medium, large) and types (e.g., revamp, new construction). Analyzing close-out reports helps identify these patterns, guiding future project planning and risk management by tailoring resource allocation to specific project categories.
Source:
• RS43-2
FAQ 5: What tools and processes are essential for effective change management?
Answer: Effective change management requires establishing an up-front baseline agreement, using classification processes for required vs. elective changes, and ensuring team members consistently use a recording system. Recognition systems and accessible data collection are critical for informed decision-making and continuous improvements.
Source:
• RS43-2
Back

## 5. Constructability_FAQs
FAQ 1: What are the key objectives of implementing constructability?
Answer: The primary objectives of constructability include understanding its concepts and barriers, performing self-assessments, recognizing benefits, and developing an implementation policy to improve project outcomes.
Source:
• RS34-2
FAQ 2: How can an organization establish a corporate constructability program?
Answer: To establish a corporate constructability program, organizations should identify a sponsor or champion, set up a functional support structure with defined procedures, and create a lessons-learned file to guide continuous improvement.
Source:
• RS34-2
FAQ 3: What are the steps for planning constructability implementation at the project level?
Answer: Planning involves developing a dedicated constructability team, addressing project-specific barriers, consulting lessons-learned databases, and integrating constructability procedures into project activities.
Source:
• RS34-2
FAQ 4: Why is documenting lessons learned important in constructability?
Answer: Documenting lessons learned helps capture insights from projects, refine future implementation strategies, and ensure continuous improvement in constructability practices.
Source:
• RS34-2
FAQ 5: What tools and resources are available for implementing constructability?
Answer: The "Constructability Implementation Guide, Second Edition" provides a roadmap with six milestones and 17 tools to evaluate, plan, and implement constructability, addressing barriers and enabling continuous improvement.
Source:
• RS34-2
Back

## 6. Disputes_FAQs
FAQ 1: What are some key strategies for preventing disputes in construction projects?
Answer:
Structured training in negotiation and conflict resolution for project managers.
Establishing formal on-site dispute resolution mechanisms, like Dispute Review Boards (DRBs).
Facilitating early intervention by project sponsors to resolve issues at the project level.
Promoting transparent communication among stakeholders to avoid misunderstandings.
Source:
• RS23-1
FAQ 2: How can claims be managed to prevent them from escalating into disputes?
Answer:
Proactively identifying and resolving potential claims early.
Treating claims as a routine part of project management rather than as adversarial.
Documenting issues thoroughly and consistently for clarity.
Establishing transparent communication channels for reporting and discussing claims.
Source:
• RS23-1
FAQ 3: What tools or models are available to evaluate and manage the potential for disputes?
Answer:
Disputes Review Boards (DRBs) to quickly and efficiently resolve on-site issues.
Disputes Potential Index (DPI) model to assess disputes' likelihood based on variables like project size and complexity.
Applying constructability reviews during design to mitigate risks.
Source:
• RS23-1
FAQ 4: What role do contracts play in dispute prevention and resolution?
Answer:
Integrating dispute prevention clauses to set collaborative expectations.
Focusing on clear and fair risk allocation during preconstruction.
Regularly reviewing contracts to clarify responsibilities and reduce ambiguities.
Source:
• RS23-1
FAQ 5: What are effective methods for resolving disputes when they arise?
Answer:
Implementing fact-based mediation and advisory opinions.
Utilizing non-binding and binding arbitration methods.
Encouraging private judging or mini-trials for expediency.
Maintaining a simple consensual process with minimal formalities.
Source:
• RS23-1
Back

## 7. Front End Planning_FAQs
FAQ 1: What are the key cost elements typically considered during Front End Planning?
Answer: Key cost elements include planning team personnel expenses, conceptual and detailed design costs, consultant fees, environmental permitting costs, project manager/construction manager fees, and licensor fees.
Source:
• RS213-1
FAQ 2: What are the typical activities and outputs of Front End Planning?
Answer: Typical activities and outputs include option analysis, scope definition, life-cycle cost analysis, cost and schedule estimates, site investigation, environmental analysis, process design basis, initial equipment design, space planning, site layout, project execution and procurement plans, architectural renderings, and appropriation submittal packages.
Source:
• RS213-1
FAQ 3: What tools can enhance the Front End Planning process?
Answer: Tools like the Project Definition Rating Index (PDRI) help in scope definition, risk assessment, and progress tracking. The Compass tool improves team communication effectiveness, while resources like the Alignment Thermometer ensure team alignment on project goals.
Source:
• RS213-1
• RS105-1
FAQ 4: How can labor force skill and availability be addressed in Front End Planning?
Answer: Conduct thorough analyses of local labor market conditions, engage contractors and suppliers, develop training programs or recruitment strategies, and incorporate contract clauses addressing labor shortages or surpluses.
Source:
• RS213-1
FAQ 5: Why is leadership critical in the Front End Planning process, and how can it be implemented effectively?
Answer: Leadership ensures alignment, progress, and effective communication. Establishing a dedicated planning team, appointing an executive sponsor, training project managers in best practices, and maintaining clear communication channels with contractors are essential steps.
Source:
• RS213-1
Back

## 8. CII Research Imple_FAQs
FAQ 1: How can organizations effectively communicate and support the implementation of CII research?
Answer: Organizations should develop a comprehensive communication plan, including the use of email, staff meetings, and other existing channels, to share CII-related activities. Collaboration between Implementation Champions (ICs) and networks of experts is essential for consistent messaging and leveraging expert knowledge.
Source:
• RS246-1
FAQ 2: What are the key tools and models for successful CII research implementation?
Answer: Key tools include the Implementation Planning Model, which offers a 10-stage process for systematic implementation, and the Experience Reference Index, which guides organizations through tailored implementation strategies based on experience levels.
Source:
• RS246-1
FAQ 3: How can organizations measure and improve their implementation practices?
Answer: Regular use of benchmarking and metrics, supported by tools like the CII Knowledge Implementation Index, enables organizations to evaluate their practices, identify areas for improvement, and implement proven processes to manage capital projects effectively.
Source:
• RS166-1
FAQ 4: What strategies can organizations use to overcome barriers during implementation?
Answer: To address barriers, organizations should develop contingency plans, foster open communication with stakeholders, and assess cultural, managerial, and technical readiness. Tools like the IMPACT Tool can help identify weaknesses and recommend tailored strategies.
Source:
• IS31-1
FAQ 5: How can geographic and organizational factors influence implementation strategies?
Answer: Geographic deployment can guide the prioritization and customization of implementation approaches. Tailoring strategies to regional characteristics, resources, and regulations ensures effective execution. Monitoring progress across regions allows for adjustments as needed.
Source:
• RS246-1
Back

## 9. LL_FAQs
FAQ 1: What leadership roles are essential for the success of a Lessons Learned Program (LLP)?
Answer: Leadership roles at both top-level and tactical levels are critical. Organizations should establish a clear vision for the LLP, assign a dedicated coordinator or champion, and ensure leadership engagement throughout the process. Regular communication and commitment to resources further enhance the program's success.
Source:
• RS230-1
FAQ 2: How can organizations foster a culture of continuous improvement in relation to lessons learned?
Answer: Organizations can promote a culture of continuous improvement by actively educating employees through formal training programs, integrating lessons into daily operations, encouraging knowledge sharing, and rewarding contributions. Regular reviews and discussions in meetings also help embed a learning mindset.
Source:
• RS230-1
FAQ 3: What strategies ensure the active implementation of lessons learned?
Answer: Active implementation can be ensured by conducting regular reviews during project development meetings, updating internal processes to reflect lessons learned, creating situation-specific training materials, and pushing relevant lessons to the field. Mentorship by experienced personnel reinforces these efforts.
Source:
• RS230-1
FAQ 4: How can the quality of lessons learned be maintained in the database?
Answer: Quality can be ensured by validating lessons through subject matter experts, establishing criteria for inclusion, regularly updating lessons to maintain relevance, and creating actionable, detailed content. A feedback loop should be implemented for users to report on the effectiveness of applied lessons.
Source:
• RS230-1
FAQ 5: How should organizations address cultural differences when implementing lessons learned programs?
Answer: Cultural differences can be addressed by developing a shared vision that involves all departments, encouraging active participation, recognizing and rewarding valuable contributions, and fostering open communication across teams and locations. Tailoring approaches to suit diverse cultural contexts is also key.
Source:
• RS230-1
Back

## 10. Material_FAQs
FAQ 1: What are the key roles and responsibilities in material management during the planning phase of a capital project?
Answer: In the planning phase, clear roles and responsibilities must be defined among stakeholders. Specific stakeholders should be assigned tasks such as material requisition, tracking, and ensuring timely delivery. Scheduling software should be used to capture and analyze core information like package dates, path of construction, and critical milestones to inform Earned Value Progress (EVP) and Construction Work in Progress (CWIP) reporting.
Source:
• FR-TC-03
FAQ 2: How can materials management systems contribute to cost savings and efficiency in construction projects?
Answer: Materials management systems optimize schedules and labor productivity, achieving savings of approximately 6% in project craft labor costs. Implementing these systems requires top management support, streamlined delivery processes, and minimized material surplus through efficient tracking and inventory control. Regular training for all project members ensures the successful application of these systems.
Source:
• RS7-1
FAQ 3: What strategies ensure timely and cost-effective procurement in global supply chain projects?
Answer: Early market studies to identify cost-effective suppliers and logistics planning are crucial. Sustainability considerations, such as ESG metrics, and collaboration with qualified local or global suppliers help align with project goals. Integrating IT systems and continuous monitoring ensure procurement efficiency and mitigate quality risks.
Source:
• RS257-1
FAQ 4: What measures can be taken to mitigate the risks of late material deliveries?
Answer: Proactive tracking and reporting of delivery schedules, coupled with contingency planning, help address risks. Regular communication with suppliers and stakeholders, timely updates on schedule changes, and incorporating lessons from past delays reduce the impacts of late material deliveries. Tools like the Late Deliverable Risk Catalog (LDRC) enhance these efforts.
Source:
• RS300-1
FAQ 5: How can emerging technologies improve materials management in construction projects?
Answer: Emerging technologies like barcoding, electronic data interchange, and integrated software systems enhance materials tracking, reporting, and control. Real-time tracking of materials across work packages and linking material data with scheduling software improves supply chain transparency and efficiency.
Source:
• FR-344
Back

## 11. Partnering_FAQs
FAQ 1: What are the key components of establishing trust in a partnering relationship?
Answer: Establishing trust involves open communication, transparency, and setting clear expectations among all stakeholders. It requires retaining committed personnel, empowering team members to make decisions aligned with partnership goals, and maintaining consistent policies throughout the project.
Source:
• RS102-1
FAQ 2: How can top management support partnering efforts effectively?
Answer: Top management can support partnering by endorsing partnering principles, clearly communicating project objectives, and ensuring alignment with organizational goals. They should also establish dispute resolution mechanisms and align performance measures with business drivers.
Source:
• RS102-1
FAQ 3: Why is it essential to establish win-win objectives in partnering, and how can this be achieved?
Answer: Win-win objectives ensure alignment and mutual benefit for all partners. These can be achieved by developing goals as general objectives, milestones, and success conditions; creating a partnering charter; and establishing incentives such as early completion bonuses, safety achievements, and financial rewards.
Source:
• RS102-1
FAQ 4: What internal barriers might hinder partnering, and how can they be addressed?
Answer: Internal barriers, such as conflicting priorities, unclear organizational goals, and lack of understanding about partnering principles, can hinder success. These can be addressed by reviewing and removing barriers, educating employees about partnering benefits, and aligning policies to organizational goals.
Source:
• RS102-1
FAQ 5: What role does a partnering champion play, and what qualities should they have?
Answer: A partnering champion directs the partnering process, communicates its benefits, and aligns efforts with organizational goals. They should possess authority, knowledge of partnering principles, effective communication skills, and the ability to drive decisions and actions that support the partnership.
Source:
• RS102-1
Back

## 12. Modularization_FAQs
FAQ 1: What is the importance of a modularization business case process in project planning?
Answer: The modularization business case process is critical for evaluating project feasibility and ensuring optimal decision-making. It should be initiated during the Opportunity Framing phase and refined iteratively throughout the project lifecycle. This process factors in all potential benefits, enabling a comprehensive analysis that guides modularization strategy.
Source:
• RS283-1
FAQ 2: What are the key differences in planning and execution between modular and stick-built projects?
Answer: Modular projects require early consideration of module envelope sizes, weights, and fabrication and transportation logistics. Key differences include planning and cost estimating, scoping, design standards, and deliverables, with over 100 unique planning items to address across project phases.
Source:
• RS283-1
FAQ 3: What are the critical success factors (CSFs) for modularization, and why are they challenging?
Answer: CSFs include timely design freeze, cost savings recognition, contractor leadership, vendor involvement, and transport delay avoidance. These factors are challenging due to the need for significant owner resources, early design completion, and robust data for optimization.
Source:
• RS283-1
FAQ 4: How can combining modularization with design standardization maximize project outcomes?
Answer: Integrating modularization with design standardization can create synergies that exceed their individual benefits. This requires developing standardized designs for targeted plant types, refining strategies with vendor collaboration, and aligning with project stage gates.
Source:
• RS283-1
FAQ 5: What tools are available to support decision-making in modularization?
Answer:
Key tools include:
1. Modularization Business Case Analysis Tools: Inform decisions on modularization timing and extent by evaluating cost, schedule, and ESG factors.
2. ESG Modularization Assessment Tool: Assesses environmental, social, and governance impacts to align modularization strategies with ESG principles.
Source:
• FR-396
Back

## 13. Startup_FAQs
FAQ 1: What is the importance of management commitment in startup planning?
Answer: Management commitment is crucial as it ensures alignment of startup objectives with project goals, secures stakeholder buy-in, and drives accountability throughout the planning and execution phases.
Source:
• RS121-1
FAQ 2: How can clear expectations for startup success be established?
Answer: Clear expectations can be set by defining key performance indicators (KPIs), establishing metrics, and developing a comprehensive project charter that outlines objectives, scope, and the overall execution approach.
Source:
• RS121-1
FAQ 3: What role do "quality gates" play in startup planning?
Answer: Quality gates act as checkpoints during the startup planning process, ensuring that activities remain on schedule and align with project objectives. They provide opportunities for analysis and corrective actions to avoid delays.
Source:
• RS121-1
FAQ 4: Why is stakeholder collaboration important during the Commissioning and Startup (CSU) phase?
Answer: Stakeholder collaboration ensures seamless integration and coordination between design, construction, and CSU phases, reducing risks, enhancing safety, and improving project performance.
Source:
• RS312-1
FAQ 5: How do innovative technologies improve CSU outcomes?
Answer: Technologies like smart P&IDs, BIM/3D models, and simulation-based virtual commissioning streamline planning, improve system understanding, and reduce startup time and costs through enhanced collaboration and training.
Source:
• RS312-1
Back

## 14. Risk Management_FAQs
FAQ 1: What are the fundamental steps in organizing a risk management process for projects?
Answer: The key steps include formalizing the risk management process, identifying key stakeholders, developing a comprehensive risk register, establishing clear roles for team members, determining risk tolerance levels, and scheduling regular reviews to update the risk process.
Source:
• RS181-1
FAQ 2: Why is pre-project planning essential in risk assessment?
Answer: Pre-project planning is critical to identify and analyze potential risks early, establish a risk baseline, and engage stakeholders for diversified input. It ensures a strong foundation for the project by analyzing scope, schedule, budget, and resources.
Source:
• RS181-1
FAQ 3: What tools are recommended for probabilistic risk assessment in construction projects?
Answer: Monte Carlo simulations, probabilistic approaches to quantify risks, and customizable risk registers are recommended to estimate potential impacts, visualize scenarios, and improve stakeholder communication.
Source:
• RS280-1
FAQ 4: How can project transitions between phases be effectively managed to minimize risks?
Answer: Effective management requires early alignment meetings, clear documentation of system boundaries and responsibilities, regular reviews of transition plans, and use of tools like RACI matrices to clarify roles.
Source:
• SP333-1
FAQ 5: How can equitable risk allocation benefit construction projects?
Answer: Equitable risk allocation reduces financial strain, ensures risks are assigned to parties most equipped to handle them, and promotes cooperative relationships. Using risk assessment worksheets and decision trees supports fair and logical distribution throughout the project.
Source:
• RS210-1
Back

## 15. Quality_FAQs
FAQ 1: What are the key elements of an effective Quality Management System (QMS)?
Answer: An effective QMS should include leadership support, process management, measurement and analysis, supplier QMS, QMS training, and certification. Leadership commitment, visible guidance, and sufficient resources are critical for successful implementation. Establishing formal training programs and using metrics to measure effectiveness are also essential.
Source:
• RS254-1
FAQ 2: How can quality metrics be used to enhance performance in projects?
Answer: Quality metrics, such as the Quality Performance Rate (QPR), track unplanned events and outcomes to provide actionable insights. The Quality Pyramid framework helps classify and monitor performance, emphasizing continuous improvement. Regular review and benchmarking against industry standards ensure progress and identify improvement areas.
Source:
• RS313-1
FAQ 3: What strategies can be used to reduce rework in construction projects?
Answer: Strategies to reduce rework include management commitment, integrating quality management personnel, conducting quality audits, and using tools like the Zero Field Rework Self-Assessment Checklist. Pre-task planning, constructability reviews, and setting clear goals for zero defects or minimal rework are also recommended.
Source:
• RS203-1
FAQ 4: How can problematic design deliverables be managed effectively?
Answer: Tools like the Design Deliverable Quality Assessment (DDQA) and Completeness of Design Deliverables Checklist (CDDC) help identify and mitigate defects in problematic deliverables. Regular audits, stakeholder collaboration, and integrating these tools into workflows ensure high-quality outcomes.
Source:
• RS320-1
FAQ 5: What role do suppliers and contractors play in Quality Management Systems?
Answer: Suppliers and contractors should align with the organization’s QMS through regular audits, training programs, and adherence to clear metrics. Collaborative efforts to share best practices and a focus on continuous improvement enhance overall quality management.
Source:
• RS254-1
Back

## 16. Team Building_FAQs
FAQ 1: What is the role of communication in effective team building for projects?
Answer: Communication is critical in team building as it ensures information accuracy, timeliness, and understanding, minimizes barriers, and establishes clear procedures. Tools like the Compass assess communication effectiveness, helping address weak areas and track improvements to enhance project success.
Source:
• RS105-1
FAQ 2: How can a consultant contribute to the team building process in construction projects?
Answer: A qualified consultant can facilitate team building by organizing workshops, fostering open communication, resolving conflicts, and monitoring progress to align the process with project objectives. Engaging a consultant early enhances trust and collaboration among stakeholders.
Source:
• RS37-1
FAQ 3: Why is starting team building early in a project important?
Answer: Beginning team building early establishes trust, aligns stakeholders with project goals, and promotes collaboration. Early planning and integration of team building into project activities help maintain momentum and address challenges proactively.
Source:
• RS37-1
FAQ 4: What practices promote a culture of trust and honesty within project teams?
Answer: A culture of trust is fostered through clear communication, transparency in decision-making, active listening, and recognizing honest feedback and contributions. Regular meetings and shared responsibility further enhance team synergy.
Source:
• RS113-1
FAQ 5: How do team-building activities enhance project outcomes?
Answer: Team-building activities improve team cohesion, foster trust, and enhance collaboration. Regular workshops, cross-functional sessions, and recognition of achievements strengthen bonds and align efforts toward shared goals.
Source:
• RS113-1
Back

## 17. Safety_FAQs
FAQ 1: What are the key steps to ensure management commitment to achieving zero accidents?
Answer:
Communicate safety expectations clearly to all stakeholders.
Integrate safety into planning, scheduling, and decision-making.
Review and assess safety performance regularly to implement improvements.
Source:
• RS160-1
FAQ 2: How can subcontractor management contribute to zero-accident techniques?
Answer:
Prequalify subcontractors based on safety performance.
Set clear safety expectations and provide necessary resources.
Monitor compliance and implement sanctions for violations.
Source:
• RS160-1
FAQ 3: What role does safety orientation and training play in preventing accidents?
Answer:
Conduct comprehensive site-specific safety orientation.
Provide detailed safety policies and periodic specialized training.
Assess training effectiveness through feedback and evaluations.
Source:
• RS32-1
FAQ 4: How can contractual safety requirements improve construction safety?
Answer:
Specify full-time safety representatives and safety plans in contracts.
Approve key safety personnel and mandate worker training.
Include safety clauses that incentivize compliance and performance.
Source:
• RS190-1
FAQ 5: What strategies can enhance hazard recognition and prevention during construction?
Answer:
Use tools like the Hazard Identification and Transmission (HIT) Board for real-time hazard updates.
Conduct pre-job safety meetings with established metrics like the Safety Meeting Quality Metric (SMQM).
Employ virtual safety tools like System for Augmented Virtuality Safety (SAVES) for risk-free scenario training.
Source:
• RS293-1
Back