## Introduction
The purpose of this worksheet is to assist project team members in the development of BIM Goals and the selection of BIM Uses based on project and team characteristics.

## Goal Identification
Priority (1-3) | Goal Description | Potential BIM Uses
1- Most Important | Value added objectives

## Goal EXAMPLE
Priority (1-3) | Goal Description | Potential BIM Uses
1- Most Important | Value added objectives
2 | Increase Field Productivity | Design Reviews, 3D Coordination
1 | Increase effectiveness of Design | Design Authoring, Design Reviews, 3D Coordination
3 | Accurate 3D Record Model for FM Team | Record Model, 3D Coordination
3 | Increase effectiveness of Sustainable Goals | Engineering Analysis, LEED Evaluation
2 | Track progress during construction | 4D Modeling
1 | Identify concerns accosiated with phasing on campus | 4D Modeling
3 | Review Design progress | Design Reviews
3 | Quickly Asses cost associated with design changes | Cost Estimation
2 | Eliminate field conflicts | 3D Coordination

## BIM Use Analysis
BIM Use* | Value to Project | Responsible Party | Value to Resp Party | Capability Rating |  |  | Additional Resources / Competencies Required to Implement | Notes | Proceed with Use
| High / Med / Low |  | High / Med / Low | Scale 1-3 (1 = Low) |  |  |  |  | YES / NO / MAYBE
|  |  |  | Resources | Competency | Experience
Maintenance Scheduling
Building Systems Analysis
Record Modeling
Cost Estimation
4D Modeling
Site Utilization Planning
Layout Control & Planning
3D Coordination (Construction)
Engineering Analysis
Site Analysis
Design Reviews
3D Coordination (Design)
Existing Conditions Modeling
Design Authoring
Programming
* Additional BIM Uses as well as information on each Use can be found at http://www.engr.psu.edu/ae/cic/bimex/

## BIM Use EXAMPLE
BIM Use* | Value to Project | Responsible Party | Value to Resp Party | Capability Rating |  |  | Additional Resources / Competencies Required to Implement | Notes | Proceed with Use
| High / Med / Low |  | High / Med / Low | Scale 1-3 (1 = Low) |  |  |  |  | YES / NO / MAYBE
|  |  |  | Resources | Competency | Experience
Record Modeling | HIGH | Contractor | MED | 2 | 2 | 2 | Requires training and software |  | YES
|  | Facility Manager | HIGH | 1 | 2 | 1 | Requires training and software
|  | Designer | MED | 3 | 3 | 3
Cost Estimation | MED | Contractor | HIGH | 2 | 1 | 1 |  |  | NO
4D Modeling | HIGH | Contractor | HIGH | 3 | 2 | 2 | Need training on latest software | High value to owner due to | YES
[7 empty] | Infrastructure needs | phasing complications
Use for Phasing & Construction
3D Coordination (Construction) | HIGH | Contractor | HIGH | 3 | 3 | 3 |  |  | YES
|  | Subcontractors | HIGH | 1 | 3 | 3 | conversion to Digital Fab required | Modeling learning curve possible
|  | Designer | MED | 2 | 3 | 3
Engineering Analysis | HIGH | MEP Engineer | HIGH | 2 | 2 | 2 |  |  | MAYBE
|  | Architect | MED | 2 | 2 | 2
Design Reviews | MED | Arch | LOW | 1 | 2 | 1 |  | Reviews to be from design model | NO
no additioanl detail required
3D Coordination (Design) | HIGH | Architect | HIGH | 2 | 2 | 2 | Coordination software required | Contractor to facilitate Coord. | YES
|  | MEP Engineer | MED | 2 | 2 | 1
|  | Structural Engineer | HIGH | 2 | 2 | 1
Design Authoring | HIGH | Architect | HIGH | 3 | 3 | 3 |  |  | YES
|  | MEP Engineer | MED | 3 | 3 | 3
|  | Structural Engineer | HIGH | 3 | 3 | 3
|  | Civil Engineer | LOW | 2 | 1 | 1 | Large learning curve | Civil not required
Programming | MED | [6 empty] | Planning Phase Complete | NO
* Additional BIM Uses as well as information on each Use can be found at http://www.engr.psu.edu/ae/cic/bimex/