## INTRO
GOAL:
This worksheet was developed to aid the project team to define the information required to implement each BIM Use with maximum efficiency.
Information Exchange (IE) Tab:
The purpose of this section is to define the information needed to produce each BIM Use. Therefore, the responsible party for the use is in charge of gathering the information required, and filling out each category using the defied Model Element Breakdown (which should be customized to fit each project)
Model Definition (MOD) Tab:
The purpose of this section is to produce the progression of the model throughout the lifecycle of the project. The information for this section should be extracted from the IE Tab. Any other information that will be modeled lifecycle of the project should be added here.
Information |  | Responsible Party
A | Accurate Size & Location, include materials and object parameters | ARCH | Architect
|  | CON | Contractor
B | General Size & Location, include parameter data | CE | Civil Engineer
|  | FM | Facility Manager
C | Schematic Size & Location | MEP | MEP Engineer
|  | SE | Structural Engineer
|  | TC | Trade Contractors
Information: This column defines the information and detail required in the model content.
Responsible Party: This column aims to define the responsible parties for the model content of the BIM deliverables. Specifically, the responsible party in this case is the author of the content.

## IE
INFORMATION EXCHANGE (IE)
BIM Use Title |  |  | Programming |  |  | Design Authoring |  |  | Existing Conditions Modeling |  |  | Cost Estimation |  |  | 3D Coordination |  |  | Design Reviews |  |  | 4d Modeling (Phasing) |  |  | Energy Analysis |  |  | Cost Estimation |  |  | 4D Modeling |  |  | Site Utilization Planning |  |  | 3D Coordination |  |  | Construction Systems Design |  |  | Record Modeling
Project Phase |  |  | Planning |  |  | Design |  |  | Design |  |  | Design |  |  | Design |  |  | Design Reviews |  |  | Design |  |  | Design |  |  | Construction |  |  | Construction |  |  | Construction |  |  | Construction |  |  | Construction |  |  | Operations
Time of Exchange (SD, DD, CD, Construction)
Responsible Party (Information Receiver)
Receiver File Format
Application & Version
Model Element Breakdown |  |  | Info | Resp Party | Notes | Info | Resp Party | Notes | Info | Resp Party | Notes | Info | Resp Party | Notes | Info | Resp Party | Notes | Info | Resp Party | Notes | Info | Resp Party | Notes | Info | Resp Party | Notes | Info | Resp Party | Notes | Info | Resp Party | Notes | Info | Resp Party | Notes | Info | Resp Party | Notes | Info | Resp Party | Notes | Info | Resp Party | Notes
A | SUBSTRUCTURE
Foundations
Standard Foundations
Special Foundations
Slab on Grade
Basement Construction
Basement Excavation
Basement Walls
B | SHELL
Superstructure
Floor Construction
Roof Construction
Exterior Enclosure
Exterior Walls
Exterior Windows
Exterior Doors
Roofing
Roof Coverings
Roof Openings
C | INTERIORS
Interior Construction
Partitions
Interior Doors
Fittings
Stairs
Stair Construction
Stair Finishes
Interior Finishes
Wall Finishes
Floor Finishes
Ceiling Finishes
D | SERVICES
Conveying Systems
Elevators & Lifts
Escalators & Moving Walks
Other Conveying Systems
Plumbing
Plumbing Fixtures
Domestic Water Distribution
Sanitary Waste
Rain Water Drainage
Other Plumbing Systems
HVAC
Energy Supply
Heat Generating Systems
Cooling Generating Systems
Distribution Systems
Terminal & Package Units
Controls & Instrumentation
Systems Testing & Balancing
Other HVAC Systems & Equipment
Fire Protection
Sprinklers
Standpipes
Fire Protection Specialties
Other Fire Protection Systems
Electrical
Electrical Service & Distribution
Lighting and Branch Wiring
Communications & Security
Other Electrical Systems
E | EQUPMENT & FURNISHINGS
Equipment
Commercial Equipment
Institutional Equipment
Vehicular Equipment
Other Equipment
Furnishings
Fixed Furnishings
Movable Furnishings
F | SPECIAL CONSTRUCATION & DEMOLITION
Special Construction
Special Structures
Integrated Construction
Special Construction Systems
Special Facilities
Special Controls & Instrumentation
Selective Bldg Demo
Building Elements Demolition
Hazardous Components Abatement
G | BUILDING SITEWORK
Site Preparation
Site Clearing
Site Demolition & Relocations
Site Earthwork
Hazardous Waste Remediation
Site Improvements
Roadways
Parking Lots
Pedestrian Paving
Site Development
Landscaping
Site Civil/Mech Utilities
Water Supply & Distribution Systems
Sanitary Sewer Systems
Storm Sewer Systems
Heating Distribution
Cooling Distribution
Fuel Distribution
Other Civil/Mechanical Utilities
Site Electrical Utilities
Electrical Distribution
Site Lighting
Site Communications & Security
Other Electrical Utilities
Other Site Construction
Service Tunnels
Other Site Systems & Equipment
1 | Construction Systems
Construction Equipment
Temporary Safety
Temporary Security
Temporary Facilities
Weather Protection
2 | Space
Construction Activity Space
Analysis Space
3 | Information
Construction Information
Engineering Information
Record Information

## MOD
) | MODEL DEFINITION (MOD)
| Project Phase Deliverable |  |  | Planning |  |  | Design |  |  | Construction |  |  | Operations
Author File Format (if varies, specify in notes)
Application & Version
| Model Element Breakdown |  |  | Info | Resp Party | Notes | Info | Resp Party | Notes | Info | Resp Party | Notes | Info | Resp Party | Notes
| A | SUBSTRUCTURE
Foundations
Standard Foundations
Special Foundations
Slab on Grade
Basement Construction
Basement Excavation
Basement Walls
| B | SHELL
Superstructure
Floor Construction
Roof Construction
Green Roof
Interior Columns
Beams
Trusses
Exterior Enclosure
Exterior Walls
Curtain wall System
Exterior Windows - Glass Panels
Railing
Exterior Doors
Roofing
Roof Coverings
Roof Openings
| C | INTERIORS
Interior Construction
Partitions
Interior Doors
Fittings
Stairs
Stair Construction
Stair Finishes
Interior Finishes
Wall Finishes
Floor Finishes
Ceiling Grid
Drop Ceiling
Ceiling Finishes
| D | SERVICES
Conveying Systems
Elevators & Lifts
Escalators & Moving Walks
Other Conveying Systems
Plumbing
Plumbing Fixtures
Domestic Water Distribution
Sanitary Waste
Rain Water Drainage
Other Plumbing Systems
HVAC
Energy Supply
Heat Generating Systems
Cooling Generating Systems
Distribution Systems
Terminal & Package Units
Controls & Instrumentation
Systems Testing & Balancing
Other HVAC Systems & Equipment
Fire Protection
Sprinklers
Standpipes
Fire Protection Specialties
Other Fire Protection Systems
Electrical
Electrical Service & Distribution
Lighting and Branch Wiring
Communications & Security
Other Electrical Systems
| E | EQUPMENT & FURNISHINGS
Equipment
Commercial Equipment
Institutional Equipment
Vehicular Equipment
Other Equipment
Furnishings
Fixed Furnishings
Movable Furnishings
| F | SPECIAL CONSTRUCATION & DEMOLITION
Special Construction
Special Structures
Integrated Construction
Special Construction Systems
Special Facilities
Special Controls & Instrumentation
Selective Bldg Demo
Building Elements Demolition
Hazardous Components Abatement
| G | BUILDING SITEWORK
Site Preparation
Site Clearing
Site Demolition & Relocations
Site Earthwork
Hazardous Waste Remediation
Site Improvements
Roadways
Parking Lots
Pedestrian Paving
Site Development - topography
Landscaping
Site Civil/Mech Utilities
Water Supply & Distribution Systems
Sanitary Sewer Systems
Storm Sewer Systems
Heating Distribution
Cooling Distribution
Fuel Distribution
Other Civil/Mechanical Utilities
Site Electrical Utilities
Electrical Distribution
Site Lighting
Site Communications & Security
Other Electrical Utilities
Other Site Construction
Service Tunnels
Other Site Systems & Equipment
| 1 | Construction Systems
Construction Equipment
Temporary Safety
Temporary Security
Temporary Facilities
Weather Protection
Construction Lay down
| 2 | Space
Department Assignments
Room Assignments
Diagrammatic Phasing
Occupancy
Construction Activity Space
Analysis Space
| 3 | Information
Construction Information
Engineering Information
Record Information
| 4 | Datum
Grid
Levels
Origin