## Slide 1: BIM EXECUTION PLANNING PROCESS
CD (MP) Engineering Analysis Model
Planning
Owner
Programming
Validate Program
Schematic Design
Architect
Design Authoring
Author Schematic Design
Design Development
Architect
Design Authoring
Author Design Development
Construction Documents
Architect
Detailed Map
Author Construction Documents
Operations
Contractor
Record Model
Compile Record Model
Schematic Design
Architect
Virtual Prototyping
Develop Virtual Prototype
Schematic Design
Contractor
4D Modeling
Create 4D Model
Schematic Design
Engineer
Engineering Analysis
Perform Engineering Analysis
Schematic Design
Architect
3D Macro Coordination
Perform 3D Coordination
Schematic Design
Contractor
Cost Estimation
Perform Cost Estimate
Design Development
Architect
Virtual Prototyping
Develop Virtual Prototype
Design Development
Contractor
4D Modeling
Create 4D Model
Design Development
Engineer
Engineering Analysis
Perform Engineering Analysis
Design Development
Architect
3D Macro Coordination
Perform 3D Coordination
Design Development
Contractor
Cost Estimation
Perform Cost Estimate
Construction Documents
Architect
Virtual Prototyping
Develop Virtual Prototype
Construction Documents
Contractor
4D Modeling
Create 4D Model
Construction Documents
Engineer
Engineering Analysis
Perform Engineering Analysis
Construction Documents
Architect
3D Macro Coordination
Perform 3D Coordination
Construction Documents
Contractor
Detailed Map
Perform Cost Estimate
Program Model
Schematic Design Cost Estimation
Schematic Design 4D Model
Schematic Design Engineering Analysis Model
Schematic Design 3D Macro Coordination Model
Schematic Design 3D Virtual Prototypes
Architectural Model
MEP Model
Structural Model
Civil Model
Schematic Design
Architectural Model
MEP Model
Structural Model
Civil Model
Design Development
Architectural Model
MEP Model
Structural Model
Civil Model
Construction
Documents (WP)
Design Development Cost Estimation
Design Development 4D Model
Design Development Engineering Analysis Model
Design Development 3D Macro Coordination Model
Design Development 3D Virtual Prototypes
CD (MP) Cost
Estimation
CD (MP)
4D Model
CD (MP) 3D Macro Coordination Model
CD (MP) 3D Virtual Prototypes
CD (MP) 3D Micro
Coordination Model
Record Model
END PROCESS

## Slide 2: EXISTING CONDITIONS MODELING
Laser Scan Model
END PROCESS
START PROCESS
Responsible Party
Collect Current Site Conditions Data
Responsible Party
Survey Existing Facilities
Responsible Party
Survey Existing Site Conditions
Responsible Party
Collect Data through Photographs
Responsible Party
Laser Scan Existing Conditions
Survey Model
Existing Conditions Information Model
Responsible Party
Compile Existing Conditions Information
Geotechnical Report
Historical Site / Facilities Information
GIS Data

## Slide 3: COST ESTIMATION
3D Model
Quantity Takeoff for Assemblies
YES
NO
Cost Reports
Analysis Method
Cost Database
Cost Estimate for Assemblies
END PROCESS
START PROCESS
Model ready for QTO/Cost Analysis?
Results acceptable?
Contractor
Establish Cost Estimates
Contractor
Adjust BIM for Takeoff
Contractor
Export BIM for Analysis
Contractor
Develop Quantities Schedule
Contractor
Review Quantities
Contractor
Evaluate Methods for Assembly Construction
Contractor
Organize Quantities to Cost Data
Contractor
Calculate Costs from Quantities
Contractor
Review Costs/Results
Contractor
Incorporate Contingencies/ Overhead
Results in compliance with cost target?
YES
NO
Contractor
Incorporate Contingencies/ Overhead
YES
NO

## Slide 4: 4D MODELING
3D Model
END PROCESS
START PROCESS
4D Modeler
Link 3D Elements to Activities
All Disciplines
Set Construction Sequencing and Flow
All Disciplines
Establish Information Exchange Requirements
All Disciplines
Prepare/Adjust Schedule
All Disciplines
Create New of Modify Previous 3D Model
Productivity Information
Lead Times
Schedule (Draft)
4D Model (Draft)
All Disciplines
Validate Accuracy of 4D Models
Schedule
4D Model
All Disciplines
Review 4D Model/Schedule
YES
NO
Schedule optimized?
YES
NO
Model correct?

## Slide 5: SITE ANALYSIS
Site Analysis Model
YES
NO
Site Investigation Data
END PROCESS
START PROCESS
Is site acceptable and available?
Is building location acceptable?
Responsible Party
Analyze Area Data
Responsible Party
Select a Building Site Location
Responsible Party
Analyze Project Site Data
Responsible Party
Generate Site Analysis Model
Responsible Party
Determine Building Location and Orientation
YES
NO

## Slide 6: PROGRAMMING
Site Analysis Model
ACCEPTABLE
NOT ACCEPTABLE
Site Information
END PROCESS
START PROCESS
Is site acceptable and available?
Owner
Create Program
Architect
Generate Conceptual Building Layout
Existing Conditions Model
Program Model
Owner
Identify Area Requirements
Owner
Identify Building Use/Type
Owner
Identify Cost Targets
Start Design Programming
Owner
Identify Final List of Requirements

## Slide 7: DESIGN AUTHORING
All Disciplines
Identify Models Required
Architect
Develop Initial Architecture Model
All Disciplines
Identify Content for Model Creation
Engineer
Create Schematic Design MEP Model
All Disciplines
Create Other Models (as needed)
Engineer
Create Schematic Design Structural Model
Architect
Create Schematic Design Architecture Model
Program Model
Schematic Design
Architectural Model
MEP Model
Structural Model
Other
END PROCESS
Engineer
Create Development Architecture MEP Model
All Disciplines
Create Other Models (as needed)
Engineer
Create Development Architecture Structural Model
Architect
Create Design Development Architecture Model
Engineer
Create Construction Documentation MEP Model
All Disciplines
Create Other Models (as needed)
Engineer
Create Construction Documentation Model
Architect
Create Construction Documentation Architecture Model
Does the model
meet the
requirements?
Does the model
meet the
requirements?
Does the model
meet the
requirements?
Design Development
Architectural Model
MEP Model
Structural Model
Other
Construction Documentation
Architectural Model
MEP Model
Structural Model
Other
START PROCESS
Preliminary Architecture Model
YES
NO
YES
NO
YES
NO
Parametric Modeling Content

## Slide 8: DESIGN REVIEW
Design Model
END PROCESS
START PROCESS
Design acceptable?
All Disciplines
Compile Design Review Feedback
Design Review Information
All Disciplines
Compile Info for O & M Review
Architect
Create Virtual Mockups
All Disciplines
Compile Model for Constructability Review
Facility Manager
Perform O & M Review
Architect/User
Perform End User Review
Contractor
Perform Constructability Review
Return to Design Authoring
YES
NO

## Slide 9: ENERGY ANALYSIS
Design Model
END PROCESS
START PROCESS
Results acceptable?
Mechanical Engineer
Review Energy Analysis Results
Energy Analysis Model
Responsible Party
Adjust BIM for Energy Analysis
Mechanical Engineer
Analyze Energy Demand and Consumption
Mechanical Engineer
Prepare Report for Documentation
Mechanical Engineer
Assign Outside Design Criteria and Energy Targets
Contractor
Assign Construction Types to Building Elements
Mechanical Contractor
Create and Assign Thermal Zones
YES
NO
Space Type Library
Mechanical System Library
Construction Type Library
Energy Takeoff
Analysis Method
Weather Data
Mechanical Engineer
Export BIM for Analysis
Is model ready for simulation?
YES
NO
Note: This map was developed from a review of the bSa/OGC AECOO-1 Testbed Project

## Slide 10: STRUCTURAL ANALYSIS
Architecture Model
Structural Analysis Model
Soil Data
Wind Loads
Structural Design Model
END PROCESS
START PROCESS
Is site acceptable and available?
Structural Engineer
Export Model to Structural Design Application
Structural Engineer
Update Structural Design Model
Structural Engineer
Generate Structural Layout
Structural Engineer
Generate Structural Design Model
Structural Engineer
Export Model to Structural Analysis Application
Structural Engineer
Analyze Model
YES
NO
Seismic Loads
Snow Loads
Structural Design Model (Draft)

## Slide 11: LIGHTING ANALYSIS
Architecture Model
Lighting Analysis Model
Solar Data
Weather Data
Lighting Design Model
END PROCESS
START PROCESS
Is building lighting acceptable?
Lighting Engineer
Export Model to Lighting Design Application
Lighting Engineer
Update Lighting Model
Lighting Engineer
Generate Lighting Layout
Lighting Engineer
Generate Basic Lighting Model
Lighting Engineer
Export Model to Lighting Analysis Application
Lighting Engineer
Modify Model for Analysis
YES
NO
Lighting Design Model (Draft)
Structural Model
Other Applicable Models
Lighting Engineer
Identify Lighting Criteria
Lighting Engineer
Analyze Model for Lighting Levels
Lighting Engineer
Analyze Model for Daylighting
Lighting Engineer
Analyze Model for Density Levels

## Slide 12: DESIGN COORDINATION
Coordination Model by Discipline
Company Implementation Standards
Contract Requirements
Coordination Model
END PROCESS
START PROCESS
Any collisions?
All Disciplines
Create Discipline Models
All Disciplines
Identify Solutions to Collisions
BIM Coordinator
Compile Composite Model
YES
NO
Design Model
BIM Coordinator
Perform Collision Detection
Information Exchange Requirements
All Disciplines
Establish a Protocol to Address Collisions
All Disciplines
Develop Schedule for Coordination
All Disciplines
Define Information for Discipline Models
BIM Coordinator
Define Coordination Meeting Location
BIM Coordinator
Create Model Sharing System
All Disciplines
Define the Areas of Coordination
Start Design Coordination Process

## Slide 13: SITE UTILIZATION PLANNING
Schedule
Site Utilization Plan
END PROCESS
START PROCESS
Are all phases analyzed (occurs for each phase)?
Contractor
Identify Construction Phases
Contractor
Distribute Plan to Various Parties
YES
NO
Construction Equipment Libraries
Contractor
Insert Phased Staging Areas
Contractor
Determine Temporary Facilities
Contractor
Add Construction Equipment
Design Model
Existing Site Conditions Model
Contractor
Analyze Site Layout for Space and Time Conflict
Contractor
Analyze Site Layout for Phase Transition
Is plan acceptable?
YES
NO

## Slide 14: 3D CONTROL AND PLANNING
Construction Model
END PROCESS
START PROCESS
Is model acceptable?
Contractor
Determine Scope of Work to be Analyzed
Contractor
Generate Construction Plans
YES
NO
3D Controls Report
Contractor
Analyze Various Methods
Contractor
Model Alternative Methods
Contractor
Identify Alternative Construction Methods
Design Model
Site Utilization Model
Contractor
Coordinate Construction Sequences
Contractor
Compare and Select Options
Is construction sequence acceptable?
YES
NO
Design Specifications and Intent
Schedule, Cost, and Labor Info
Construction Families and Libraries

## Slide 15: RECORD MODELING
Record Model
END PROCESS
START PROCESS
Is model acceptable?
Owner
Identify Information Requirements
YES
NO
COBIE Requirements
Facility Manager
Compile Information in FM Application
Facility Manager
Generate Additional Required Information
Facility Manager
Compile Information
Equipment Information
Project Submittal Information
Design Model
4D Model
Coordination Model

## Slide 16: MAINTENANCE SCHEDULING
Schedule
START PROCESS
Correct?
Facility Manager
Collect Building System Data
YES
NO
Productivity Information
Responsible Party
Perform Maintenance
Facility Manager
Prepare/Adjust Schedule
Facility Manager
Interpret Data for Maintenance Needs
Sensor Information
CMMS Information
Warranty and Specification Information
Record Model
Facility Manager
Regenerate Maintenance Data
Responsible Party
Validate Equipment Performance
END PROCESS

## Slide 17: BUILDING SYSTEMS ANALYSIS
Building Performance Analysis Model
START PROCESS
Results acceptable?
Responsible Party
Adjust BIM for Performance Analysis
YES
NO
Performance Targets
Facility Manager
Perform Maintenance
Responsible Party
Prepare/Adjust Schedule
Energy Analysis Model
Facility Manager
Validate Equipment Performance
Sensor Data
Other Performance Data
Performance Costs
Weather Data
Record Model
Building Performance Analysis Output
Facility Manager
Interpret Data for Maintenance Needs
Facility Manager
Interpret Data for Maintenance Needs
Responsible Party
Prepare/Adjust Schedule
Is model ready for simulation?
YES
NO
END PROCESS