## Sheet1
Issue | Detail | Standard Straight Time 40 Hour per Week Schedules |  |  |  |  | Innovative Scheduling Techniques |  | Overtime Schedules | [5 empty] | Shutdown Schedules
|  | 5-8 Hr Days | 4-10 Hr Days | 2-9 Hr & 2-11 Hr Days | 4-9 Hr & 1-4 Hr Days | 2nd/3rd Shifts | Rolling Schedules (4-10, 3-12, 4-12s) | 4-10 Hr Days & 3-13 Hr Days | 5-9 Hr Days | 5-10 Hr Days | 6-8 Hr Days | 6-10 Hr Days | 5-10 Hr & 1-8 Hr Days | 7 -10 Hr 7 -12 Hr Days | Double Shift 6-10 Hr or 7-12 Hr
Performance | Safety | Eight-hour workdays are the safest because crews are not fatigued and can remain focused throughout the workday. | Fatigue associated with 10 to 11 hour shifts can reduce safety. The extra day of rest associated with these schedules helps offset the fatigue factor. |  |  | Fatigue related to the 2nd or 3rd shift can reduce safety performance. | Fatigue associated with 10 to 11 hour shifts can reduce safety. The extra day of rest associated with these schedules helps offset fatigue factor. |  | Fatigue amplifies the incidence of job site accidents.
|  |  | 10 and 11 hour shifts can be risky during shortened day light hours of the winter months. |  |  | When working at night, poor lighting conditions can reduce safety. | Extended 10 and 11 hour shifts can be risky during shortened daylight of winter months.
| Absenteeism | Standard 5-8s were rated second for effectiveness in minimizing absenteeism behind 4-10s. | Absenteeism is lowest under these scheduling techniques because workers have a weekday off to conduct personal business. |  |  | Odd hours of 2nd shift lead to increased fatigue, can be difficult for workers to maintain. Absenteeism becomes a larger issue in comparison to the 1st shift. | Absenteeism is reduced because workers lose 25% to 33% of weekly pay for a missed day rather than 20% under a 5-8s schedule. |  | Fatigue as well as needed time off for personal business will result in greater levels of absenteeism under overtime and shutdown schedules.
|  |  | Absenteeism is reduced because workers lose 25% of weekly pay for a missed day rather than 20% under a 5-8s schedule. | [7 empty] | Problems with absenteeism are the greatest when the number of workdays per week is extended to 6 or 7 days.
Issue | Detail | Standard Straight Time 40 Hour per Week Schedules |  |  |  |  | Innovative Scheduling Techniques |  | Overtime Schedules | [5 empty] | Shutdown Schedules
|  | 5-8 Hr Days | 4-10 Hr Days | 2-9 Hr & 2-11 Hr Days | 4-9 Hr & 1-4 Hr Days | 2nd/3rd Shifts | Rolling Schedules (4-10, 3-12, 4-12s) | 4-10 Hr Days & 3-13 Hr Days | 5-9 Hr Days | 5-10 Hr Days | 6-8 Hr Days | 6-10 Hr Days | 5-10 Hr & 1-8 Hr Days | 7 -10 Hr 7 -12 Hr Days | Double Shift 6-10 Hr or 7-12 Hr
Productivity | Fatigue | Low worker fatigue and high morale combine to make these schedules very productive. |  |  |  | 2nd and 3rd shifts are least productive scheduling options because of management and coordination difficulties. | Little productivity loss due to fatigue on rolling schedules. | No significant difference from rolling 4-10s. | Productivity reduced due to worker fatigue on long duration overtime schedules. | [5 empty] | Productivity reduced due to worker fatigue from overtime and abnormal hours.
| Supervision | Minimizes unproductive time by facilitating materials procurement and placing less pressure on detailing and fabricating. | Reduces number of occurrences of work starts and stop times of the workweek from 5 to 4. |  |  | A smaller scope facilitates coordination, planning, and supervision of the second shift. | Unlike standard 4-10s schedule, a rolling schedule requires crews to work different days each week. This makes it difficult for workers to take a second job over the weekend and keeps them fresh for the workweek. | No significant difference from rolling 4-10s.
| Downtime | Down time reduced because crews have constant access to support groups, expediting solutions to unexpected problems. | By working 4 days rather than 5 there are 2 fewer breaks, 1 less lunch, and 1 less sequence of startups and shutdowns. |  |  | 2nd shift may consist of “lower tier” less productive workers if preventative care is not taken. |  | No significant difference from rolling 4-10s.
Schedule has added benefit of a built-in makeup day when a day is lost to weather or a holiday.
| Macro Study | Macro Study: 5-8 schedule has an Avg. P.I. of 1.04. | Macro Study: 4-10 schedule has an Avg. P.I. of 1.06. |  |  | Use of two shifts can increase productivity and control cost if used for a well defined relatively small scope of work. | Rolling 4-10 schedule includes no overtime. Crews avg. 35 hours per workweek so they are less fatigued. | No significant difference from rolling 4-10s. |  | Macro Study: 5-10 schedule has an Avg. P.I. of 0.90 |  | Macro Study: 6-10 schedule has an Avg. P.I. of 0.78. |  | Macro Study Equation not applicable outside stated limits.
Worker productivity is a function of project size and the number of hours worked per crewmember per week. The following equation can be used to estimate productivity based on these factors:
Productivity Index (Budgeted/Actual) = 1.44 - [0.00947*(Average Hours per Worker per Week)] - [2.2E-7*(Actual Total Work Hours)].
Note: Equation is designed for use on projects within the following limits: (31.6-66.6 Average Hours per Worker per Week) , (700 - 1.4 Million Work Hours)
Issue | Detail | Standard Straight Time 40 Hour per Week Schedules |  |  |  |  | Innovative Scheduling Techniques |  | Overtime Schedules | [5 empty] | Shutdown Schedules
|  | 5-8 Hr Days | 4-10 Hr Days | 2-9 Hr & 2-11 Hr Days | 4-9 Hr & 1-4 Hr Days | 2nd/3rd Shifts | Rolling Schedules (4-10, 3-12, 4-12s) | 4-10 Hr Days & 3-13 Hr Days | 5-9 Hr Days | 5-10 Hr Days | 6-8 Hr Days | 6-10 Hr Days | 5-10 Hr & 1-8 Hr Days | 7 -10 Hr 7 -12 Hr Days | Double Shift 6-10 Hr or 7-12 Hr
Project Cost | Average Rate of Pay | Absence of overtime pay, shift premiums, and craft inefficiencies make this a very cost effective schedule. | Union regulations in some areas may require overtime pay after 8 hours in the workday. Working extended shift schedules may be impractical in these areas. |  |  | Project costs increased by this schedule due to need for supervision overlap between shifts, shift premium wage, and fatigue related reduction in productivity during the 2nd shift. | Compared to overtime or multiple shift schedules, which result in fatigue related productivity losses and require greater amounts of overtime pay or a shift premium, these schedules may be more cost effective approaches to schedule compression. |  | Probable fatigue related reductions in labor productivity along with overtime wages of typically 100% to 200% base pay will result in increased project costs. | [5 empty] | Project costs are increased by this schedule due to the need for a supervision overlap between shifts, a shift premium wage, an overtime wage and also because of the fatigue related reduction in productivity.
| Coordination | High productivity levels maintained for extended durations making productivity easy to schedule and track / cost easy to maintain. | Particularly cost effective on out of town projects. Reduces wear and tear on vehicles. Reduces paid overnight stays for crewmembers. |  |  | When multiple shifts are used, mistakes can be very costly due to the increased rate of man hour expenditure in comparison to a single shift schedule.
Multiple shifts can be a more cost effective schedule compression method than overtime because shift premiums are generally less expensive than overtime wages.
Issue | Detail | Standard Straight Time 40 Hour per Week Schedules |  |  |  |  | Innovative Scheduling Techniques |  | Overtime Schedules | [5 empty] | Shutdown Schedules
|  | 5-8 Hr Days | 4-10 Hr Days | 2-9 Hr & 2-11 Hr Days | 4-9 Hr & 1-4 Hr Days | 2nd/3rd Shifts | Rolling Schedules (4-10, 3-12, 4-12s) | 4-10 Hr Days & 3-13 Hr Days | 5-9 Hr Days | 5-10 Hr Days | 6-8 Hr Days | 6-10 Hr Days | 5-10 Hr & 1-8 Hr Days | 7 -10 Hr 7 -12 Hr Days | Double Shift 6-10 Hr or 7-12 Hr
Project Cost | Offsite Support | Infrastructure and technical support routinely available during normal business and routinely extended hours. |  |  |  | Offsite support limited and must be planned and prearranged. | Offsite support limited and must be planned and prearranged. |  | Infrastructure and technical support routinely available during normal business and routinely extended hours. |  | Offsite support limited and must be planned and prearranged. |  |  |  | Offsite support limited and must be planned and prearranged.
| Contractor Intefaces | Majority of contractors work 5-8hr days. Schedule is likely to allow continuous and complete interface. | If it is necessary to provide assistance to contractors working a five day schedule, it may require the use of overtime or alternative schedules. |  | Provides five days of contact with other contractors on site. | Requires careful coordination with contractors operating on alternate shifts. | Good subcontractor interface provided by this schedule. |  | Would provide adequate coverage as most subcontractors work 5-8 hr days per week. | [5 empty] | Would provide good coverage as most subcontractors work 5-8 hr days per week.
| Union Impact | This is the baseline work schedule specified in many union labor agreements. | These schedules may be impractical in areas where labor agreements require O.T. pay after 8 hours in a day. |  |  | Unions require a 10% to 33% shift differential wage rate and/or 7 to 7 1/2 hours work for eight hours pay. | These schedule may be impractical in areas where labor agreements require O.T. pay after 8 hours in a day. |  | Unions gladly accept overtime schedules due to overtime wage rates of 150% to 200% the base wage.
Issue | Detail | Standard Straight Time 40 Hour per Week Schedules |  |  |  |  | Innovative Scheduling Techniques |  | Overtime Schedules | [5 empty] | Shutdown Schedules
|  | 5-8 Hr Days | 4-10 Hr Days | 2-9 Hr & 2-11 Hr Days | 4-9 Hr & 1-4 Hr Days | 2nd/3rd Shifts | Rolling Schedules (4-10, 3-12, 4-12s) | 4-10 Hr Days & 3-13 Hr Days | 5-9 Hr Days | 5-10 Hr Days | 6-8 Hr Days | 6-10 Hr Days | 5-10 Hr & 1-8 Hr Days | 7 -10 Hr 7 -12 Hr Days | Double Shift 6-10 Hr or 7-12 Hr
Project Cost | Craft | Long duration activities are sometimes hard to complete in an 8hr day, requiring use of O.T. | Less O.T. than 5-8s for concrete pours and hot welds. |  |  | NA | Overtime is required for weekend work. | Requires a minimum amount of overtime to complete long duration items. | Labor agreements generally require 150% base pay for overtime hours. Also common is a requirement for 200% base pay for all work conducted on Sundays and holidays.
[9 empty] | Planned O.T. costs are significant. |  | The premium cost for O.T. plus the loss in productivity results in an unreasonable inflation of the unit labor cost.
| Overhead | Same no. of people are required to support 5-8s as 4-10s. | Less personal time required off jobs. Average turnover is less on jobs using these schedules. |  |  | Would require two staffs resulting in highest overhead cost. |  |  | Same overhead costs associated with craft overtime. |  | Would result in significant O.T. to support added days schedule. |  |  |  | Would require two staffs resulting in highest overhead cost.
| Supervison | Same no. of direct supervisors for 5-8s, 4-10s, 2-9s&2-11s, and 4-9s&1-4. |  |  |  | Significant increase in supervision. Supervision overlap needed for continuity in communication. |  |  | Same overhead costs associated with craft overtime. |  | Would result in significant O.T. to support added days schedule. |  |  |  | Significant increase in supervision. Supervision overlap needed for continuity in communication.
| Tools | No significant difference, tools are generally a function of total craft activities over a standard 4 or 5 day work week. | [6 empty] | Extended work hours and work days may demand more frequent replacement and/or more accountability and control over tools to maintain cost ratios.
| Major Equipment | Requires more equipment starts and stops and forces maintenance to work Saturdays or night shifts making it difficult to obtain quality mechanics. | Better utilization of equipment because of fewer starts and stops. |  | Same as 5-8s. | Least desirable of all alternatives due to all maintenance (except breakdowns) being performed on afternoon or night shifts. |  |  | Can get higher weekly utilization from same basic equipment, will have to complete preventative maintenance on weekend and nightshifts at maximum shift operations. |  | Increased utilization of equipment will result in some savings, but six or seven day schedule will make preventative maintenance more difficult to perform. May require some additional equipment. |  |  |  | Increased utilization of equipment will result in some savings, but 24/7 coverage makes preventative maintenance very difficult. Will require additional equipment.
Allows more time for refueling at maximum shift operations, allows 3 day weekend for major maintenance.
Issue | Detail | Standard Straight Time 40 Hour per Week Schedules |  |  |  |  | Innovative Scheduling Techniques |  | Overtime Schedules | [5 empty] | Shutdown Schedules
|  | 5-8 Hr Days | 4-10 Hr Days | 2-9 Hr & 2-11 Hr Days | 4-9 Hr & 1-4 Hr Days | 2nd/3rd Shifts | Rolling Schedules (4-10, 3-12, 4-12s) | 4-10 Hr Days & 3-13 Hr Days | 5-9 Hr Days | 5-10 Hr Days | 6-8 Hr Days | 6-10 Hr Days | 5-10 Hr & 1-8 Hr Days | 7 -10 Hr 7 -12 Hr Days | Double Shift 6-10 Hr or 7-12 Hr
Duration | Mobilization Time | 5 mobilizations per week per employee at one hour each equals 5 hours per week per employee. | 4 mobilizations per week per employee at one hour each equals 4 hours per week per employee. |  | 5 mob. per week per employee at one hour each equals 5 hours per week per employee. | If worked in conjunction with a first shift, 2 to 3 times the mobilization time of a similar single shifted schedule. | Twice the mobilization time of a similar single shifted schedule. | 7 mobilizations per week per employee at one hour each equals 7 hours per week per employee. | 5 mobilizations per week per employee at one hour each equals 5 hours per week per employee. |  | 6 mobilizations per week per employee at one hour each equals 6 hours per week per employee. |  |  |  | Twice the mobilization time of a similar single shifted schedule.
| Schedule | Extensive industry experience with this schedule and understanding of associated productivity levels make durations predictable and maintainable. | Schedule easy to maintain due to built-in weather makeup day. |  |  | Nearly doubles the number of production hours each week helping to reduce project duration. | Allows 70 to 79 hours of production each week and maximizes productivity by rotating fresh crews and working during daylight hours only. |  | When used effectively, overtime schedules increase the number of production hours in the working week and thus reduce project duration. | [5 empty] | 24 hours per day 7 days per week coverage maximizes weekly production hours.
| Hrs/Wk | 40 hrs per week |  |  |  | 40 hrs per week (1st Shift) + 37.5 hrs per week (2nd Shift) + 35 hrs per week (3rd Shift) | 70 to 84 hrs per week | 79 hrs per week | 45 hrs per week | 50 hrs per week | 48 hrs per week | 60 hrs per week | 58 hrs per week | 70 to 84 hrs per week | 60 to 84 hrs per week per shift
| Maximum | 120 hrs per week | 80 hrs per week |  |  |  | 168 hrs per week | 119 hrs per week | 90 hrs per week | 100 hrs per week | 144 hrs per week | 120 hrs per week | 116 hrs per week | 168 hrs per week | 168 hrs per week
Issue | Detail | Standard Straight Time 40 Hour per Week Schedules |  |  |  |  | Innovative Scheduling Techniques |  | Overtime Schedules | [5 empty] | Shutdown Schedules
|  | 5-8 Hr Days | 4-10 Hr Days | 2-9 Hr & 2-11 Hr Days | 4-9 Hr & 1-4 Hr Days | 2nd/3rd Shifts | Rolling Schedules (4-10, 3-12, 4-12s) | 4-10 Hr Days & 3-13 Hr Days | 5-9 Hr Days | 5-10 Hr Days | 6-8 Hr Days | 6-10 Hr Days | 5-10 Hr & 1-8 Hr Days | 7 -10 Hr 7 -12 Hr Days | Double Shift 6-10 Hr or 7-12 Hr
Craft Workforce | Opinion | Workers are accustomed to the 5-8s schedule and enjoy the amount of free time it offers compared to overtime schedules. | Workers enjoy the extended weekends associated with these schedules. Especially popular during summer months because of added leisure time. |  |  | It can be difficult to staff a multishift project because they tend to be unpopular with the workforce. | There is equity between crews. Both get the same amount of premium pay for weekend work, so there is no jealousy. | There may be jealousy between shifts because of inequality. Weekend crew earns overtime pay and works only 39 hrs per week. | Workers enjoy overtime pay and may seek out overtime jobs. | [5 empty] | It can be difficult to staff a shutdown schedule because they tend to be unpopular with the workforce.
|  |  | Workers more likely to accept travel under this schedule because it requires one less day away from home/ family. | [5 empty] | Some workers may not be able to work longer days because of family and other obligations.
Crews enjoy flexibility offered by these schedules when they provide the option of working Friday or Saturday as overtime.
| Staffing | Is acceptable to most salaried employees. | Often requires five ten hour days work from salaried employees to avoid falling behind. |  |  | May be difficult to staff. | Would require additional staff and schedule would be continuously changing. |  | If overtime is paid to salaried personnel then it is an acceptable schedule, if not it is a demotivator. | [5 empty] | May be difficult to staff.
| Maintenance | Standard 40 hour per week schedules are generally acceptable and maintainable for workers. Turnover may be a problem if crews have the option of working a job that provides overtime pay. |  |  |  | Odd hours of shift work can be difficult for workers to maintain leading to increased turnover. | Roughly the same as a standard 40 hr per week schedule. 12 to 13 hour shifts may increase turnover in the long term. |  | More acceptable than 5-8hr day to compensate for travel time. These schedules can be expected to have some positive impact on turnover. |  | Although overtime pay is attractive to workers, these schedules do not allow adequate time with the family or for personal business. No improvement in turnover should be expected under these schedules. |  |  |  | Long hours and odd shifts are difficult to maintain. Increased turnover should be expected.
| Attraction | 5-8hr day schedule less attractive than overtime or a schedule providing a 3 day weekend. | Workers prefer schedules that offer an extended weekend and will commute additional miles as compared to 5-8s. |  |  | The odd hours of shift work can make locating workers difficult. | Workers prefer schedules that offer an extended weekend and will commute additional miles as compared to 5-8s. |  | Overtime pay would attract qualified craft workers to a project. Additional overtime increases the labor draw area and brings in commuters. | [5 empty] | The odd hours and long shifts make locating workers difficult.
Issue | Detail | Standard Straight Time 40 Hour per Week Schedules |  |  |  |  | Innovative Scheduling Techniques |  | Overtime Schedules | [5 empty] | Shutdown Schedules
|  | 5-8 Hr Days | 4-10 Hr Days | 2-9 Hr & 2-11 Hr Days | 4-9 Hr & 1-4 Hr Days | 2nd/3rd Shifts | Rolling Schedules (4-10, 3-12, 4-12s) | 4-10 Hr Days & 3-13 Hr Days | 5-9 Hr Days | 5-10 Hr Days | 6-8 Hr Days | 6-10 Hr Days | 5-10 Hr & 1-8 Hr Days | 7 -10 Hr 7 -12 Hr Days | Double Shift 6-10 Hr or 7-12 Hr
Effectivness Summary |  | Well suited for projects where turnaround time is not a major factor. | Good choice for out of town projects. |  |  | Multiple shifts double or triple the number of work hours per week making it an effective option for projects with a limited duration. | Very effective for projects with limited durations. Schedules listed above allow 70 to 84 hours of coverage per week. They maximize the daylight hours earned for each week and minimize nighttime construction. |  | When used effectively, overtime schedules increase the number of productive hours in the working week and thus reduce project duration. | [5 empty] | Shutdown schedules provide the ability to work twenty-four hours per day to complete a project as rapidly as possible and minimize the shutdown of a client’s services.
|  | Eight hour workdays are beneficial during shortened days of winter months. | Reduces travel time to and from jobsite. |  | Good choice for travel jobs that require overnight stays when contact with other contractors is necessary 5 days per week. | When a worksite is very congested, conflicting crews can be assigned to different shifts. | Best suited for projects that have been completely designed, detailed, and fully planned beforehand because access to support groups and materials procurement is reduced at certain times of the workday and workweek. |  | Overtime schedules can be applied when schedule compression is necessary and a shift or rolling schedule is not an option because of a lack of qualified workers to man two crews, or some other constraint.
|  |  | Reduces number of overnight stays when necessary due to travel distance to jobsite. |  |  | A 2nd or 3rd shift can be worked to avoid interrupting a client’s services during normal business hours. | Reduces congestion due to overmanning. Conflicting crews can be scheduled to different shifts to eliminate interferences. |  | During strong economic periods or in competitive markets, it may be necessary to operate under an overtime schedule in order to attract craftsmen with overtime wages.
Shifting helps alleviate strains on facilities, lunchrooms, restrooms, and parking space problems.
Projects will execute best only when all crews are working the same schedule. If a variety of schedules are worked by different trades, communication and coordination suffer and crews distract one another by beginning and ending their workday at dissimilar times.
Issue | Detail | Standard Straight Time 40 Hour per Week Schedules |  |  |  |  | Innovative Scheduling Techniques |  | Overtime Schedules | [5 empty] | Shutdown Schedules
|  | 5-8 Hr Days | 4-10 Hr Days | 2-9 Hr & 2-11 Hr Days | 4-9 Hr & 1-4 Hr Days | 2nd/3rd Shifts | Rolling Schedules (4-10, 3-12, 4-12s) | 4-10 Hr Days & 3-13 Hr Days | 5-9 Hr Days | 5-10 Hr Days | 6-8 Hr Days | 6-10 Hr Days | 5-10 Hr & 1-8 Hr Days | 7 -10 Hr 7 -12 Hr Days | Double Shift 6-10 Hr or 7-12 Hr
Summary of Potential Problems |  | May be difficult to attract labor to 40 hour project due to lack of overtime pay. |  |  |  | Requires detailed coordination between shifts and a double supervision effort. | Can be a terrific strain on salaried staff and support organizations (tool room, safety, etc.). |  | Worker fatigue associated with extended hours of work can result in productivity levels dropping to or below those of a five-eight hour days per week schedule. The result is an increase in labor costs with no reduction in project duration. | [5 empty] | Requires detailed coordination between shifts and a double supervision effort.
|  | Crews accustomed to overtime schedules may view this schedule as an indication that there is no need to hurry and thus work unproductively. | Extended hour shifts may be a poor choice during the winter months. Productivity and safety may be negatively impacted by darkness at the beginning and/or end of the shift. |  |  | Poor coordination results in low productivity and often a great deal of rework between shifts. | Workers may pace themselves to provide eight hours of work each day. Difficult to use during the shortened daylight of the winter months. | [7 empty] | Poor coordination results in low productivity and often a great deal of rework between shifts.
|  |  | When crews work a ten hour shift, they may pace themselves to provide 8 hours of productive work. |  |  | Labor productivity rates are decreased by job handoffs and twice as many startups and shutdowns each week. | Crafts working a R4-12 or R3-12 schedule will average 42 hours of work per week, overtime approval may be necessary. | There may be jealousy between shifts because of inequality. Weekend crew earns overtime pay and works only 39 hrs per week. | [6 empty] | Labor productivity rates are decreased by job handoffs and twice as many startups and shutdowns each week.
|  |  | Workers may take advantage of 3 day weekend by working a second job. This situation may reduce productivity. |  |  | Productivity is reduced to a greater extent during 2nd shift because of fatigue and reduced access to support groups. | Union labor agreements in some areas of the country may not include wording that would allow the use of a rolling schedule. | [7 empty] | Productivity is reduced to a greater extent during 2nd shift because of fatigue and reduced access to support groups.
Issue | Detail | Standard Straight Time 40 Hour per Week Schedules |  |  |  |  | Innovative Scheduling Techniques |  | Overtime Schedules | [5 empty] | Shutdown Schedules
|  | 5-8 Hr Days | 4-10 Hr Days | 2-9 Hr & 2-11 Hr Days | 4-9 Hr & 1-4 Hr Days | 2nd/3rd Shifts | Rolling Schedules (4-10, 3-12, 4-12s) | 4-10 Hr Days & 3-13 Hr Days | 5-9 Hr Days | 5-10 Hr Days | 6-8 Hr Days | 6-10 Hr Days | 5-10 Hr & 1-8 Hr Days | 7 -10 Hr 7 -12 Hr Days | Double Shift 6-10 Hr or 7-12 Hr
Suggestions for Effective Utilization |  | These schedules are excellent choices when turnaround time is not a major issue. Schedules result in consistently high levels of productivity. |  | This alternative to 4-10s can be used to create shorter shifts on travel days and longer shifts midweek when crews are away from home and family. | Good alternative to 4-10 schedule. Gives workers a half day off on Friday while still requiring time on site 5 days/week to communicate with other contractors and accept deliveries. | Coordination between shifts is improved by overlapping field supervision. When the second crew arrives they can be given instructions by their supervisor and begin working immediately. | Workers may have reservations if required to work on the weekend for straight time pay. If a premium is paid for weekend work, workforce morale is greatly improved. |  | Dramatic reductions in productivity often associated with overtime schedules can be minimized by holding schedules to ten-hour days, including breaks in the workday, and working no more than six days per week. | [5 empty] | Shutdown projects should be undertaken on a reimbursable contract basis only to minimize contractor risk.
[7 empty] | Supervision overlap is recommended at job handoff times to allow a smooth and productive transition between crews . | [7 empty] | Supervision overlap is recommended at job handoff times to allow a smooth and productive transition between crews .